PART A

# PROJECT DIGEST

| 1) Name of the Project: |  | Community Infrastructure Services Program (CISP) of AJK |
| --- | --- | --- |
| 2) Authorities Responsible for: i). Sponsoring: ii) Execution: iii) Operation & Maintenance: |  | Government of Azad Jammu Kashmir Local Government and Rural Development Department (LGRDD) Beneficiary Communities/Community Based Organizations |
| 3) Time required for completion of Program: |  | 60 Months (July 2002 – June 2007) |
| - Plan Provision: - i. If the program is included in Five year Plan, specify actual allocation: ii. If not included in the current plan, how is it now proposed to be accommodated (inter/inter-sectoral adjustments in allocation or other reason may be indicated). b. If project in not included in the plan what warrants its inclusion in the plan: |  | The program is proposed to be included in the AJK Government’s 10 year Perspective Plan (2001-2011) N.A N.A |
| - Relationship of the Project with the objectives of the sector: indicate the contribution of the project, quantified if possible to the targets in Five Year Plan and name the other projects (whether sanctioned or under preparation) which would program within the sector: |  | I. The project objectives are in line with the sector objectives viz: - Poverty alleviation - Focus on improving the well being of low-income communities. - Capacity building at the local levels for good governance - Encouraging community participation in local development. - Improvement of health indicators. II. A major portion of the program funds are proposed to be spent on providing infrastructure services including: - Water supply - Sanitation - Access (Roads and Bridges) - Street Pavement - Drainage - Street light Improvement of these services forms part of the sector objectives. |
| - Capital Cost of the Program |  | - Local PKR 2124.26 million - F.E Cost: PKR 170.00 million Total: PKR 2294.26 million (Excluding community share) |
| - Annual Recurring Expenditure after Completion: |  | The infrastructure will be operated and maintained by the participating community. |
| 8) Objectives of the Program preferably in quantifiable terms: |  | - As per general agreements reached during various missions’ of the IDA to the CISP, the objectives of the program will be as follows: - deliver cost effective and sustainable community development programs and sustainable infrastructure services to un-served and under-served, low income rural and urban communities using participatory community based approaches; - test models of similar approaches in peri-urban communities; - strengthen the role and capabilities of the Districts and lower level of local governments to extend technical, financial and management support to the community-based organizations (CBOs); - increase participation through community development and expanding the number and capacity of community based organizations (CBOs) to increase their participation in development activities; and - promote effective governance and accountability through improvement of operational procedures/guidelines, monitoring and evaluation. This also include financial, budgeting and processing procedures to ensure transparency in program implementation. II) The Program intends to improve living condition of: - about one million population of five hundred rural and seventy five urban communities. . |

Compiled and

Prepared by:	1.	Ghulam Murtaza Khan) ________________________________________

Deputy Project Director LGRDD

2.	(Syed Zaheer Hussain Gardezi),  _________________________________

Additional Project Director LGRDD

Reviewed and

Checked by:   	1.	(M. Saleem Bismil ) ___________________________________________

Director, LGRDD

2.	(Khawaja Ghulam Rasul) _______________________________________

Secretary LGB

Approved By:	(Sardar Riaz Ahmad Khan) __________________________________________

Secretary, LGRDD

#### PART B

PROJECT DESCRIPTION

| - Location of the Program: |  | Azad Jammu and Kashmir |
| --- | --- | --- |
| - Existing facilities: Decentralized Planning and Implementation: Community Development Infrastructure Upgrading and Services: |  | CISP comprises three components; (i) decentralized Planning and Implementation; (ii) Community Development; and (iii) Infrastructure Upgrading and Services. A description of the current situation in each of these is given below:- 1. Decentralized Planning and Implementation: At present planning and implementation processes are divided between districts and state offices with top down approach generally prevailing. Identification of community schemes is done at the Local Council/Markaz/ District levels. Community involvement needs further strengthening. The project communities which implement the community schemes are mostly unregistered. This ‘loose’ relationship often hampers proper financial close of the completed schemes. - Due to lack of proper community mobilization, organization and training, selection of sites often suffers from biases. - Approval of all schemes is normally done at the state level. - Implementation is normally done with the active involvement of district offices. 2. Community Development - At present there are unregistered Water and Sanitation Committees (WSCs) and informal groups in about 500 villages. Proper auditing of accounts in the WSCs is yet to be instituted. - Formal community based organizations (CBOs) to implement schemes are evolving but at very slow pace. - Women representation is almost non-existent. - Capacity to develop community action plans is minimal. - Lack of trained community workers/leaders to ensure sustainability of schemes. - Lack of authority on use of government development funds at the community and users groups level. - Lack of training on issues of health, hygiene, sanitation, organization and campaigns etc. 3. Infrastructure Upgrading and Services: The extent, age and condition of the existing infrastructure varies from community to community and ranges from essentially non-existent, through aged and dilapidated to recent but poorly maintained. - Water supply schemes are mostly spring based in the Northern parts of AJK and in some plain areas of the Southern parts of AJK ground water (dug well, hand pump and boreholes) is used. Maintenance is generally below the standards, unofficial connections to the supply network cause decreases in delivery pressure, and leakage in the supply network is generally a significant problem. Main and distribution pipelines in urban and other densely populated areas are often located along sullage water drains providing the possibility of drawing contaminated water into the line through leaking joints. The quality of the water is poor in some cases. About 40% population is yet to be provided with piped water facilities. - Drainage (sullage and stormwater flow) facilities comprise katcha and pucca drains along the roads/streets/pathways of the settlements. These are poorly maintained in the overwhelming majority of cases, are generally of inadequate size for the flows, many are discontinuous (i.e. not interconnected), many have no outfall and there is no treatment of the waste water. This situation generally results in the drains overflowing into the streets, collecting in low points and forming puddles of stagnant water throughout the community. In urban slum settlements and peri-urban inhabitations, the situation is often aggravated by discharge of human waste into the drainage channels. - Sanitation facilities are mostly rudimentary with many properties having no latrine facilities whatsoever. In such cases residents usually use the fields adjacent to the settlements. Where latrines exist they are mostly not properly used and their maintenance is highly neglected. Overall availability of latrines with the households is about 40% but in the case of rural areas this facility is still below 20%. There are not available reasonable facilities of Public/Community latrines. - Solid waste disposal practices vary, with waste in rural and some semi urban areas generally comprising organic matter which itself gets composted at dumping places and some times it is burnt by the residents. In urban areas non-organic waste is also generated and it is generally collected by the urban local councils and transported to the dumping sites. - In most communities storage of waste is unorganized and waste is often deposited in public places/streets/roads from where it is scattered into the streets by the wind and by scavenging animals, resulting in unhygienic and unsightly conditions in the community. - Accesses to and within communities may be paved (brick, stone, concrete, black topped) but many, particularly more minor streets and access way in rural communities, are kutcha. The paved streets are generally inadequately maintained, many in need of extensive Repair/reconstruction or are buried by over burden. Unpaved streets and pathways become impassable in the rainy season, generate dust nuisance in summer and generally make pedestrian and vehicular access difficult. The communities living across the rivers and streams face access difficulties where nearby crossings are not available. - The institutions, the government departments and local councils which are responsible for delivery of infrastructure are not successful in achieving the targets, as required, due to: - Insufficient management skills - Lack of resources |
| - Description of Program History: Current Indicators Policy Framework |  | - History: Azad Jammu and Kashmir with an area of 13297 Sq. Km. has a population of 2.9 million (1998 census) about 88% of the population lives in the rural areas. About 40% of the population lives below the poverty line. An IDA assisted Rural Water Supply and Sanitation Program Project (RWSSP), spreading over 8 years implementation span and costing about 1210 million rupees, was completed by the LGRDD in 2000. Performance of this Program Project has been highly satisfactory. Under this project, 1600 drinking water supply schemes for a population of about one million were selected and implemented. Majority of these schemes have been functioning under the formal and informal arrangements of the beneficiary communities. Success of this program project persuaded the Govt. of AJK to plan and implement an other community based program project that should address drinking water supply problems of the remaining communities and along the water supply schemes should also provide other community based infrastructure and services to the low income communities both in urban and rural areas. The World Bank indicated their interest in providing financial assistance to the new expected project in which lessons learnt from the RWSSP and the World Bank assisted community infrastructure project of the NWFP could be practiced and further developments in the community based approaches could be achieved. - Current Indicators: Some of the current indicators, detailed below provide the basis for investment in the program under the new project: - Access to Road/Transport: Link roads are not available in most rural areas, tracks for 4x4 Jeep exist in some areas. Public/private transport plies on the main roads only which entails 2-3 Km. of walking to destination. After sunset transport is usually not available. Similarly, access to remote areas is difficult due to inadequate foot bridges, pathways. - Water Supply/Sanitation: About 81% urban and 55% rural population has access to water supply. Overall 40% households have latrines while in rural areas less 20% households have this facility. - Drainage: While most of the urban areas have planned drainage systems, the rural areas have little or none. Investments made in providing access/roads without proper drainage in such areas are always at risk of being washed away. - Street Pavements/Lighting: Settlements of urban/peri-urban areas having the poor inhabitants are mostly unplanned and their streets are mostly unpaved and without streetlight facilities. - Solid Waste Management (SWM): Present arrangements are grossly below the standard. Collection and disposal of solid wastes is required to be imposed specially at district headquarters. - Tagging/Numbering Streets: At present, there is no organized system of identifying houses/properties in the low income communities in the urban/peri-urban and slum areas. - Trunk Infrastructure: Infrastructure provided under the previous projects and to be provided under CISP schemes will be integrated into the trunk/main infrastructure. These linkages will ensure better coordination of management of the facilities. This also includes new and appropriate technology. - Community Organization: At present the communities are organized on the basis of Biradarees (clans), political affiliations and income levels. While most of the development schemes are planned and implemented by the various line departments of the Government. Participation of the community is low with the shift in emphasis to the bottom – top approach in planning/implementing infrastructure. The communities are expected to play a leading role in CISP. However this would entail proper training, motivation, upgrading of the skills and effective involvement of women. - Policy Framework: To guide the community based approach to basic infrastructure services in AJK, it has been agreed with the World Bank that a policy framework would need to be formulated to achieve the objectives of the CISP. The policy framework would be developed and made applicable keeping in view the following guiding principles: |
|  |  | - provision of integrated social, economic and physical infrastructure and services to low income communities in rural and urban areas to be selected based on the community demands. - priority to those communities which demonstrate commitment through their capacity for social organization and financial and other cost sharing contribution; - communities organized into CBOs or user committees to participate in and be jointly responsible for the identification, design, and implementation of community development activities, infrastructure and services and to be fully responsible for their subsequent O&M; - communities to contribute land required and at least a 20% share of the capital costs of infrastructure in cost sharing arrangements to be agreed (other than primary infrastructure); - devolution of powers and authority to the lower tiers of the Government and elected local governments; - empowerment of the beneficiary communities through their CBOs and organizations; - ensuring that the essentials of the good governance are promoted through the CISP activities; - local councils/governments to be effectively involved in the planning and implementation of the CISP activities; and - a uniform policy to align other government programs with this policy framework of the CISP. |
| Project Development Process Proposed Standards and Scheme Designs Environmental Aspects Social Aspects Selection Criteria Eligibility |  | 4. Project Development Process: (a) Community mobilization, awareness training and project identification; (b) community participation in project preparation and design, (c) implementation of infrastructure and community development activities; (d) hand-over of completed assets for operation and maintenance and registration process. As part of this process each eligible community, with assistance from the CISP, is to prepare a Community Action Plan (CAP) which has been discussed with the local council/Local Government approved by the Program Policy Coordination Committee (PPCC) and reviewed by IDA, if required. The CAP includes: (a) the organizational structure of community organization, including office bearers, project related committees and user groups, membership, representation of women's and other interested groups' etc. (b) an assessment of the basic infrastructure needs of the community; (c) the selected infrastructure design, including summary of other technical options considered, community development, training and hygiene awareness requirements; (d) a statement of investment and O&M costs, sources of funding and timetable for resource mobilization; (e) arrangements for collection, safekeeping and accounting for the community's contribution; and (f) an implementation plan, including arrangements and a timetable for procurement, supervision and monitoring and evaluation. 5. Proposed Standards and Scheme Designs The planning and Design standards adopted for CISP are flexible, cost effective and, in most cases, compatible with the other line agencies dealing in provision of similar basic infrastructure through various schemes. The CISP standards and scheme designs will be reviewed and commented by the IDA/World Bank, if so required. However, design standards of the RWSSP will be used to the extent applicable in the case of drinking water supply schemes. 6. Environmental Aspects The Environmental Assessment, prepared by the Environmental Protection Agency (EPA) AJK, concludes that the impact of the project is beneficial or, in some instances, neutral or positive. The requirements of the environment framework will be complied with while selecting and implementing the CISP activities. Important decisions in this regard are given here below: - Update both EMF and Operational Manual (which is derived from the EMF), as per comments/suggestions; - Carry out further consultations and test forms and checklists with project staff and communities; and - Once revisions are completed, the updated EMF will also be made available in public locations - Environmental Manual and Resource Kit will be developed for use by program staff. The environmental screening and mitigation guidelines and checklists already provided in the EMF will be refined and expanded and included in the Environment Manual and Resource Kit for use by program staff. The activity would be financed under PHRD grant. - Services of an environment specialist will be hired. Outline TOR and schedule are provided in the EMF document and guidelines. This activity will be financed under the PHRD grant and thereafter if required under the program. - EPA will continue to act as a service provider during preparation and implementation of the program, and the required financial resources will be provided to EPA from the CISP. (a) carry out the 6-monthly monitoring (b) assist the project to design the environmental training programs and prepare training materials (c) assist the project in the health, environment and sanitation awareness component (HESA). - The Director of the EPA will be a member of the Program Policy and Coordination Committee (PPCC). - Linkages of CISP will be developed with other Departments and AJK-EPA activities to enhance environmental benefits of the project, as described in the EMF. - At the time of source selection, water will be tested for biological contamination (e.g. E-coli count). The labs of Health Department will analyze the water. EPA is commissioning a comprehensive statewide study to analyze the quality of drinking water, for physical, chemical and biological parameters. Results of the study will be available before program effectiveness and will inform the nature of testing procedures and mitigation measures to be put in place before and during program implementation, notably in areas where chemical contamination has been detected (e.g. hotspots for fluoride, etc.). - For water monitoring, a facility will be created within Health Department to test water quality as required by the communities (on demand). EPA will monitor periodically a representative sample of water schemes under operation. Water quality indicators will be made available publicly. - The activities under the CISP concerning the environment will be primarily planned and implemented with active participation of the EPA. The CISP will provide a suitable vehicle and operational cost to the EPA to support and monitor the program activities. 7. Social Aspects The social assessment for the planning and implementation of the CISP has been completed. The recommendations of the report will be implemented in the CISP. Subproject selection will ensure compliance with social safe guards, poverty focus, inclusiveness, participation of community based organizations, benefits to poorer groups/areas and prevention of elite takeover and will ensure existence of a local level grievance redressal mechanism. It has been agreed with the IDA that (a) approval will appraise against the social parameters laid out at selection; (b) implementation will be at decentralized level with community participation and ownership; (c) the M&E will be a multi-tiered system with participatory community monitoring being one aspect. Monitoring indicators for participatory monitoring will be simple, relevant and used at the community level; (d) support women’s and children component will be closely monitored to ensure progress in implementation and accrual of benefits, and (e) village cross visits will be utilized for experience sharing and solution of problems. Please see attachment A on the social checklist/screening. 8. Selection Criteria Communities for the first phase have been identified vide Annex-‘A’. Eligibility of these identified communities and of those to be identified during subsequent phases will be assessed/evaluated based on the following criteria: a. Low income b. Lack of basic infrastructure and slum areas c. Investment potential d. Size of settlements above 1000 persons e. Geographic spread across districts and urban/rural balance f. Potential for community participation g. Per capita slabs, if any, as may be approved by the PPCC 9. Eligibility: To be eligible for the program financing schemes proposed by communities have to satisfy the following requirements demonstrating that they are technically sound, ready for implementation, and economically and financially viable: - Community and Local Council /Government Participation and Contribution. The community must demonstrate a willingness to participate in the selection design, and implementation of the infrastructure and, in particular, to contribute at least 20% to the capital costs of the community infrastructure. (excluding trunk infrastructure costs) and to undertake O&M. The Local council/Government must be prepared to participate in all CISP activities in their jurisdiction. - Resource Availability. Trunk infrastructure must be available, or to be provided subject to technical and economic justification. If the primary infrastructure costs of any scheme exceed 50% of the gross cost limit, a technical and economic justification and feasibility analysis will be prepared for review prior to its approval. Any land required must be in public or common ownership or dedicated under legally acceptable arrangements. - Environmental Sustainability. Any scheme which creates the possibility of an adverse environmental impact has been avoided. - Technical Viability. Schemes must demonstrate improvements benefiting the majority of households lacking service, endeavor to provide a balanced package of infrastructure elements, conforming with technical design standards, and have implementation arrangements consistent with proven capacities of community/ CBO. Infrastructure sub-components are to be designed as completely functioning systems. - Economic Viability. Excluding the cost of primary infrastructure, the cost of schemes must fall below a cost limit. Although communities will still be able to select a higher cost scheme by contributing full incremental costs. If gross costs exceed PKR 10500 per household (or PKR 1500 per person) then data should be provided: (i) to indicate the source of incremental financing, and (ii) to reconfirm that the site conforms with the agreed selection criteria. - Sustainability. The community must be aware of O&M consequences of their schemes, and prior agreements must be in place for adopting completed infrastructure, for provision for O&M financing. Continuing O&M of earlier phases of project infrastructure must be satisfactory. |
| Program Components |  | 10. Program Components: The program will comprise the following three complementary components: 1. Decentralized Planning and Implementation: This component would develop the capacity of state, district, communities and NGO/CBOs for: - community driven program development approaches and techniques, promotion and awareness campaigns, and capacity building; - design and implementation of infrastructure sub-projects; - institutional strengthening; - establishing a monitoring and evaluation system including process monitoring and capacity/training activities; and - operational activities, research and technical assistance activities which support the implementing agencies in meeting operating costs. The Program will finance capacity building activities and services provided among others, by local training/academic institutes, local service organizations, private sector - who will be called service providers, together with facilitating partnership arrangements with training institutions; and - two jobs of baseline surveys will be completed. 2. Community Development: This program component will include: - mobilization, organization and capacity building through development of Community Action Plans (CAP), as a basis for active participation of the community and members in planning, implementation and operation of their development programs; - Health, Environment, and Sanitation awareness (HESA) program to reduce morbidity and mortality by generating demand for safe water and sanitation, other basic infrastructure, and improve the overall environment; - Support to Women and Children (SWC) in areas of health, skill and management training, Economic/ Functional literacy and livelihood opportunities through linkages to economic and micro credit facilities. The Program will finance capacity building activities and services provided among others, by local NGOs, private sector (service providers) along with training and related equipments. A complementary economic literacy (or functional literacy) assistance will be provided for 10-15% of participating community households and emphasis will be on adult literacy and in areas to help combat other urban pathologies emerging in many areas. Related equipments would also be included under these operations. This component will finance mostly capacity building activities and related equipment would also be included as needed; 3. Infrastructure Upgrading and Services: This component involves investment for basic infrastructure upgrading and services, with priorities to be established in partnership with the communities through their CBOs. This operation is designed in a way that the actual locations of the proposed interventions are not identified at this stage since a process planning approach will be used during implementation. A menu of infrastructure to be provided would include: - water supply; - community latrines; - storm water drainage; - street pavements; - street lighting; - solid waste management; - internal pathways; - foot bridges; - tagging/ numbering streets; - trunk and other specialized infrastructure facilities will also be included to ensure that basic infrastructure functions efficiently. Particular attention will be given to the interconnection between the delivery and timing of water supply and health and sanitation components. The Program will finance civil works, material and equipments, capacity building, technical services for pre-feasibility, design, supervision of works and operation and maintenance; and - physical phasing is being given in Annex ‘B’. Note: A brief description on sub-components of the above three main components is presented in Annex-‘C’. It is expected that keeping in view the nature of the program some other sub-components will be identified and included in the CISP with the PPCC’s approval. |
| Institutional Arrangements Implementation Schedule/Action Plan Cost Sharing and O&M Memorandum of Understanding (MOU) and Agreement Finances Summary of Estimated Costs ###### Procurement |  | 11. Institutional Arrangements: CISP will be implemented through the existing institutional structure of GoAJK to deal with community infrastructure services. While the program relies heavily on the existing system for accomplishment of program objectives, the program will facilitate and enhance the capacity of the existing institutions in keeping with the ongoing decentralization of local government system in Pakistan. (The overall Institutional relationships and responsibilities of the program and roles and responsibilities are contained in Annex ‘D’. It has been agreed with the World Bank that: the overall responsibility of CISP implementation, would be with the LGRDD headed by Secretary, responsible for the overall program execution including the financial responsibility; - Steering Committee: At the highest level of the GoAJK, a Steering Committee will be set up under the Additional Chief Secretary, Development, to advise on the policies, and overall guidance for the program. The Steering Committee would comprise Secretary level representation from the relevant departments, for example, departments of finance, planning and development, LGRDD, health, education etc. - Program Policy and Coordination Committee (PPCC): At the program planning and implementation level, a (PPCC) to be chaired by the Secretary LGRDD will also be constituted to articulate and prepare details of the overall policy framework, and approve community sub-projects, and other sub-projects and leading activities of the CISP. The members of the PPCC will include Director General CISP/ Director LGRDD, Secretary LGB, Director EPA and representatives from: departments of finance, planning and development, public works, audit and accounts, local councils/local governments; NGOs; Academic/ Research/Training institutes; and Private Sector. - District Offices of the LGRDD and CBOs. The existing district offices of LGRDD would be the main implementing arm in carrying out the rural CIS program while Urban Local Councils would function as the implementing agencies for the urban community sub projects. - CBOs and Users' Groups will be the main partners in the planning and implementation of the CISP. Communities will submit proposals to the district/urban local councils who then will be responsible for technical review of each proposal and subsequently submit the same to the Directorate/Directorate General of Local Government and Rural Development Department (LGRDD) and Local Government Board (LGB) in case of rural and urban schemes respectively. The Directorate/Directorate General of Local Government and Rural Development Department (LGRDD) and Local Government Board (LGB) will review the proposals based on agreed criteria for eligibility and selection (based on the technical, financial, economic, social and environmental factors). The proposals will then be endorsed to the PPCC for final approval. Rural as well as urban Non-Governmental Organizations (NGOs) and Community Based Organizations (CBOs), private groups and training/research and academic institutions would be assigned roles in implementing community level CIS projects as service providers, provided there are no conflict of interest issues involved. Obtaining the assistance of service providers would widely be encouraged for all activities at both the district and community levels. Details of the institutional and implementation arrangements are discussed in Annex ‘D’ and will be elaborated further in the operational manual. - Staff of CISP: It has been agreed with the World Bank that the existing trained staff of the RWSSP would be shifted to and continue in the CISP. As per requirement of the workload, some new staff positions will be provided in the CISP. During implementation or on expiry of the CISP, the key temporary/contract staff, in number to the extent required and justified, will be regularized under rules in the core strength of the LGRDD. Government servants (core staff) posted/working on the CISP will be provided additional benefits in shape of project allowance as per rules, which is presently of 20% of the salary. The staff initially recruited on the project on contract bases with graded salaries will be granted incentive for good performance. This incentive will be approved by the PPCC based on judicious evaluation of the performance. Incentive may be in the form of cash prize or advance increments. List of the staff to be included/engaged in the CISP is given in Table-3.1 of Annex- ‘E’. 12. Implementation Schedule /Action Plan: It has been agreed with the World Bank that CISP would be implemented through two sub programs i.e. Rural CIS Sub Program and Urban CIS Sub Program. The Rural CIS sub program will cover about 500 villages benefiting 884,000 rural people while Urban Sub Program consists of 75 low income settlements benefiting 188,000 people. Thus more than 34% population of AJK will be benefited. Details are provided in Annex ‘B’ ### 13. Cost Sharing and O&M: The GoAJK agreed with the World Bank on cost sharing and O&M broad arrangements, which are: ### CBOs would be registered bodies and the GoAJK would facilitate the registration process. The government would review the various methods of registration and used the most suited for community organizations; ### Communities would share in the capital costs of the various physical infrastructure through a combination of component sharing and minimum percentage sharing principles. The details of capital cost sharing will be notified and delineated in the policy framework ### Communities would be provided the government’s contribution in the form of advances equal to previously agreed installments. Where applicable, the communities would also deposit their share of the works in the bank account ### 14. Memorandum of Understanding (MOU) and Agreement: Once the Memorandum of Understanding is signed which includes details of financial arrangements and responsibilities between the CBO and the government, the communities will start collecting the community contributions (Capital share, O&M cost etc.) from the households. MOU and other required agreements would be got authenticated legally. 15. Finances: The CISP would initially use the ring-fenced system used in the RWSSP with appropriate refinements and modifications in order to make it more sound and as much in line with the mainstream system of the GoAJK. It has been agreed with the World Bank that the refinements and modifications would entail, at a minimum, at the start of the program operation: - as much as possible, use the Accountant General’s (AG’s) office and field staff, especially at the district level, to be responsible for auditing and accounting purposes of the CISP. - have the Financial Information System part of the Management Information System, developed and introduced by the time of credit effectiveness. Financial Information System should cover preparation of quarterly reports of expenditure, initially at District level and consolidated for the project, showing amounts expensed for each component, and for infrastructure, by type of infrastructure. This should be reconciled with a summary statement of sources and uses of funds, including direct and Special Account withdrawals, reconciling with the Special Account balance. - responsibility of managing funds should be at the state and district level. - government’s contribution to the physical infrastructure would be transferred to the CBOs’ bank accounts (or other savings arrangements in the case of communities which do not have Banks in their vicinity) for works managed by the communities. The bank account would be in the name of the CBO and would have joint signatories from the CBO and the CISP. 1. Program Cost: Base costs have been calculated in October 2001 prices and the conversion rate used for one USD is 65 PKR. Price contingencies and physical contingencies on the base cost estimates have been added as follow: ##### Price Contingencies; %. FY1; 0. FY2; 6.5. FY3; 13. FY4; 20. FY5; 20. ##### Physical Contingencies. Civil Works; 10. Equipment/Material; 5. Technical Assistance; 5. Source: Planning Manual and Staff Appraisal Report of RWSSP Costs are summarized in table below. Further details appear in Annex ‘E’ which provides a complete cost tables. CISP: Summary of Estimated Costs Components / Sub Components; Cost (Million). PKR; USD. A. COMMUNITY DEVELOPMENT. Community Mobilization and Capacity Building; 125.450; 1.930. Health, Environment & Hygiene Education; 47.450; 0.730. Support to Women & Children; 87.100; 1.340. Sub Total; 260.000; 4.000. B. DECENTRALIZED PLANNING AND IMPLEMENTATION. Technical Assistance; 228.540; 3.516. Program Operation; 96.460; 1.484. Sub Total; 325.000; 5.000. C. INFRASTRUCTURE UPGRADING AND SERVICES. Water supply; 921.375; 14.175. Community Latrine; 26.325; 0.405. Stormed Water Drainage; 140.400; 2.160. Internal Pathways; 175.500; 2.700. Foot Bridges; 140.400; 2.160. Street Pavement; 70.200; 1.080. Street Lighting; 5.265; 0.081. Solid Waste Management; 10.530; 0.162. Tagging/ Numbering Streets; 1.755; 0.027. Trunk Infrastructure /Hydel Power; 165.750; 2.550. Sub Total; 1657.500; 25.500. Physical Contingencies; 104.94; 1.61. Price Contingencies; 239.90; 3.69. TOTAL PROGRAM COST INC. COMMUNITY SHARE; 2587.34; 39.81. TOTAL PROGRAM COST EXC. COMMUNITY SHARE; 2294.26; 35.30. 2. Financing Plan: A financing plan is shown in the table below. These estimates have been prepared based on discussions with the appraisal and pre-appraisal missions from the IDA. The community participation part of the cost estimates is calculated based upon previous experience of the RWSSP. ##### Financing Plan Millions Source; PKR; USD; Percent. Communities; 293.09; 4.51; 11%. Govt. of AJK; 229.43; 3.53; 9%. IDA and other Foreign Donors; 2064.83; 31.77; 80%. Total; 2587.35; 39.81; 100%. 3. Audit: The establishment of audit arrangements for the CISP would be: - The CISP’s financial statements and audited financial statements will be sent to Auditor General with a management letter to IDA within 6 months after closing of the financial year - A system/ form of financial and technical check on the performance, relating to the works as well as financial records, of CBOs/Users' Groups and the LGRDD (including the state, district and urban local council offices) will be established and incorporated into the manual and detailed guidelines. Service providers will be hired to train CBOs/Users' Groups and their partners as needed. It was also agreed that the Financial Monitoring Report (FMR) shall be an important part of the financial management system. 4. Financial Consultancy: It was agreed that the Bank would appoint a financial management consultant to review the ring-fenced system used in the RWSSP with the objective to refine and modify it to achieve the above critical requirements, so that it can be used at the start of the program. The comprehensive financial management study and design of the phased financial management system and the preparation of the financial management manual would be separately undertaken through the project preparation activities (PHRD grant fund). 5. Disbursement. The proposed IDA and other donor’s share would be disbursed over a period of five years. This foreign financing amounts to 78 percent of the total cost of the CISP. The proceeds of the foreign financing would be disbursed against eligible expenditures, net of taxes and duties. Tentative disbursement against foreign financing is proposed as follows: Cat; Cost Items; Share. 1.; Civil Works; 80%. 2.; Goods and Equipment; 100%. 3.; Consultants Services and Training; 100%. 4.; Operations and Incremental Staff; 100%. Disbursements would be fully documented except for those expenditures: (a) under contracts not exceeding the equivalent of: (i) US$150,000 each for goods and civil works, (ii) US$ 100,000 for the services of consulting firms, and (iii) US$.50,000 for services of individual consultants. Such disbursement would be made against Statement of Expenditures (SOE), the documentation for which would not be submitted to IDA but retained by the LGRDD at a central place and made available during the course of program supervision. It is envisaged that about 75% disbursement would take place through SOEs. LGRDD would keep safe and secure all documentation relating to the disbursement of the CISP funds for review by the IDA and for audit purposes. 6. Special Account. (a) To facilitate timely payment/disbursement, a Special Account would be opened by the LGRDD, with an amount of up to US$.1.5 million in the National Bank of Pakistan on terms and conditions acceptable to IDA. This would be used for IDA's share of financing of the expenditures. The Special Account would be opened and maintained by LGRDD and would be used for payments of all eligible foreign and local expenditures. The Special Account would be replenished on a monthly basis or whenever 20% of the account has been utilized, whichever occurs first. (b) On the part of GoAJK, revolving fund with an adequate amount of PKR would be set up to arrange prompt payments to the CBOs/Users' Groups. This revolving fund would be used for the payment of the claims/bills and replenished with the transfers of funds from the IDA and GoAJK respective shares. Final adjustment/settlement of the revolving fund would be made at the close of the CISP accounts. 7. Retroactive Financing: Retroactive financing would be made available to the GoAJK by IDA to cover eligible expenditures on civil works, materials, incremental staff, vehicles and equipment, consultancy services and training upto USD 600,000equivalent, incurred after May 2000 and before the credit signing date. 16. Procurement: The status, key issues and agreed actions highlighted during the Appraisal Mission are summarized as follows: - Contract packaging arrangements envisaged under the program and the preliminary procurement plans (Annex ‘F’) for contracts expected during the first year of the program, have been prepared and provided to the Bank. - The preliminary procurement plans for first year contracts have been prepared. The preliminary plans for the remaining period of the project will be prepared later and provided to the Bank. Although it is difficult (because of the community driven nature of this program) to define the exact number of contract packages and the procurement plans at this stage, the preliminary plans still need to be prepared and updated/refined during the implementation phases of the CISP. - In order to strengthen the existing capacity of the LGRDD, the appointment of a Procurement Consultant to provide procurement support and guidance and to serve as the focal point for all program procurement matters related to both the rural and urban sub-programs, will be made. Basic procurement training will be received from the Bank staff before the start of the CISP and periodically during its implementation. - Procurement of Goods, Equipment and Works under the program will be carried out in accordance with the World Bank’s Procurement Guidelines, and Consultants’ Services will be procured according to the Bank’s Consultant Guidelines. - The Bank’s standard/sample bidding documents will be used for procurement of goods and works under International Competitive Bidding and National Competitive Bidding. The model contract document for procurement of works through community participation (based on the Bank’s sample format) will be used. |
| 12) Give date when capital expenditure estimates were prepared |  | October, 2001 |
| 13) Give break down of capital cost year wise, covering the whole of the investment period as indicated. |  | A summary of capital cost is shown below. For details see Annex ‘E’ Year; ADP; Comm.; Total. Y1; 281.45; 43.91; 325.36. Y2; 456.21; 58.90; 515.11. Y3; 701.73; 87.82; 789.55. Y4; 631.59; 73.18; 704.77. Y5; 223.28; 29.27; 252.55. Total; 2294.26; 293.09; 2587.34. |
| 14 Basis of cost estimates (give full details): |  | Cost estimates for civil works are based on the Composite Schedule of Rates, 1998 with average 12% premium. For water supply schemes, the cost estimates are based on the completed RWSS works and the open market rates. |
| - Estimates of annual recurring expenditures of each phase of Project (Also indicate the sources of financing recurring expenditure). |  | For the institutional component the recurring expenditure comprise the following: - Salaries and regular allowances. - Other operational costs. The above expenditure will be borne by the program. For the community infrastructure the recurring expenditure will be borne by the beneficiary communities through their CBOs/Users' Groups. |
| - Unit cost of each category of service output. |  | The unit costs of the various service outputs are: ## (1) Piped Water Supply Public Tapstand = Service Level PKR 1500 per person ## (2) Sanitation School Latrine = PKR 500 per student (PKR 20000 per Latrine House) Public Latrine = PKR 300,000 per unit ## (3) Access Road (up-gradation) = PKR 350,000 per Km Bridges (RCC) = PKR 200,000 per metre Bridge (Suspension) = PKR 25,000 per metre (4) Street Brick paved = PKR 850 per metre Stone paved = PKR 960 per metre PCC = PKR 900 per metre |
| - Indicate if any charges will be levied for providing the service. |  | No changes are proposed to be levied on the service provided as O&M responsibility will rest with the communities/CBOs |
| - Annual phasing of physical work and financial requirements for the Project. |  | A summary of the annual phasing of physical work is shown in Annex ‘B’. Summary of the financial requirements is shown in Table-1 of Annex ‘E’ |
| - Foreign exchange expenditure: |  | (1) Consultants' Services = PKR 70.00 million (2) Equipment and Vehicles = PKR 100.00 million Total = PKR 170.00 million Say = USD 2.62 million |
| - a) Likely sources and foreign exchange cost of the project. |  | IDA and other donors. |
| b) Present position regarding availability, commitment or negotiations. |  | Appraisal of the CISP has been completed. Project Appraisal Document (PAD) will be circulated shortly. Negotiations are expected somewhere during the first quarter of 2002. |
| - Indicate sources and amount of rupee component of Program. |  | Annual Development Program of GoAJK. (a) Government = PKR 229.43 million (b) Community = PKR 293.09 million (c) IDA and other donors = PKR 2064.83 million |
| 22. Results of the Program |  |  |
| - Direct benefits. |  | (a) Improved water supply facilities for about eleven thousand households. (b) Better access, sanitation and environmental facilities for about 575 communities. |
| - Indirect and other socio/economic benefits. |  | (a) Community mobilization and organization for collective efforts. (b) Creation of physical assets commonly owned and used by the communities. (c) Provision of the community based services especially to the low income families particularly the women and children. (d) Contribution to decrease the occurrence of environment related diseases. (e) Contribution to the public education and awareness on the governance issues. |
| - Economic Appraisal |  | An economic appraisal of the CISP has been done to assess the economic viability of the investment. Capital and O & M costs have been valued in economic term by exclusion of taxes and application of appropriate shadow prices to factor inputs. Benefit is only taken in terms of time saving to be used in fetching water from the source arising from the program. a. Social Costs and Benefits All such programs which are established for public unity such as water supply and community infrastructure etc. are to be evaluated on the bases of social costs and benefits. The ultimate benefits that are potentially achievable through participatory development schemes of water supply and community infrastructures relate to: - Time, cost and energy saving; - Increased leisure; - Reduced food requirements; - Involvement in income generating activities; - Reduced diseasing resulting in decreased medical expenditure; - Better children care; - Looking after livestock; - Collective effort of development for common benefits; - Integration of the poorer sections of population in local development resulting in poverty reduction; - Beneficiaries’ participation leading to inculcation of democratic values; - More time to education ; and - Reduced infant and maternal morality rate; ###### b. Internal Economic Rate of Return (IERR) The economic viability of the program has been tested through estimation of IERR. The economic values of program (RWSS scheme) benefits have been calculated by evaluating social benefits using conversion factor of 0.846. Economic costs have been calculated from the RWSS schemes cost using standard conversion factor. The IERR for the Five Year Program comes to 9.03%. c. Cost / Benefits Ratio The Cost Benefit Ratio correctly ranks the community sub- projects / schemes. Cost benefit ratio at different discounts rates for RWS schemes of 5 years plan is as under. Cost Benefit Ratio Discounts Rate 5 years plan 8 % 1 :0.93 10 % 1 :1.08 12 % 1 :1.25 d. Program Justification The IERR of 9.03% and cost benefit ratio at discount rate of 10% through 25% remains above unity for the 5 years plan. This, 5 years program is economically feasible at the discount rate of 10% and above. If other non-quantifiable benefits of RWS schemes and community infrastructure are taken into account, it would further strengthen the justification of the program. Provision of potable water and community infrastructure including community services to the beneficiaries, particularly the poor, would provide cleaner and better living conditions. This will in turn result in improving the health, wealth and general standard of living of the people who are benefited. |
| 23. a) Approximate number and categories of job opportunities likely to be created indirectly as a result of: |  | - Implementation Skilled and Unskilled labour = 100,000 workdays - Operation and Maintenance Skilled and Unskilled Employees = 600 Nos |
| - Economic life of project components - Building - Equipment - Books |  | Water supply - Electro mechanical equipments = 5-10Yrs - Pipes GI = 25Yrs HDPE = 30Yrs - Masonary Structures = 10Yrs Sanitation - Latrines = 30Yrs - Local Sewerage Systems = 20Yrs - SWM structures = 30Yrs Access - Roads = 15Yrs - Bridges = 25Yrs - Streets = 20Yrs Street Lights = 20Yrs |

PART C

PROJECT REQUIREMENTS

| 24. I) Detailed list of technicians and professionals required for implementation of the project. |  |  |
| --- | --- | --- |
| - Manpower: |  | Category; Person Months. Professionals (Advisors, Consultants); 100. Management and Coordination; 450. Engineering and Technical; 6000. Community Development; 4200. Information Technology; 1050. Finance, Audit and Accounts; 1100. Clerical; 800. Others; 5000. Total; 18700. |
| - Likely shortage of manpower by occupation. |  | N.A |
| - Efforts to be made in the program for skills development. |  | - Community mobilization and organization. - Participatory planning and implementation of community based projects - Appropriate technology - Monitoring and Evaluation - Information Technology - Project Management and Supervision. |
| - Physical and other facilities to be provided from the project. |  | Vehicles, Office and Field Equipments and Office accommodations. |
| - If any civil works of any kind included in the Project then provide details: |  | CISP includes civil works. Details are provided in the Infrastructure Upgrading and Services component of the Program. |
| - a) Material, supplies and Equipment requirements: |  | G.I Pipes = 7.00 million meter HDPE = 0.37 million meter Motor/Pumps = 415 units Cement = 50,000 metric ton Steel = 1,650 metric ton Steel Wire Rope = 100,000 meter Vehicles = 19 Nos. Motor Cycles = 28 Nos Computer sets = 32 Sets Photocopiers = 14 Nos Field equipment = for 40 team.(18 Sets) Furniture/fixture = for 10 offices |
| - In the case of imported material and equipment for execution, indicate: Justification for imports. |  | Vehicles may be procured under International Competitive Bidding (ICB). |
| - Beneficiaries Participation |  | - Communities will contribute at least 20% of the capital cost of infrastructure sub-components as to be agreed with the beneficiary communities during planning of their sub-projects/schemes. - Entire O&M will be responsibility of the beneficiary community through their CBOs/Users' Groups/Organizations. |