## Table 1
Table 1: CISP:Summary Cost Timeline
Million
No | Cost Components/ Sub Components | Total Cost |  | 2002 |  | 2003 |  | 2004 |  | 2005 |  | 2006 |  | Cost (Inc. D exc. E1)
|  | PKR | USD | PKR | USD | PKR | USD | PKR | USD | PKR | USD | PKR | USD | PKR | USD
A | COMMUNITY DEVELOPMENT
A.1 | Community Mobilization and Capacity Building | 125.45 | 1.93 | 18.8175 | 0.2895 | 25.09 | 0.386 | 37.635 | 0.579 | 31.3625 | 0.4825 | 12.545 | 0.193 | 140.89 | 2.17
A.2 | Health, Environment & Hygiene Education | 47.45 | 0.73 | 7.1175 | 0.1095 | 9.49 | 0.146 | 14.235 | 0.219 | 11.8625 | 0.1825 | 4.745 | 0.073 | 53.29 | 0.82
A.3 | Support to Women & Children | 87.1 | 1.34 | 13.065 | 0.201 | 17.42 | 0.268 | 26.13 | 0.402 | 21.775 | 0.335 | 8.71 | 0.134 | 97.82 | 1.5
| Sub Total | 260 | 4 | 39 | 0.6 | 52 | 0.8 | 78 | 1.2 | 65 | 1 | 26 | 0.4 | 292 | 4.49
B | DECENTRALIZED PLANNING AND IMPLEMENTATION
B.1 | Technical Assistance | 228.54 | 3.516 | 34.281 | 0.5274 | 45.708 | 0.7032 | 68.562 | 1.0548 | 57.135 | 0.879 | 22.854 | 0.3516 | 268.09 | 4.12
B.2 | Program Operation | 96.46 | 1.484 | 14.469 | 0.2226 | 19.292 | 0.2968 | 28.938 | 0.4452 | 24.115 | 0.371 | 9.646 | 0.1484 | 113.15 | 1.74
| Sub Total DPIF: | 325 | 5 | 48.75 | 0.75 | 65 | 1 | 97.5 | 1.5 | 81.25 | 1.25 | 32.5 | 0.5 | 381.24 | 5.86
C | INFRASTRUCTURE UPGRADING AND SERVICES
C.1 | Water Supply | 921.375 | 14.175 | 138.2063 | 2.1263 | 184.275 | 2.835 | 276.4125 | 4.2525 | 230.3438 | 3.5438 | 92.1375 | 1.4175 | 875.73 | 13.47
C.2 | Community Latrine | 26.325 | 0.405 | 3.9487 | 0.06075 | 5.265 | 0.081 | 7.8975 | 0.1215 | 6.5812 | 0.10125 | 2.6325 | 0.0405 | 31.28 | 0.48
C.3 | Stormwater Drainage | 140.4 | 2.16 | 21.06 | 0.324 | 28.08 | 0.432 | 42.12 | 0.648 | 35.1 | 0.54 | 14.04 | 0.216 | 133.44 | 2.05
C.4 | Internal Pathways | 175.5 | 2.7 | 26.325 | 0.405 | 35.1 | 0.54 | 52.65 | 0.81 | 43.875 | 0.675 | 17.55 | 0.27 | 166.8 | 2.57
C.5 | Foot Bridges | 140.4 | 2.16 | 21.06 | 0.324 | 28.08 | 0.432 | 42.12 | 0.648 | 35.1 | 0.54 | 14.04 | 0.216 | 133.44 | 2.05
C.6 | Street Pavement | 70.2 | 1.08 | 10.53 | 0.162 | 14.04 | 0.216 | 21.06 | 0.324 | 17.55 | 0.27 | 7.02 | 0.108 | 66.72 | 1.03
C.7 | Street Lighting | 5.265 | 0.081 | 0.78975 | 0.01215 | 1.053 | 0.0162 | 1.5795 | 0.0243 | 1.3162 | 0.02025 | 0.5265 | 0.0081 | 5 | 0.08
C.8 | Solid Waste Management | 10.53 | 0.162 | 1.5795 | 0.0243 | 2.106 | 0.0324 | 3.159 | 0.0486 | 2.6325 | 0.0405 | 1.053 | 0.0162 | 10.01 | 0.15
C.9 | Tagging/ Numbering Streets | 1.755 | 0.027 | 0 | 0 | 1.755 | 0.027 | 0 | 0 | 0 | 0 | 0 | 0 | 1.68 | 0.03
C.10 | Trunk Infrastructure | 165.75 | 2.55 | 0 | 0 | 49.725 | 0.55 | 58.0125 | 1 | 58.0125 | 1 | 0 | 0 | 196.92 | 3.03
| Sub Total CI: | 1657.5 | 25.5 | 223.4992 | 3.4385 | 349.479 | 5.1616 | 505.011 | 7.8769 | 430.5113 | 6.7307 | 148.9995 | 2.2923 | 1621.02 | 24.94
| Community Share | 293.085 | 4.509 | 43.9101 | 0.67554 | 58.8978 | 0.90612 | 87.8202 | 1.3511 | 73.1835 | 1.1259 | 29.2734 | 0.45036
| Community Infrastructure Balance | 1364.415 | 20.991 | 179.5891 | 2.7629 | 290.5812 | 4.2555 | 417.1908 | 6.5258 | 357.3277 | 5.6048 | 119.7261 | 1.8419
| Base Cost (BC) | 1949.415 | 29.991 | 267.3392 | 4.1129 | 407.5812 | 6.0555 | 592.6908 | 9.2258 | 503.5777 | 7.8548 | 178.2261 | 2.7419
D. | CONTINGENCIES
D.1 | Physical
* | Civil Works @ 10%: | 40.9325 | 0.62973 | 5.3877 | 0.082887 | 8.7174 | 0.12766 | 12.5157 | 0.19577 | 10.7198 | 0.16815 | 3.5918 | 0.055258
** | TA/Equipment/Material @ 5% : | 64.0045 | 0.98469 | 8.7231 | 0.1342 | 13.4203 | 0.19894 | 19.4767 | 0.3034 | 16.569 | 0.25867 | 5.8154 | 0.089468
| Sub Total: | 104.937 | 1.6144 | 14.1108 | 0.21709 | 22.1378 | 0.32661 | 31.9924 | 0.49918 | 27.2888 | 0.42682 | 9.4072 | 0.14473
D.2 | Price
| Percentage by year of BC: |  |  | 0% | 0% | 6.5% | 6.5% | 13% | 13% | 20% | 20% | 20% | 20%
| Amount | 239.9034 | 3.6908 | 0 | 0 | 26.4928 | 0.39361 | 77.0498 | 1.1994 | 100.7155 | 1.571 | 35.6452 | 0.54839
| TOTAL PROGRAM COST EXC. COMM. SHARE | 2294.2553 | 35.2962 | 281.4499 | 4.33 | 456.2118 | 6.7757 | 701.733 | 10.9244 | 631.5821 | 9.8526 | 223.2785 | 3.4351
E | PROGRAM FINANCING
E.1 | Community | 293.085 | 4.509 | 43.9101 | 0.67554 | 58.8978 | 0.90612 | 87.8202 | 1.3511 | 73.1835 | 1.1259 | 29.2734 | 0.45036
E.2 | GoAJK | 229.4255 | 3.5296 | 28.145 | 0.433 | 45.6212 | 0.67757 | 70.1733 | 1.0924 | 63.1582 | 0.98526 | 22.3279 | 0.34351
E.3 | IDA and other Foreign Donors | 2064.8298 | 31.7666 | 253.305 | 3.897 | 410.5906 | 6.0981 | 631.5597 | 9.8319 | 568.4239 | 8.8674 | 200.9507 | 3.0915
| TOTAL PROGRAM COST INC. COMM. SHARE | 2587.3403 | 39.8052 | 325.36 | 5.0055 | 515.1096 | 7.6818 | 789.5532 | 12.2754 | 704.7656 | 10.9785 | 252.5519 | 3.8854
* 30% of C excluding community share
** 100% of B and 70% of C excluding community share

## Table 2
Table 2: CISP: Community Development Cost
| Component/ Activity | Details of Activity |  |  |  | Total
|  | No of Person per Site/ CBO | Duration/No days | No of Sites | Unit Cost (Rs) | PK. Rs.(M) | US$(M)
B1 | Community Mobilization and Capacity Building
| Leadership Training | 4600P in all sites | 2 |  | 125 | 1.15 | 0.017692
| CAP Training | 4600P in all sites | 5 |  | 125 | 2.9 | 0.044615
| Treasure Training | 2p |  | 575 | 125 | 0.144 | 0.0022154
| Activist Training | 5d | 2 | 575 | 125 | 0.718 | 0.011046
| CROSS VISIT (INAJK) | 5P | 3 | 575 | 1000 | 4 | 0.061538
| CV.OUTSIDE AJK in Pakistan | 2P | 6 | 25 | 10000 | 2.5 | 0.038462
| Infrastructure Maintenance Training | 12p | 3 | 575 | 125 | 0.432 | 0.0066462
| Community/private initiative |  |  |  |  | 1 | 0.015385
| Orientation Training for senior staff | 16p | 2 |  | 1000 | 0.032 | 0.00049231
| Preparation of pre-planning workshop |  |  |  |  | 0.03 | 0.00046154
| Pre-feasibility Planning phase | 100p | 4 |  | 750 | 0.75 | 0.011538
| Honorarium for Community Activist | 1150 | Sub Project Pe | 575 | 1000 | 1.15 | 0.017692
| Training of CBO's | 10 | 2 | 575 | 250 | 2.875 | 0.044231
| Training of Trainers | 25 | 6 |  | 1000 | 0.936 | 0.0144 | 18.617
B2 | Health Environment & Sanitation (HESA Training)
| Health Environment & Sanitation (HESA) | 8 Persons | 6 days | 575 sites | 125 | 3.45 | 0.053077
| HESA Material Kits | 8 Persons x 6 modules | - | 575 s | 300 | 1.38 | 0.021231
| Healthy home training | 10p | 3 | 575 s | 125 | 2.16 | 0.033231
| Household materials (kits) | 10p | - | 575 s | 150 | 0.86 | 0.013231
| Resource persons (RP) payment | 2 RP's per district | 15 | 7 districts | 500 per day | 0.105 | 0.0016154
| O & M Training | 5p | 5 | 575 | 72 | 1.045 | 0.016077 | 9
B3 | Support to Women and Children
| Functional/Economic Education | 19125 (3055 per CBO) | 6 months | 575 | 1072 | 20.5 | 0.31538
| Dev. Of Micro Credit Linkages | 10p | - | 575 | 160 | 9.1 | 0.14 | 29.6
| Total: |  |  |  |  | 57.217 | 0.88026 | 57.217

## Table 3
Table 3: Decentralized Planning and Implementation
No | Component/ Activity | Estimated Cost US$ | Estimated Cost (Rs)
A | Technical Assistance
A.1 | Community Development Specialist (international) USD 12500/6months | 75000 | 4875000
A.2 | Procurement Specialist (Local) Rs.81250/12 months | 15000 | 975000
A.3 | Short Term Technical Assistance (National) Rs.81250/40 months | 50000 | 3250000
A.4 | State, District and Field Staff (additional staff) | 1392325 | 90501125
A.5 | Vehicles and Equipment | 1282154 | 83340010
A.6 | Overseas Training | 280000 | 18200000
| Sub Total | 3094479 | 201141135
B | Program Operations
B.2 | Studies | 120000 | 7800000
B.3 | Water Quality Testing | 46153.85 | 3000000.25
B.7 | Baseline Surveys | 460000 | 29900000
| Sub Total | 626153.85 | 40700000.25
| Grand Total | 3720632.85 | 241841135.25

## Table 3.1
Table 3.1: Incremental Staff | [15 empty] | Allow
S.No | Name of Post |  | BPS | No. of Posts |  |  | Basic | Incr. | With | Estimated Cost PKR |  |  |  |  | Grand | 44.45%
|  |  |  | Ist Year | 2-5 Yr | Total | Pay | Rate | Allow. | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total PKR
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
STATE
Senior Staff
1 | Project Director | MC | B-19 | 1 | 1 | 1 | 12400 | 615 | 20986.8 | 251841.6 | 252456.6 | 253071.6 | 253686.6 | 254301.6 | 1265358
2 | Superintending Engineer (Director Works) | ET | B-19 | 1 | 1 | 1 | 12400 | 615 | 20986.8 | 251841.6 | 252456.6 | 253071.6 | 253686.6 | 254301.6 | 1265358
3 | Dy. Director (Human Resource Development) | CD | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 178452.09 | 886410.45
4 | Dy.Director (Coordination) | MC | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 178452.09 | 886410.45
5 | Dy.Director (Comminity Development) | CD | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 178452.09 | 886410.45
6 | Dy.Director (Monitoring) | MC | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 178452.09 | 886410.45
7 | XEN | ET | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 178452.09 | 886410.45
8 | Computer Program Officer | IT | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 137404.14 | 682370.7
9 | Assistant Director (Environment) | ET | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 137404.14 | 682370.7
10 | Assistant Director (Tech.) | ET | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 137404.14 | 682370.7
11 | Finance and Accounts Officer | FAA | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 137404.14 | 682370.7
12 | Audit Officer | FAA | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 137404.14 | 682370.7
| Sub-Total |  |  | 12 | 12 | 12 |  |  |  | 2061964.35 | 2068444.35 | 2074924.35 | 2081404.35 | 2087884.35 | 10374621.75
Support Staff
1 | Data Processing Officer | IT | B-16 | 4 | 4 | 4 | 3805 | 295 | 6971.3225 | 334623.48 | 335803.48 | 336983.48 | 338163.48 | 339343.48 | 1684917.4
2 | Sub-Engineer | ET | B-16 | 1 | 1 | 1 | 3805 | 295 | 6971.3225 | 83655.87 | 83950.87 | 84245.87 | 84540.87 | 84835.87 | 421229.35
3 | Senior Scale Stenographer | CS | B-15 | 1 | 1 | 1 | 3285 | 265 | 6070.1825 | 72842.19 | 73107.19 | 73372.19 | 73637.19 | 73902.19 | 366860.95
4 | Accountant | FAA | B-15 | 1 | 1 | 1 | 3285 | 265 | 6070.1825 | 72842.19 | 73107.19 | 73372.19 | 73637.19 | 73902.19 | 366860.95
5 | Stenographer | CS | B-12 | 1 | 1 | 1 | 2745 | 195 | 4940.1525 | 59281.83 | 59476.83 | 59671.83 | 59866.83 | 60061.83 | 298359.15
6 | Senior Auditor | FAA | B-11 | 1 | 1 | 1 | 2590 | 175 | 4616.255 | 55395.06 | 55570.06 | 55745.06 | 55920.06 | 56095.06 | 278725.3
7 | Senior Clerk/Telephone Operator | CS | B-7 | 1 | 1 | 1 | 2220 | 120 | 3806.79 | 45681.48 | 45801.48 | 45921.48 | 46041.48 | 46161.48 | 229607.4
8 | Junior Clerk | CS | B-5 | 3 | 3 | 3 | 2100 | 100 | 3533.45 | 127204.2 | 127504.2 | 127804.2 | 128104.2 | 128404.2 | 639021
9 | Machine Operator | OS | B-5 | 1 | 1 | 1 | 2100 | 100 | 3533.45 | 42401.4 | 42501.4 | 42601.4 | 42701.4 | 42801.4 | 213007
10 | Driver | OS | B-4 | 13 | 13 | 13 | 2040 | 85 | 3371.78 | 525997.68 | 527102.68 | 528207.68 | 529312.68 | 530417.68 | 2641038.4
11 | Peon | OS | B-1 | 14 | 14 | 14 | 1870 | 55 | 2976.215 | 500004.12 | 500774.12 | 501544.12 | 502314.12 | 503084.12 | 2507720.6
| Sub-Total |  |  | 41 | 41 | 41 |  |  |  | 1919929.5 | 1924699.5 | 1929469.5 | 1934239.5 | 1939009.5 | 9647347.5
DISTRICTS
Senior Staff
1 | Dy.Director (North/South) | MC | B-18 | 2 | 2 | 2 | 8135 | 585 | 14676.0075 | 352224.18 | 353394.18 | 354564.18 | 355734.18 | 356904.18 | 1772820.9
2 | Executive Engineer (North/South) | ET | B-18 | 2 | 2 | 2 | 8135 | 585 | 14676.0075 | 352224.18 | 353394.18 | 354564.18 | 355734.18 | 356904.18 | 1772820.9
3 | Assistant Engineer | ET | B-17 | 15 | 15 | 15 | 6210 | 465 | 11295.345 | 2033162.1 | 2040137.1 | 2047112.1 | 2054087.1 | 2061062.1 | 10235560.5
4 | Community Dev. Officer | CD | B-16 | 7 | 7 | 7 | 3805 | 295 | 6971.3225 | 585591.09 | 587656.09 | 589721.09 | 591786.09 | 593851.09 | 2948605.45
| Sub-Total |  |  | 24 | 24 | 24 |  |  | 0 | 2970977.37 | 2981187.37 | 2991397.37 | 3001607.37 | 3011817.37 | 16729807.75
Support Staff
1 | Computer Assistant | IT | B-11 | 7 | 7 | 7 | 2590 | 175 | 4616.255 | 387765.42 | 388990.42 | 390215.42 | 391440.42 | 392665.42 | 1951077.1
2 | Sub-Engineer | ET | B-16 | 3 | 3 | 3 | 3805 | 295 | 6971.3225 | 250967.61 | 251852.61 | 252737.61 | 253622.61 | 254507.61 | 1263688.05
3 | Accountant/Senior Auditor | FAA | B-11 | 7 | 7 | 7 | 2590 | 175 | 4616.255 | 387765.42 | 388990.42 | 390215.42 | 391440.42 | 392665.42 | 1951077.1
4 | Draftsman | ET | B-11 | 7 | 7 | 7 | 2590 | 175 | 4616.255 | 387765.42 | 388990.42 | 390215.42 | 391440.42 | 392665.42 | 1951077.1
5 | Junior Clerk | CS | B-5 | 7 | 7 | 7 | 2100 | 100 | 3533.45 | 296809.8 | 297509.8 | 298209.8 | 298909.8 | 299609.8 | 1491049
6 | Driver | OS | B-4 | 28 | 28 | 28 | 2040 | 85 | 3371.78 | 1132918.08 | 1135298.08 | 1137678.08 | 1140058.08 | 1142438.08 | 5688390.4
7 | Peon | OS | B-1 | 28 | 28 | 28 | 1870 | 55 | 2976.215 | 1000008.24 | 1001548.24 | 1003088.24 | 1004628.24 | 1006168.24 | 5015441.2
| Sub-Total |  |  | 87 | 87 | 87 |  |  |  | 3843999.99 | 3853179.99 | 3862359.99 | 3871539.99 | 3880719.99 | 19311799.95
Field Teams (Rural)
1 | Community Organizer (Male) | CD | B-12 | 22 | 30 | 30 | 2745 | 195 | 4940.1525 | 1304200.26 | 1784304.9 | 1790154.9 | 1796004.9 | 1801854.9 | 8476519.86
2 | Community Organizer (Female) | CD | B-12 | 22 | 30 | 30 | 2745 | 195 | 4940.1525 | 1304200.26 | 1784304.9 | 1790154.9 | 1796004.9 | 1801854.9 | 8476519.86
3 | Overseer | ET | B-11 | 50 | 50 | 50 | 2590 | 175 | 4616.255 | 2769753 | 2778503 | 2787253 | 2796003 | 2804753 | 13936265
| Sub-Total |  |  | 94 | 110 | 110 |  |  |  | 5378153.52 | 6347112.8 | 6367562.8 | 6388012.8 | 6408462.8 | 30889304.72
| Total Rural |  |  | 258 | 274 | 274 |  |  |  | 16175024.73 | 17174624.01 | 17225714.01 | 17276804.01 | 17327894.01 | 86952881.67
Urban Local Councils
1 | Environment Officer | ET | B-17 | 0 | 3 | 3 | 6210 | 465 | 11295.345 | 0 | 408027.42 | 409422.42 | 410817.42 | 412212.42 | 1640479.68
2 | Community Development Officer | CD | B-16 | 0 | 4 | 4 | 3805 | 295 | 6971.3225 | 0 | 335803.48 | 336983.48 | 338163.48 | 339343.48 | 1350293.92
3 | Computer Assistant | IT | B-11 | 2 | 2 | 2 | 2590 | 175 | 4616.255 | 110790.12 | 111140.12 | 111490.12 | 111840.12 | 112190.12 | 557450.6
| Total Urban Local Councils |  |  | 2 | 9 | 9 |  |  |  | 110790.12 | 854971.02 | 857896.02 | 860821.02 | 863746.02 | 3548224.2
| G.TOTAL |  | 4: 260; 5: 283; 6: 283; 13: G.Total PKR; 15: 90501105.87
[13 empty] | G.Total USD |  | 1392324.7057
[13 empty] | Say USD (million) |  | 1.3923

## Table 3.2
Table 3.2: DIFFERENT ITEMS (OPRATIONAL COST)
ITEM | UNIT | OFFICES
| COST | STATE |  | DISTRICTS |  | LGB/ULCs |  | TOTAL
|  | NO | COST | NO | COST | NO | COST | COST Rs. | Cost USD
Vehicle | 1.5 | 4 | 6 | 12 | 18 | 3 | 4.5 | 17.1 | 0.26719
Motor Bikes | 0.08 |  | 0 | 28 | 2.24 |  | 0 | 2.24 | 0.035
Survey Equip. | 0.17 |  | 0 | 18 | 3.06 |  | 0 | 3.06 | 0.047813
Computers | 0.08 | 14 | 1.12 | 15 | 1.2 | 3 | 0.24 | 2.56 | 0.04
Photocopiers | 0.15 | 2 | 0.3 | 7 | 1.05 | 5 | 0.75 | 2.1 | 0.032813
Multimedia | 0.3 | 1 | 0.3 |  | 0 | 1 | 0.3 | 0.6 | 0.009375
Furniture/Fix. | L/S |  | 1.5 |  | 0.25 |  | 0.25 | 2 | 0.03125
Rents | L/S |  | 1.3 |  | 4.2 |  | 0.5 | 6 | 0.09375
POL/O&M Vehicle | L/S |  | 12.85 |  | 10.33 |  | 2.5 | 25.68 | 0.40125
O&M Equip. | L/S |  | 0.22 |  | 0.6 |  | 0.08 | 0.9 | 0.014063
Office Supplies | L/S |  | 1.8 |  | 2.1 |  | 1.2 | 5.1 | 0.079687
Utilities | L/S |  | 3 |  | 1.5 |  | 0.5 | 5 | 0.078125
TA/DA | L/S |  | 3 |  | 6 |  | 1 | 10 | 0.15625
Misc. | L/S |  | 0.5 |  | 0.3 |  | 0.2 | 1 | 0.015625
[8 empty] | 83.34 | 1.3022

## Table 4 & 4.1
Table 4 | [13 empty] | Table 18.0.0 - Backup
GOVERNMENT OF AZAD JAMMU & KASHMIR
COMMUNITY DISTRICT INFRASTRUCTURE SERVICES PROJECT
PROPOSED PHYSICAL INFRASTRUCTURE | [13 empty] | PROPOSED PHYSICAL INFRASTRUCTURE
SUMMARY OF WORKS COST | [13 empty] | FINANCES DISTRIBUTION IN DISTRICTS
|  | Water | Community | Stormwater | Access |  | Street | Street | Solid | Tagging / | Trunk |  |  |  |  | SUB-COMPONENT: WATER SUPPLY SCHEMES
|  | Supply | Latrines | Drainage | Internal | Foot | Pavement | Lighting | Waste | Numbering | Infrastructure / | Total
No. | District | Schemes |  |  | Pathways | Bridges |  |  | Management | Streets | Hydel Power | (% Share) |  | S. |  | Spring-based |  | Ground Water-based
|  | No. | No. | (Linear Meter) | (Kilometers) | (Linear Meter) | (Linear Meter) | (No. of Poles) | No. of Bin/Depot | Job |  |  |  | No. | District | Gravity | Pumping | Tubewell | Open Well | Hand Pump | Total
1 | Muzaffarabad | 475.9135 | 310.0734 | 92998.464 | 140.4 | 1572.48 | 21163.9235 | 165.6404 | 178.4533 | 1 |  | 28% |  | 1 | Muzaffarabad | 232.1865 | 25.7985 | 0 | 0 | 0 | 257.985 | 257.985
2 | Bagh | 207.7583 | 155.0367 | 46499.232 | 70.2 | 786.24 | 10581.9618 | 82.8202 | 89.2267 |  |  | 14% |  | 2 | Bagh | 116.0932 | 12.8993 | 0 | 0 | 0 | 128.9925 | 128.9925
3 | Poonch | 270.5476 | 121.8145 | 36535.1109 | 55.1571 | 617.76 | 8314.3985 | 65.073 | 70.1067 |  |  | 11% |  | 3 | Poonch | 91.2161 | 10.1351 | 0 | 0 | 0 | 101.3512 | 101.3512
4 | Sudhnoti | 147.1621 | 66.4443 | 19928.2423 | 30.0857 | 336.96 | 4535.1265 | 35.4944 | 38.24 |  |  | 6% |  | 4 | Sudhnoti | 44.226 | 11.0565 | 0 | 0 | 0 | 55.2825 | 55.2825
5 | Kotli | 248.7358 | 254.7031 | 76391.5954 | 115.3286 | 1291.68 | 17384.6515 | 136.0618 | 146.5867 |  |  | 23% |  | 5 | Kotli | 169.533 | 42.3832 | 0 | 0 | 0 | 211.9162 | 211.9162
6 | Mirpur | 44.7308 | 77.5183 | 23249.616 | 35.1 | 393.12 | 5290.9809 | 41.4101 | 44.6133 |  |  | 7% |  | 6 | Mirpur | 19.3489 | 6.4496 | 6.4496 | 19.3489 | 12.8993 | 64.4963 | 64.4963
7 | Bhimber | 65.6138 | 121.8145 | 36535.1109 | 55.1571 | 617.76 | 8314.3985 | 65.073 | 70.1067 |  |  | 11% |  | 7 | Bhimber | 30.4054 | 10.1351 | 10.1351 | 30.4054 | 20.2703 | 101.3512 | 101.3512
Total: |  | 1460.4619 | 1107.405 | 332137.3714 | 501.4286 | 5616 | 75585.4412 | 591.573 | 637.3333 |  |  | 100% |  |  | Total | 703.0091 | 118.8574 | 16.5847 | 49.7542 | 33.1695 | 921.375 | 921.375
| Community Share | 184.275 | 0 | 28.08 | 35.1 | 28.08 | 14.04 | 1.053 | 2.106 | 0.351 | 0 | 293.085 | 17.68%
| Project Balance | 737.1 | 26.325 | 112.32 | 140.4 | 112.32 | 56.16 | 4.212 | 8.424 | 1.404 | 165.75 | 1364.415
| LGRDD Share | 151.1055 | 6.5812 | 28.08 | 35.1 | 28.08 | 14.04 | 1.053 | 2.106 | 0.351 | 33.15 | 266.4968 | 16.08%
| WB Share | 585.9945 | 19.7437 | 84.24 | 105.3 | 84.24 | 42.12 | 3.159 | 6.318 | 1.053 | 132.6 | 1064.7683 | 64.24%
Total Cost (Rs. mil.): |  | 921.375 | 26.325 | 140.4 | 175.5 | 140.4 | 70.2 | 5.265 | 10.53 | 1.755 | 165.75 | 1657.5
Total Cost (USD mil.): |  | 14.175 | 0.405 | 2.16 | 2.7 | 2.16 | 1.08 | 0.081 | 0.162 | 0.027 | 2.55 | 25.5 | 25.5
|  | 52.5% | 1.5% | 8% | 10% | 8% | 4% | 0.3% | 0.6% | 0.1%
Notes / Assumptions
1 USD = Pak Rs. 65.0
Table 4.1
PROPOSED PHYSICAL INFRASTRUCTURE
SUMMARY OF DISTRICT WISE COST DISTRIBUTION
|  | Water | Community | Stormwater | Access |  | Street | Street | Solid | Tagging / | Trunk
|  | Supply | Latrines | Drainage | Internal | Foot | Pavement | Lighting | Waste | Numbering | Infrastructure / | Total
No. | District | Schemes |  |  | Pathways | Bridges |  |  | Management | Streets | Hydel Power
|  | Rs | Rs | Rs | Rs | Rs | Rs | Rs | Rs | Rs | Rs
1 | Muzaffarabad | 257.985 | 7.371 | 39.312 | 49.14 | 39.312 | 19.656 | 1.4742 | 2.9484 | 0.4914 | 46.41 | 464.1 |  | 28%
2 | Bagh | 128.9925 | 3.6855 | 19.656 | 24.57 | 19.656 | 9.828 | 0.7371 | 1.4742 | 0.2457 | 23.205 | 232.05 |  | 14%
3 | Poonch | 101.3512 | 2.8958 | 15.444 | 19.305 | 15.444 | 7.722 | 0.57915 | 1.1583 | 0.19305 | 18.2325 | 182.325 |  | 11%
4 | Sudhnoti | 55.2825 | 1.5795 | 8.424 | 10.53 | 8.424 | 4.212 | 0.3159 | 0.6318 | 0.1053 | 9.945 | 99.45 |  | 6%
5 | Kotli | 211.9162 | 6.0548 | 32.292 | 40.365 | 32.292 | 16.146 | 1.2109 | 2.4219 | 0.40365 | 38.1225 | 381.225 |  | 23%
6 | Mirpur | 64.4963 | 1.8428 | 9.828 | 12.285 | 9.828 | 4.914 | 0.36855 | 0.7371 | 0.12285 | 11.6025 | 116.025 |  | 7%
7 | Bhimber | 101.3512 | 2.8958 | 15.444 | 19.305 | 15.444 | 7.722 | 0.57915 | 1.1583 | 0.19305 | 18.2325 | 182.325 |  | 11%
Total: |  | 921.375 | 26.325 | 140.4 | 175.5 | 140.4 | 70.2 | 5.265 | 10.53 | 1.755 | 165.75 | 1657.5
Total Cost (Rs. mil.): |  | 921.375 | 26.325 | 140.4 | 175.5 | 140.4 | 70.2 | 5.265 | 10.53 | 1.755 | 165.75 | 1657.5
Total Cost (USD mil.): |  | 14.175 | 0.405 | 2.16 | 2.7 | 2.16 | 1.08 | 0.081 | 0.162 | 0.027 | 2.55 | 25.5
Notes / Assumptions
1 USD = Pak Rs. 65.0

## Table 4.2
Table 4.2
PROPOSED PHYSICAL INFRASTRUCTURE
TARGET POPULATION FOR WATER SUPPLY SCHEMES
S. |  | Spring-based |  | Ground Water-based
No. | District | Gravity | Pumping | Tubewell | Open Well | Hand Pump | Total
1 | Muzaffarabad | 255522.7786 | 20435.3748 | 0 | 0 | 0 | 275958.1534
2 | Bagh | 98364.1661 | 7013.2361 | 0 | 0 | 0 | 105377.4022
3 | Poonch | 101710.1504 | 5977.6704 | 0 | 0 | 0 | 107687.8208
4 | Sudhnoti | 43648.3567 | 8224.6927 | 0 | 0 | 0 | 51873.0494
5 | Kotli | 126338.4732 | 36222.8267 | 0 | 0 | 0 | 162561.2998
6 | Mirpur | 13778.3789 | 5344.5685 | 2118.1034 | 14557.1473 | 11405.1724 | 47203.3706
7 | Bhimber | 21651.7383 | 10009.5122 | 3328.4483 | 22875.5172 | 17922.4138 | 75787.6298
| Total | 661014.0421 | 93227.8814 | 5446.5517 | 37432.6646 | 29327.5862 | 826448.726 | 826448.726
Notes / Assumptions
| The total targeted population (Rural & Peri-urban) for all types of Water Supply Schemes is |  |  |  |  | 826448.726

## Table 4.3 & 4.4
Table 4.3
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: COMMUNITY LATRINES (Peri-Urban)
|  | Population |  |  |  |  | Average Pop. | No. of | Av. Cost / | Total | Total
No. | District | at 2000 | Peri-Urban |  | Target for Peri-Urban |  | size | Schemes | Scheme | Cost | Cost
|  |  | % | No. | % | No. | >1000 | No. | Rs. (mil.) | Rs. (mil.) | USD (mil.)
1 | Muzaffarabad | 655543 | 20% | 131108.6 | 10% | 13110.86 | 3300 | 4.1769 | 0.3 | 1.2531 | 0.019278
2 | Bagh | 386548 | 20% | 77309.6 | 10% | 7730.96 | 3300 | 2.0884 | 0.3 | 0.62653 | 0.009639
3 | Poonch | 363067 | 20% | 72613.4 | 10% | 7261.34 | 3300 | 1.6409 | 0.3 | 0.49228 | 0.0075735
4 | Sudhnoti | 205921 | 20% | 41184.2 | 10% | 4118.42 | 3300 | 0.89505 | 0.3 | 0.26852 | 0.004131
5 | Kotli | 536893 | 20% | 107378.6 | 10% | 10737.86 | 3300 | 3.431 | 0.3 | 1.0293 | 0.015835
6 | Mirpur | 217941 | 80% | 174352.8 | 5% | 8717.64 | 3300 | 1.0442 | 0.3 | 0.31327 | 0.0048195
7 | Bhimber | 295107 | 80% | 236085.6 | 5% | 11804.28 | 3300 | 1.6409 | 0.3 | 0.49228 | 0.0075735
| Total | 2661020 |  | 840032.8 |  | 63481.36 |  | 14.9175 | 0.3 | 4.4752 | 0.06885
Notes / Assumptions
In Peri-Urban areas, a community latrine with two Water Closets and two Wash Hand Basins each for Men and Women is proposed.
For Typcial Layout of Latrines, see Attachment 4.11
The Unit Cost for Community Latrine in the Rural area is based on IDA RWSS completed work. The Unit Cost for Community Latrine in the Peri-Urban area is based on market rates. The cost of land is not included in the estimate.
Table 4.4
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: COMMUNITY LATRINES (Rural)
|  | Population |  |  |  |  | Average Pop. | No. of | Av. Cost / | Total | Total
No. | District | at 2000 | Rural |  | Target for Rural |  | size | Schemes | Scheme | Cost | Cost
|  |  | % | No. | % | No. | < 250 | No. | Rs. (mil.) | Rs. (mil.) | USD (mil.)
1 | Muzaffarabad | 655543 | 80% | 524434.4 | 20% | 104886.88 | 250 | 305.8965 | 0.02 | 6.1179 | 0.094122
2 | Bagh | 386548 | 80% | 309238.4 | 20% | 61847.68 | 250 | 152.9483 | 0.02 | 3.059 | 0.047061
3 | Poonch | 363067 | 80% | 290453.6 | 20% | 58090.72 | 250 | 120.1736 | 0.02 | 2.4035 | 0.036977
4 | Sudhnoti | 205921 | 80% | 164736.8 | 20% | 32947.36 | 250 | 65.5493 | 0.02 | 1.311 | 0.020169
5 | Kotli | 536893 | 80% | 429514.4 | 20% | 85902.88 | 250 | 251.2721 | 0.02 | 5.0254 | 0.077314
6 | Mirpur | 217941 | 20% | 43588.2 | 20% | 8717.64 | 250 | 76.4741 | 0.02 | 1.5295 | 0.02353
7 | Bhimber | 295107 | 20% | 59021.4 | 20% | 11804.28 | 250 | 120.1736 | 0.02 | 2.4035 | 0.036977
| Total | 2661020 |  | 1820987.2 |  | 364197.44 |  | 1092.4875 | 0.02 | 21.8498 | 0.33615
Notes / Assumptions
In Rural areas, the community latrine can be for Schools, Mosques, BHUs. The exisiting design used for schools is proposed to be used.
The Unit Cost for Community Latrine in the Rural area is based on IDA RWSS completed work. The Unit Cost for Community Latrine in the Peri-Urban area is based on market rates. The cost of land is not included in the estimate.

## Table 4.5
Table 4.5
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STORMWATER DRAINAGE
|  |  | Low Income/Peri-Urban |  | Rural |  | Total |  |  | Terrain Analysis | [7 empty] | Target Region/Area Analysis
S. |  | Terrain: | Hilly | Flat/Rolling | Hilly | Flat/Rolling | Hilly | Flat/Rolling
No. | District | Section: | Type A | Type B | Type A | Type B | Type A | Type B | [9 empty] | Hilly |  |  | Flat
|  |  | (Linear Meter) | (Linear Meter) | (Linear Meter) | (Linear Meter) | (Linear Meter) | (Linear Meter) |  | No. | District | Hilly | Flat | Total | Hilly | Flat | Rs | Peri @86% | Rural @14% | Total | Peri @86% | Rural @14% | Total
1 | Muzaffarabad |  | 58157.8234 | 21820.8557 | 9467.5526 | 3552.2323 | 67625.376 | 25373.088 |  | 1 | Muzaffarabad | 97% | 3% |  |  |  | 39.312 | 32.7941 | 5.3386 | 38.1326 | 1.0142 | 0.16511 | 1.1794
2 | Bagh |  | 29078.9117 | 10910.4278 | 4733.7763 | 1776.1162 | 33812.688 | 12686.544 |  | 2 | Bagh | 90% | 10% |  |  |  | 19.656 | 15.2137 | 2.4767 | 17.6904 | 1.6904 | 0.27518 | 1.9656
3 | Poonch |  | 22847.7163 | 8572.479 | 3719.3957 | 1395.5198 | 26567.112 | 9967.9989 |  | 3 | Poonch | 90% | 10% |  |  |  | 15.444 | 11.9537 | 1.9459 | 13.8996 | 1.3282 | 0.21622 | 1.5444
4 | Sudhnoti |  | 12462.3907 | 4675.8976 | 2028.7613 | 761.1926 | 14491.152 | 5437.0903 |  | 4 | Sudhnoti | 90% | 10% |  |  |  | 8.424 | 6.5202 | 1.0614 | 7.5816 | 0.72446 | 0.11794 | 0.8424
5 | Kotli |  | 47772.4978 | 17924.2743 | 7776.9182 | 2917.9051 | 55549.416 | 20842.1794 |  | 5 | Kotli | 80% | 20% |  |  |  | 32.292 | 22.2169 | 3.6167 | 25.8336 | 5.5542 | 0.90418 | 6.4584
6 | Mirpur |  | 14539.4558 | 5455.2139 | 2366.8882 | 888.0581 | 16906.344 | 6343.272 |  | 6 | Mirpur | 25% | 75% |  |  |  | 9.828 | 2.113 | 0.34398 | 2.457 | 6.3391 | 1.0319 | 7.371
7 | Bhimber |  | 22847.7163 | 8572.479 | 3719.3957 | 1395.5198 | 26567.112 | 9967.9989 |  | 7 | Bhimber | 20% | 80% |  |  |  | 15.444 | 2.6564 | 0.43243 | 3.0888 | 10.6255 | 1.7297 | 12.3552
| Total |  | 207706.512 | 77931.6274 | 33812.688 | 12686.544 | 241519.2 | 90618.1714 | 241519.2 |  | Total | [5 empty] | 140.4 | 93.4679 | 15.2157 | 108.6836 | 27.2761 | 4.4403 | 31.7164
| Average Cost/Linear Meter (Rs.) |  | 450 | 350 | 450 | 350 | 450 | 350 | [8 empty] | 140.4 |  |  | 450 |  |  | 350
| Total Cost (Rs. mil.) |  | 93.4679 | 27.2761 | 15.2157 | 4.4403 | 108.6836 | 31.7164 | [11 empty] | 241519.2 |  |  | 90618.1714
| Total Cost (USD mil.) |  | 1.438 | 0.41963 | 0.23409 | 0.068312 | 1.6721 | 0.48794
|  |  |  | 120.744 |  | 19.656 | 241519.2 | 90618.1714 |  | Total LM now available |  |  | 476000
[7 empty] | 108.6836 | 31.7164 |  |  |  |  | #DIV/0!
Notes / Assumptions
Length of drains proposed is in proportion to the population breakup.
The following breakup of terrain (Hilly and Flat/Rolling) has been assumed in the above table.
| District | Hilly | Flat/Rolling
| Muzaffarabad | 97% | 3%
| Bagh | 90% | 10%
| Poonch | 90% | 10%
| Sudhnoti | 90% | 10%
| Kotli | 80% | 20%
| Mirpur | 25% | 75%
| Bhimber | 20% | 80%
86% of total drainage proposed is in Peri-Urban / Low Income areas.
For Typical Cross Section of Drain Type A & B, see Attachment 4.5
Unit Costs based on the Composite Schedule of Rates 1998, with average 12% premium.
1 USD = Pak Rs. 65.0

## Table 4.6
Table 4.6
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: ACCESS - INTERNAL PATHWAYS(upgradation)
S. |  | Rural | Total
No. | District | (Kilometers) | (Kilometers)
1 | Muzaffarabad | 140.4 | 140.4
2 | Bagh | 70.2 | 70.2
3 | Poonch | 55.1571 | 55.1571
4 | Sudhnoti | 30.0857 | 30.0857
5 | Kotli | 115.3286 | 115.3286
6 | Mirpur | 35.1 | 35.1
7 | Bhimber | 55.1571 | 55.1571
| Total | 501.4286 | 501.4286
| Average Cost/Kilometer (Rs.) | 0.35
| Total Cost (Rs. mil.) | 175.5 | 175.5
| Total Cost (USD mil.) | 2.7 | 2.7
Notes / Assumptions
Length of pathways proposed in a district is in proportion to the population breakup.
For Typical Cross Section of Pathway, see Attachment 4.6
Unit Costs based on the Composite Schedule of Rates 1998.

## Table 4.7
Table 4.7
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: ACCESS - FOOT BRIDGES
S. |  | Rural | Total
No. | District | (Linear Meter) | (Linear Meter)
1 | Muzaffarabad | 1572.48 | 1572.48
2 | Bagh | 786.24 | 786.24
3 | Poonch | 617.76 | 617.76
4 | Sudhnoti | 336.96 | 336.96
5 | Kotli | 1291.68 | 1291.68
6 | Mirpur | 393.12 | 393.12
7 | Bhimber | 617.76 | 617.76
| Total | 5616 | 5616
| Average Cost/Linear Meter (Rs.) | 25000
| Total Cost (Rs. mil.) | 140.4 | 140.4
| Total Cost (USD mil.) | 2.16 | 2.16
Notes / Assumptions
Length of Foot Bridges proposed in a district is in proportion to the population breakup.
A Typical Suspension Bridge Section is attached as attachment No.4.7.
Average length of Suspension Bridge is assumed to be 61.0 m (200 ft).
Unit Cost assumed for Foot Bridge (Wooden) is based on LGRDD's past work experience.
For Suspension Bridges (Jeepable) design paramenters of Central Design Office (CDO) wil be used.

## Table 4.8
Table 4.8
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STREET PAVEMENT (SIDEWALKS / WALKWAYS)
Low Income/Peri-Urban
S. |  | Terrain: | Hilly | Flat / Rolling | Total
No. | District | Section: | Type A | Type B | Type A+B
|  |  | (Linear Meter) | (Linear Meter) | (Linear Meter)
1 | Muzaffarabad |  | 15151.5 | 6012.4235 | 21163.9235 | 19.656
2 | Bagh |  | 7575.75 | 3006.2118 | 10581.9618 | 9.828
3 | Poonch |  | 5952.375 | 2362.0235 | 8314.3985 | 7.722
4 | Sudhnoti |  | 3246.75 | 1288.3765 | 4535.1265 | 4.212
5 | Kotli |  | 12445.875 | 4938.7765 | 17384.6515 | 16.146
6 | Mirpur |  | 3787.875 | 1503.1059 | 5290.9809 | 4.914
7 | Bhimber |  | 5952.375 | 2362.0235 | 8314.3985 | 7.722
| Total |  | 54112.5 | 21472.9412 | 75585.4412
| Average Cost/Linear Meter (Rs.) |  | 960 | 850
| Total Cost (Rs. mil.) |  | 51.948 | 18.252 | 70.2 | 70.2
| Total Cost (USD mil.) |  | 0.7992 | 0.2808 | 1.08
70.2
Notes / Assumptions
Length of Street Pavement proposed is in proportion to the population breakup.
In Peri-Urban areas, approximately 74% terrain is Hilly and 26% Flat/Rolling.
For Typical Cross Section of Street Pavement Type A & B, see Attachment 4.8
Unit Cost based on the Composite Schedule of Rates 1998, with average 12% premium.

## Table 4.9
Table 4.9
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STREET LIGHTING
Low Income/
S. | District | Peri-Urban
No. |  | (No. of Units)
1 | Muzaffarabad | 210.6
2 | Bagh | 105.3
3 | Poonch | 82.7357
4 | Sudhnoti | 45.1286
5 | Kotli | 172.9929
6 | Mirpur | 52.65
7 | Bhimber | 82.7357
| Total | 752.1429
| Average Cost/Pole (Rs.) | 7000
| Total Cost (Rs. mil.) | 5.265
| Total Cost (USD mil.) | 0.081
Notes / Assumptions
Target Project Population for street lighting is 28,000
One street light proposed to be provided for every 48 persons or 6 households.
Unit Cost of Street Light includes the provision of Mild Steel Pole, light bulb, foundations, cable, control box, etc. and is estimated at market rates.

## Table 4.10
Table 4.10
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: SOLID WASTE MANAGEMENT
[7 empty] | Low Income/Peri-Urban |  |  | Table 4.11
S. |  | Population |  |  |  |  | Waste Collection Bin | Waste Collection Depot
No. | District | at 2000 | Peri-Urban |  | Target for Peri-Urban |  | Type A | Type B | Total
|  |  | % | No. | % | No. | (No.) | (No.)
1 | Muzaffarabad | 655543 | 20% | 131108.6 | 13.84% | 18144 | 168 | 10.4533 |  | PROPOSED PHYSICAL INFRASTRUCTURE
2 | Bagh | 386548 | 20% | 77309.6 | 11.73% | 9072 | 84 | 5.2267 |  | SUB-COMPONENT: COMMUNITY LATRINES (Peri-Urban)
3 | Poonch | 363067 | 20% | 72613.4 | 9.816% | 7128 | 66 | 4.1067
4 | Sudhnoti | 205921 | 20% | 41184.2 | 9.441% | 3888 | 36 | 2.24 |  |  |  | Population |  |  |  |  | Average Pop. | No. of | Av. Cost / | Total | Total
5 | Kotli | 536893 | 20% | 107378.6 | 13.88% | 14904 | 138 | 8.5867 |  | No. | District | at 2000 | Peri-Urban |  | Target for Peri-Urban |  | size | Schemes | Scheme | Cost | Cost
6 | Mirpur | 217941 | 80% | 174352.8 | 2.602% | 4536 | 42 | 2.6133 |  |  |  |  | % | No. | % | No. | >1000 | No. | Rs. (mil.) | Rs. (mil.) | USD (mil.)
7 | Bhimber | 295107 | 80% | 236085.6 | 3.019% | 7128 | 66 | 4.1067 |  | 1 | Muzaffarabad | 655543 | 20% | 131108.6 | 10% | 13110.86 | 3300 | 4 | 0.3 | 1.2 | 0.018462
| Total | 2661020 |  | 840032.8 |  | 64800 | 600 | 37.3333 |  | 2 | Bagh | 386548 | 20% | 77309.6 | 10% | 7730.96 | 3300 | 2 | 0.3 | 0.6 | 0.0092308
| Average Cost/No. (Rs.) | [5 empty] | 2000 | 15000 |  | 3 | Poonch | 363067 | 20% | 72613.4 | 10% | 7261.34 | 3300 | 2 | 0.3 | 0.6 | 0.0092308
| Total Cost (Rs. mil.) | [5 empty] | 1.2 | 0.56 | 1.76 | 4 | Sudhnoti | 205921 | 20% | 41184.2 | 10% | 4118.42 | 3300 | 1 | 0.3 | 0.3 | 0.0046154
| Total Cost (USD mil.) | [5 empty] | 0.018462 | 0.0086154 | 0.027077 | 5 | Kotli | 536893 | 20% | 107378.6 | 10% | 10737.86 | 3300 | 3 | 0.3 | 0.9 | 0.013846
[10 empty] | 6 | Mirpur | 217941 | 80% | 174352.8 | 5% | 8717.64 | 3300 | 4 | 0.3 | 1.2 | 0.018462
[10 empty] | 7 | Bhimber | 295107 | 80% | 236085.6 | 5% | 11804.28 | 3300 | 4 | 0.3 | 1.2 | 0.018462
| Notes / Assumptions | [9 empty] | Total | 2661020 |  | 840032.8 |  | 63481.36 |  | 20 |  | 6 | 0.092308
Each household produces 3/4 cubic feet solid waste per day; the total waste per day for 18 households is 3/4 x 18 = 13.5 cubic feet. Two (2 No.) Waste Collection Bins - Type A (7 cubic feet each) - appropriately located are proposed to be provided at the street level to serve 18 households (108 persons).
At least one (1 No.) Waste Collection Depot - Type B - (design capacity 140 cubic feet) appropriately located - is proposed to be provided to collect solid waste from 14 Collection Bins type A.
For Typcial Plans/Sections of Waste Collection Bins/Depots Type A & B, see Annex - Works 18.6
The Unit Cost of the Bin is market-based and the Depot on the Composite Schedule of Rates 1998, with average 12% premium.

## Table 4.12
Table 4.12
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: TAGGING/NUMBERING STREETS & HOMES
As this is a totally new initiative therefore it is proposed to do a Pilot Project in the Muzaffarabad District in the Low Income/Peri-Urban area. Depending on the outcome of this activity and availability of funds, the scope maybe expanded.
Funds amounting to Pak Rs. 3.25 m are proposed to be set aside for this Pilot Project.
Low Income/
S. | District | Peri-Urban | Total
No. |  | (Job)
1 | Muzaffarabad | 1 | 1
| Total | 1 | 1
| Lumpsum for Job | 1.76 | 1.76
| Total Cost (Rs. mil.) | 1.76 | 1.76
| Total Cost (USD mil.) | 0.027077 | 0.027077

## Table 4.13
Table 4.13
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: INTEGRATION WITH TRUNK INFRASTRUCTURE & MICRO HYDEL POWER GENERATION
Under this sub-component it is proposed to undertake the following activities:
a. Provide necessary facilities to integrate the IDA RWSS infrastructure with the trunk infrastructure.
b. To provide micro hydel power generation facilities in the AJK.
Funds amounting to Pak Rs. 325 m are proposed to be set aside for this sub-component.
Low Income/
S. | District | Peri-Urban | Total
No. |  | (Job)
1 | Muzaffarabad | 1 | 1
2 | Bagh | 1 | 1
3 | Poonch | 1 | 1
4 | Sudhnoti | 1 | 1
5 | Kotli | 1 | 1
6 | Mirpur | 1 | 1
7 | Bhimber | 1 | 1
| Total | 7 | 7
| Lumpsum for Jobs | 165.75 | 165.75
| Total Cost (Rs. mil.) | 165.75 | 165.75
| Total Cost (USD mil.) | 2.55 | 2.55

## Att.4.11
Attachment of Table 4.11
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: SANITATION - LATRINES
A. | For Community Latrines (schools, mosques, BHUs) in the Rural areas, follow the existing Design.
B. | Urban Public Latrine
in Peri-Urban Area
Notes / Assumptions
Total Covered area = 324 sft
Size of each toilet is 5ft x 3 ft.
Entrance passage is 3 ft wide.
Separate entrance for men and women.
Estimated cost @ Rs. 900 /sft: 291,600/- (Say Rs.0.3 million)
Construction of an urban public latrine consists following:
i) | Excavation in foundation.
ii) | Brick masonry in walls/foundation.
iii) | RCC (1:2:4) roofing.
iv) | Glazed tiles on internal walls.
v) | Joinery Work (Deodar Wood)
vi) | P/F of Ist Class Sanitary appliances
vii) | P/F of Electrification.
viii) | P/F of Water Tank (Fiber Glass/Polyethelyne).
ix) | Constt. Of Septic Tank.
x) | White Washing/Painting.
18'-0"
18'-0"
Not to Scale
Men
Women
Typical Layout

## Att. T4.5
Attachement of Table 4.5
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STORMWATER DRAINAGE
Item Rate Analysis
Drain Type: A (for Hilly terrain)
Measurement
S.No. | Item Description | L | B | H | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
|  | m | m | m
1 | Excavation in Hard Soil | 1 | 0.7 | 0.58 | cu.m. | 0.406 | 31.65 | 12.8499
2 | PCC 1:4:8 | 1 | 0.38 | 0.075 | cu.m. | 0.0285 | 1063.75 | 30.3169
3 | PCC 1:2:4 | 1 | 1.17 | 0.15 | cu.m. | 0.1755 | 1987.7 | 348.8413
[7 empty] | Total: | 392.0081
[5 empty] | Add 12% average premium |  |  | 47.041
439.0491
Say Rs. 450 per LM
Item Rate Analysis
Drain Type: B (for Flat/Rolling terrain)
Measurement
S.No. | Item Description | L | B | H | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
|  | m | m | m
1 | Excavation in Hard Soil | 1 | 0.7 | 0.58 | cu.m. | 0.406 | 32.6 | 13.2356
2 | PCC 1:4:8 | 1 | 0.38 | 0.075 | cu.m. | 0.0285 | 1063.75 | 30.3169
3 | PCC 1:3:6 | 1 | 1.17 | 0.15 | cu.m. | 0.1755 | 1293.4 | 226.9917
4 | 12 mm plaster in 1:3 CSM | 1 | 0.94 | 0 | Sq.m. | 0.94 | 43.45 | 40.843
[7 empty] | Total: | 311.3872
[5 empty] | Add 12% average premium |  |  | 37.3665
348.7536
Say Rs. 350 per LM
Notes / Assumptions
The above rates are based on the Composite Schedule of Rates 1998 (Government of Punjab). Premium @ 12% is based on the average of 20 various regions of AJK.
150 mm
150 mm
400 mm
150 mm
380 mm
75 mm PCC 1:4:8
PCC 1:2:4
(Not to Scale)
Type A
Varies 300 - 375 mm
150 mm
150 mm
150 mm
400 mm
380 mm
12 mm Pl
Varies 300 - 375 mm
150 mm
75 mm PCC 1:4:8
150 mm
PCC 1:3:6
(Not to Scale)
Type B

## Att. T4.6
Attachment of Table 4.6
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: ACCESS - INTERNAL PATHWAYS(upgradation)
Item Rate Analysis per Km length of Rural Road. Quantities based on historical data
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Pick Work | 1000 Cft. | 9561.5 | 706.65 | 6756.634
2 | Jamper Work | 1000 Cft. | 8011.75 | 1379.4 | 11051.408
3 | Blasting Work | 1000 Cft. | 6524 | 1834.75 | 11969.909
4 | Earth Filling | 1000 Cft. | 7103 | 653.4 | 4641.1002
5 | R.R Retaining Walls/Breast Walls | 100 Cft. | 7600.4 | 1227.65 | 93306.3106
6 | Wire Crates | 100 Sft. | 868 | 895 | 7768.6
7 | Cross Drainage | Nos. | 3 | 25000 | 75000
8 | Stone Soling 6" th. With sand fill | 100 Cft | 19680 | 850 | 167280
9 | Side berms | 100Sft | 6560 | 100 | 6560
10 | Stone pitching 3"Th. on berm and drain | 100 Cft. | 10037 | 4 | 40148
|  |  | Total: |  | 424481.9617
|  |  | Deduction 13% on Item No.5 |  | -12129.8204
|  |  | Total: |  | 412352.1413
**** | Contractors' profit |  | Deduct 15% **** |  | -61852.8212
|  |  | Total: |  | 350499.3201
|  |  | Say |  | 350000
Notes / Assumptions

## Att.T4.6r
Attachment of Table 4.6
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STREET PAREMENT (Side Walks/Walkways)
Type A (for hilly terrain)
Item Rate Analysis per meter length. Quantities based on Schedule of Rates 1998 & Market Rates
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 0.3425 | 31.65 | 10.8401
2 | P.C.C (1:4:8) in bed | M3 | 0.122 | 1063.75 | 129.7775
3 | Sand bedding | M3 | 0.061 | 600 | 36.6
4 | Course rubble massonary dressed stone | M2 | 1.22 | 290 | 353.8
5 | Kerb Stone P.C.C (1:2:4) | M3 | 0.0375 | 2069.4 | 77.6025
|  |  | Total: |  | 608.6201
S.R = | Schedule Rates 1998 |  | Add 12% above on item 1,2,5 |  | 26.1864
M.R = | Market Rates |  | Total: |  | 634.8065
|  |  | Deduct 15% Contractor Profit |  | -95.221
|  |  | Total: |  | 539.5856
|  |  | Say |  | 539.5856
50 mm Sand Bed
100 mm Dressed Stone
100 mm PCC 1:4:8
1.22 m
100 mm
375 mm
Compacted Sub-Grade

## Att. T4.8
Attachment of Table 4.8
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STREET PAVEMENT (SIDEWALKS / WALKWAYS)
Item Rate Analysis
Rural Area
Type: A (for Hilly terrain)
Measurement
S.No. | Item Description | L | B | H | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
|  | m | m | m
1 | Excavation and backfilling in hard/rock material | 1 | 1.22 | 0.25 | cu.m. | 0.305 | 31.65 | 9.6532
| - Ditto - for Kerb Stone | 1 | 0.1 | 0.325 | cu.m. | 0.0325 | 31.65 | 1.0286
2 | PCC 1:4:8 in Bed | 1 | 1.22 | 0.1 | cu.m. | 0.122 | 1063.75 | 129.7775
3 | Sand Bedding | 1 | 1.22 | 0.05 | cu.m. | 0.061 | 706 | 43.066
4 | Coursed Rubble Masonry in dressed stone in 1:3 CSM | 1 | 1.22 | 0 | sq.m. | 1.22 | 152.39 | 185.9158
5 | Kerb Stone PCC 1:2:4 | 1 | 0.1 | 0.375 | cu.m. | 0.0375 | 2434.25 | 91.2844
[7 empty] | Total: | 460.7255
[6 empty] | Add 12% premium: |  | 46.0726
[7 empty] | G. Total: | 506.7981
Say Rs. 510 per LM
Typical Cross Section of Sidewalk
Note: For Walkway in a steet, add a Kerb stone of half the height on either side.)
(Not to Scale)
Item Rate Analysis
Rural Area
Type: B (for Flat/Rolling terrain)
Measurement
S.No. | Item Description | L | B | H | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
|  | m | m | m
1 | Excavation and backfilling in hard/rock material | 1 | 1.22 | 0.25 | cu.m. | 0.305 | 31.65 | 9.6532
| - Ditto - for Kerb Stone | 1 | 0.1 | 0.325 | cu.m. | 0.0325 | 31.65 | 1.0286
2 | PCC 1:4:8 in Bed | 1 | 1.22 | 0.1 | cu.m. | 0.122 | 1063.75 | 129.7775
3 | Sand Bedding | 1 | 1.22 | 0.05 | cu.m. | 0.061 | 706 | 43.066
4 | Brick on Edge in 1:3 CSM | 1 | 1.22 | 0 | sq.m. | 1.22 | 170 | 207.4
5 | Kerb Stone PCC 1:2:4 | 1 | 0.1 | 0.375 | cu.m. | 0.0375 | 1987.7 | 74.5387
[7 empty] | Total: | 465.4641
[6 empty] | Add 12% premium: |  | 55.8557
[7 empty] | G. Total: | 521.3198
Say Rs. 530 per LM
Typical Cross Section of Sidewalk
Note: For Walkway in a steet, add a Kerb stone of half the height on either side.)
(Not to Scale)
Item Rate Analysis | [6 empty] | Attachement of Table 4.8
Peri-Urban Area
Type: A (for Hilly terrain)
Measurement
S.No. | Item Description | L | B | H | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
|  | m | m | m
1 | Excavation and backfilling in hard/rock material | 1 | 2.135 | 0.25 | cu.m. | 0.53375 | 31.65 | 16.8932
| - Ditto - for Kerb Stone | 1 | 0.15 | 0.325 | cu.m. | 0.04875 | 31.65 | 1.5429
2 | PCC 1:4:8 in Bed | 1 | 2.135 | 0.1 | cu.m. | 0.2135 | 1063.75 | 227.1106
3 | Sand Bedding | 1 | 2.135 | 0.05 | cu.m. | 0.10675 | 706 | 75.3655
4 | PCC 1:2:4 laid in Panels | 1 | 2.135 | 0 | sq.m. | 2.135 | 198.77 | 424.3739
5 | Kerb Stone PCC 1:2:4 | 1 | 0.15 | 0.375 | cu.m. | 0.05625 | 1987.7 | 111.8081
[7 empty] | Total: | 857.0943
[6 empty] | Add 12% premium: |  | 102.8513
[7 empty] | G. Total: | 959.9456
Say Rs. 960 per LM
Typical Cross Section of Sidewalk
Note: For Walkway in a steet, add a Kerb stone of half the height on either side.)
(Not to Scale)
Item Rate Analysis
Peri-Urban Area
Type: B (for Flat/Rolling terrain)
Measurement
S.No. | Item Description | L | B | H | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
|  | m | m | m
1 | Excavation and backfilling in hard/rock material | 1 | 2.135 | 0.25 | cu.m. | 0.53375 | 31.65 | 16.8932
| - Ditto - for Kerb Stone | 1 | 0.1 | 0.325 | cu.m. | 0.0325 | 31.65 | 1.0286
2 | PCC 1:4:8 in Bed | 1 | 2.135 | 0.1 | cu.m. | 0.2135 | 1063.75 | 227.1106
3 | Sand Bedding | 1 | 2.135 | 0.05 | cu.m. | 0.10675 | 706 | 75.3655
4 | Brick on Edge in 1:3 CSM | 1 | 2.135 | 0 | sq.m. | 2.135 | 170 | 362.95
5 | Kerb Stone PCC 1:2:4 | 1 | 0.1 | 0.375 | cu.m. | 0.0375 | 1987.7 | 74.5387
[7 empty] | Total: | 757.8867
[6 empty] | Add 12% premium: |  | 90.9464
[7 empty] | G. Total: | 848.8331
Say Rs. 850 per LM
Typical Cross Section of Sidewalk
Note: For Walkway in a steet, add a Kerb stone of half the height on either side.)
(Not to Scale)
50 mm Sand Bed
100 mm Dressed Stone
100 mm PCC 1:4:8
1.22 m
100 mm
375 mm
Compacted Sub-Grade
50 mm Sand Bed
Brick on Edge
100 mm PCC 1:4:8
1.22 m
100 mm
375 mm
Compacted Sub-Grade
50 mm Sand Bed
100 mm PCC 1:2:4
100 mm PCC 1:4:8
Varies 1.83 - 2.44; Av. 2.135 m
150 mm
375 mm
Compacted Sub-Grade
50 mm Sand Bed
Brick on Edge
100 mm PCC 1:4:8
100 mm
375 mm
Varies 1.83 - 2.44; Av. 2.135 m
Compacted Sub-Grade