## Table 1
Table 1: CISP:Summary Cost Timeline
No | Cost Components/ Sub Components | Total Cost |  | 2002 |  | 2003 |  | 2004 |  | 2005 |  | infrastructure upgrading and services
|  | PKR | USD | PKR | USD | PKR | USD | PKR | USD | PKR | USD | 9.2427 | 0 | 0
1 | Decentralized Planning and Implementation | 180.681 | 2.7797 | 27.1022 | 0.41696 | 54.2043 | 0.83391 | 54.2043 | 0.83391 | 45.1703 | 0.69493 | 18.4854 | 0.065 | 24.031
2 | Community Development | 125.23 | 1.9266 | 18.7845 | 0.28899 | 37.569 | 0.57798 | 37.569 | 0.57798 | 31.3075 | 0.48165 | 18.4854 | 0.13 | 48.062
3 | Infrastructure Upgrading and Services | 1232.36 | 18.9594 | 184.854 | 2.8439 | 369.708 | 5.6878 | 369.708 | 5.6878 | 308.09 | 4.7398 | 15.4045 | 0.195 | 60.0776
| Total Base Cost | 1538.271 | 23.6657 | 230.7406 | 3.5499 | 461.4813 | 7.0997 | 461.4813 | 7.0997 | 384.5677 | 5.9164 | 61.618 |  | 132.1706
| Physical Contingency @5% of No 3 Above | 61.618 | 0.94797 | 9.2427 | 0.1422 | 18.4854 | 0.28439 | 18.4854 | 0.28439 | 15.4045 | 0.23699
| Price Contingency * | 164.9796 | 2.5381 | 0 | 0 | 29.9963 | 0.46148 | 59.9926 | 0.92296 | 74.9907 | 1.1537 |  | difference | 193.7886
| G.Total | 1764.8686 | 27.1518 | 239.9834 | 3.6921 | 509.963 | 7.8456 | 539.9593 | 8.3071 | 474.963 | 7.3071
| Financing | Total |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4
|  | PKR | USD | PKR | USD | PKR | USD | PKR | USD | PKR | USD | #REF!
| International Development Association/Donors | 1300 | 20 | 195 | 3 | 390 | 6 | 390 | 6 | 325 | 5 | #REF!
| Government of AJK | 238.4673 | 3.6687 | 14.1705 | 0.21801 | 54.5223 | 0.8388 | 80.7037 | 1.2416 | 89.0709 | 1.3703 | #REF!
| Communities | 226.4013 | 3.4831 | 30.8129 | 0.47404 | 65.4407 | 1.0068 | 69.2556 | 1.0655 | 60.8921 | 0.9368 | #REF!
| Total | 1764.8686 | 27.1518 | 239.9834 | 3.6921 | 509.963 | 7.8456 | 539.9593 | 8.3071 | 474.963 | 7.3071
* @ Y1=0,Y2=6.5,Y3=13,Y4=19.5%

## Table 2
Table 2: Decentralized Planning and Implementation
No | Component/ Activity |  |  | Estimated Cost PKR | Estimated Cost USD
A | Technical Assistance
A.1 | Community Development Specialist (6MM) International |  |  | 4.875 | 0.075
A.2 | Procurement Specialist (12MM) National Firm |  |  | 0.976 | 0.015015
A.3 | Other Short Term Consultants (40MM) National Firm |  |  | 3.25 | 0.05
B | Incremental Staff Cost
B1 | State, District and Field Staff |  |  | 66.14 | 1.0175
C | Different Items( Operational Cost)
C1 | Vehicles,Motor Bikes,Equipment and Running Cost etc. |  |  | 72.44 | 1.1145
D | Overseas Training |  |  | 10 | 0.15385
E | Studies
E1 | Water Quality Testing |  |  | 3 | 0.046154
E2 | Baseline Surveys |  |  | 20 | 0.30769
| Total |  |  | 180.681 | 2.7797
MM = Man Months
Total Cost Summary of Decentralized Planning and Implementation Showing Contingencies |  |  |  |  | PKR in Million
| Total | Year 1 | Year 2 | Year 3 | Year 4
Base Cost | 180.68 | 27.1 | 54.2 | 54.2 | 45.17
Price Contingency* | 19.3772 | 0 | 3.523 | 7.046 | 8.8081
Total | 200.0572 | 27.1 | 57.723 | 61.246 | 53.9781
* @ Y1=0, Y2=6.5%, Y3=13% and Y4=19.5%

## Table 2.1
Table 2.1: Incremental Staff | [14 empty] | Allow
S.No | Name of Post |  | BPS | No. of Posts |  |  | Basic | Incr. | With | Estimated Cost PKR |  |  |  | Grand | 44.45%
|  |  |  | Ist Year | 2-4 Yr | Total | Pay | Rate | Allow. | Year 1 | Year 2 | Year 3 | Year 4 | Total PKR
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 15
STATE
Senior Staff
1 | Project Director | MC | B-19 | 1 | 1 | 1 | 12400 | 615 | 20986.8 | 251841.6 | 252456.6 | 253071.6 | 253686.6 | 1011056.4
2 | Superintending Engineer (Director Works) | ET | B-19 | 1 | 1 | 1 | 12400 | 615 | 20986.8 | 251841.6 | 252456.6 | 253071.6 | 253686.6 | 1011056.4
3 | Dy. Director (Human Resource Development) | CD | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 707958.36
4 | Dy.Director (Coordination) | MC | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 707958.36
5 | Dy.Director (Comminity Development) | CD | B-18 | 0 | 1 | 1 | 8135 | 585 | 14676.0075 | 0 | 176697.09 | 177282.09 | 177867.09 | 531846.27
6 | Dy.Director (Monitoring) | MC | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 707958.36
7 | Executive Engineer | ET | B-18 | 1 | 1 | 1 | 8135 | 585 | 14676.0075 | 176112.09 | 176697.09 | 177282.09 | 177867.09 | 707958.36
8 | Computer Program Officer | IT | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 544966.56
9 | Assistant Director (Environment) | ET | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 544966.56
10 | Assistant Engineer | ET | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 544966.56
11 | Accounts and Finance Officer | FAA | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 544966.56
12 | Audit Officer | FAA | B-17 | 1 | 1 | 1 | 6210 | 465 | 11295.345 | 135544.14 | 136009.14 | 136474.14 | 136939.14 | 544966.56
| Sub-Total |  |  | 11 | 12 | 12 |  |  |  | 1885852.26 | 2068444.35 | 2074924.35 | 2081404.35 | 8110625.31
Support Staff
1 | Data Processing Officer | IT | B-16 | 4 | 4 | 4 | 3805 | 295 | 6971.3225 | 334623.48 | 335803.48 | 336983.48 | 338163.48 | 1345573.92
2 | Sub-Engineer | ET | B-16 | 1 | 1 | 1 | 3805 | 295 | 6971.3225 | 83655.87 | 83950.87 | 84245.87 | 84540.87 | 336393.48
3 | Senior Scale Stenographer | CS | B-15 | 1 | 1 | 1 | 3285 | 265 | 6070.1825 | 72842.19 | 73107.19 | 73372.19 | 73637.19 | 292958.76
4 | Accountant | FAA | B-15 | 1 | 1 | 1 | 3285 | 265 | 6070.1825 | 72842.19 | 73107.19 | 73372.19 | 73637.19 | 292958.76
5 | Stenographer | CS | B-12 | 1 | 1 | 1 | 2745 | 195 | 4940.1525 | 59281.83 | 59476.83 | 59671.83 | 59866.83 | 238297.32
6 | Senior Auditor | FAA | B-11 | 1 | 1 | 1 | 2590 | 175 | 4616.255 | 55395.06 | 55570.06 | 55745.06 | 55920.06 | 222630.24
7 | Senior Clerk/Telephone Operator | CS | B-7 | 1 | 1 | 1 | 2220 | 120 | 3806.79 | 45681.48 | 45801.48 | 45921.48 | 46041.48 | 183445.92
8 | Junior Clerk | CS | B-5 | 3 | 3 | 3 | 2100 | 100 | 3533.45 | 127204.2 | 127504.2 | 127804.2 | 128104.2 | 510616.8
9 | Machine Operator | OS | B-5 | 1 | 1 | 1 | 2100 | 100 | 3533.45 | 42401.4 | 42501.4 | 42601.4 | 42701.4 | 170205.6
10 | Driver | OS | B-4 | 13 | 13 | 13 | 2040 | 85 | 3371.78 | 525997.68 | 527102.68 | 528207.68 | 529312.68 | 2110620.72
11 | Peon/ Attendents | OS | B-1 | 14 | 14 | 14 | 1870 | 55 | 2976.215 | 500004.12 | 500774.12 | 501544.12 | 502314.12 | 2004636.48
| Sub-Total |  |  | 41 | 41 | 41 |  |  |  | 1919929.5 | 1924699.5 | 1929469.5 | 1934239.5 | 7708338
DISTRICTS
Senior Staff
1 | Dy.Director (North + South) | MC | B-18 | 2 | 2 | 2 | 8135 | 585 | 14676.0075 | 352224.18 | 353394.18 | 354564.18 | 355734.18 | 1415916.72
2 | Executive Engineer (North + South) | ET | B-18 | 2 | 2 | 2 | 8135 | 585 | 14676.0075 | 352224.18 | 353394.18 | 354564.18 | 355734.18 | 1415916.72
3 | Assistant Engineer | ET | B-17 | 15 | 15 | 15 | 6210 | 465 | 11295.345 | 2033162.1 | 2040137.1 | 2047112.1 | 2054087.1 | 8174498.4
4 | Community Development Officer | CD | B-16 | 7 | 7 | 7 | 3805 | 295 | 6971.3225 | 585591.09 | 587656.09 | 589721.09 | 591786.09 | 2354754.36
| Sub-Total |  |  | 26 | 26 | 26 |  |  |  | 3323201.55 | 3334581.55 | 3345961.55 | 3357341.55 | 13361086.2
Support Staff
1 | Computer Assistant | IT | B-11 | 7 | 7 | 7 | 2590 | 175 | 4616.255 | 387765.42 | 388990.42 | 390215.42 | 391440.42 | 1558411.68
2 | Sub-Engineer | ET | B-16 | 3 | 3 | 3 | 3805 | 295 | 6971.3225 | 250967.61 | 251852.61 | 252737.61 | 253622.61 | 1009180.44
3 | Accountant/Senior Auditor | FAA | B-11 | 7 | 7 | 7 | 2590 | 175 | 4616.255 | 387765.42 | 388990.42 | 390215.42 | 391440.42 | 1558411.68
4 | Draftsman | ET | B-11 | 7 | 7 | 7 | 2590 | 175 | 4616.255 | 387765.42 | 388990.42 | 390215.42 | 391440.42 | 1558411.68
5 | Junior Clerk | CS | B-5 | 7 | 7 | 7 | 2100 | 100 | 3533.45 | 296809.8 | 297509.8 | 298209.8 | 298909.8 | 1191439.2
6 | Driver | OS | B-4 | 15 | 15 | 15 | 2040 | 85 | 3371.78 | 606920.4 | 608195.4 | 609470.4 | 610745.4 | 2435331.6
7 | Peon/ Attendents | OS | B-1 | 15 | 15 | 15 | 1870 | 55 | 2976.215 | 535718.7 | 536543.7 | 537368.7 | 538193.7 | 2147824.8
| Sub-Total |  |  | 61 | 61 | 61 |  |  |  | 2853712.77 | 2861072.77 | 2868432.77 | 2875792.77 | 11459011.08
Field Teams (Rural)
1 | Community Organizer (Male) | CD | B-12 | 22 | 30 | 30 | 2745 | 195 | 4940.1525 | 1304200.26 | 1784304.9 | 1790154.9 | 1796004.9 | 6674664.96
2 | Community Organizer (Female) | CD | B-12 | 22 | 30 | 30 | 2745 | 195 | 4940.1525 | 1304200.26 | 1784304.9 | 1790154.9 | 1796004.9 | 6674664.96
3 | Overseer | ET | B-11 | 36 | 50 | 50 | 2590 | 175 | 4616.255 | 1994222.16 | 2778503 | 2787253 | 2796003 | 10355981.16
| Sub-Total |  |  | 80 | 110 | 110 |  |  |  | 4602622.68 | 6347112.8 | 6367562.8 | 6388012.8 | 23705311.08
| Total Rural |  |  | 219 | 250 | 250 |  |  |  | 14585318.76 | 16535910.97 | 16586350.97 | 16636790.97 | 64344371.67
Urban Local Councils
1 | Environment Officer | ET | B-17 | 0 | 3 | 3 | 6210 | 465 | 11295.345 | 0 | 408027.42 | 409422.42 | 410817.42 | 1228267.26
2 | Computer Assistant | IT | B-11 | 1 | 2 | 2 | 2590 | 175 | 4616.255 | 55395.06 | 111140.12 | 111490.12 | 111840.12 | 389865.42
| Total Urban Local Councils |  |  | 1 | 5 | 5 |  |  |  | 55395.06 | 519167.54 | 520912.54 | 522657.54 | 1618132.68
| G.TOTAL |  | 4: 220; 5: 255; 6: 255; 13: G.Total PKR; 15: 66.14
[13 empty] | G.Total USD | 1.0175

## Table 2.2
Table 2.2: DIFFERENT ITEMS (OPRATIONAL COST)
ITEM | UNIT | OFFICES |  |  | TOTAL
| COST | STATE | DISTRICTS | LGB/ULCs | COST Rs. | Cost USD
Vehicle * |  | 7 | 11 | 3 | 17 | 0.26154
Motor Bikes | 0.08 |  | 28 |  | 2.24 | 0.034462
Survey Equipment | 0.5 |  | 6 |  | 3 | 0.046154
Computers | 0.08 | 12 | 15 | 5 | 2.56 | 0.039385
Photocopiers | 0.15 | 2 | 7 | 5 | 2.1 | 0.032308
Multimedia | 0.3 | 1 |  | 1 | 0.6 | 0.0092308
Furniture/Fix. | L/S |  |  |  | 2 | 0.030769
Rents | L/S |  |  |  | 4.8 | 0.073846
POL & O&M of Vehicles** | L/S |  |  |  | 20.54 | 0.316
O&M Equip. | L/S |  |  |  | 0.72 | 0.011077
Office Supplies | L/S |  |  |  | 4.08 | 0.062769
Utilities | L/S |  |  |  | 4 | 0.061538
Misc. | L/S |  |  |  | 0.8 | 0.012308
TADA*** |  |  |  |  | 8 | 0.12308
Total |  |  |  |  | 72.44 | 1.1145
* Type of Vehicle
Cars (3) = PKR 2900000
Jeeps Pothohar (13) = PKR 9100000
Single Cab Pickups With Hood (5) = PKR 5000000
** = Car/jeep/ Pickup on avarage Rs12,000/= per month, Motorbikes on avarage Rs 1000/= per month
***TADA= on avarage 12% of staff cost

## Table 3
Table 3: CISP: Community Development Cost
| Component/ Activity | Details of Activity |  |  |  | Total
|  | No of Person per Site/ CBO | Duration/No days | No of Sites | Unit Cost (Rs) | PK. Rs.(M) | US$(M)
B1 | Community Mobilization and Capacity Building
B.1.1 | Leadership Training | 8 | 2 | 425 | 125 | 0.85 | 0.013077
B.1.2 | CAP Training | 8 | 5 | 425 | 125 | 2.125 | 0.032692
B.1.3 | Treasure Training | 2 | 1 | 425 | 125 | 0.10625 | 0.0016346
B.1.4 | Activist Training | 5 | 2 | 425 | 125 | 0.53125 | 0.0081731
B.1.5 | Orientation to Community | 5 | 2 | 425 | 125 | 0.53125 | 0.0081731
B.1.6 | Cross Visit (in AJK) | 5 | 3 | 425 | 1400 | 8.925 | 0.13731
B.1.7 | Cross Visit (outside AJK) | 2 | 6 | 25 | 10000 | 3 | 0.046154
B.1.8 | Construction Training | 15 | 2 | 425 | 125 | 1.5938 | 0.024519
B.1.9 | Skill Development | 40 | 24 weeks | 425 | 1000 | 17 | 0.26154
B.1.10 | Community Action Plan (CAP) Monitoring | 250 | 10 |  | 700 | 1.75 | 0.026923
B.1.11 | Training of CBO's | 10 | 2 | 425 | 250 | 2.125 | 0.032692
B.1.12 | Training of Trainers | 25 | 6 |  | 1000 | 0.15 | 0.0023077
B.1.13 | Pre-feasibility Planning Phase | 100 | 4 |  | 750 | 0.3 | 0.0046154
B.1.14 | Orientation Training for Senior Staff | 16 | 2 |  | 1000 | 0.032 | 0.00049231
B.1.15 | Preparation of Pre-planning Workshop |  |  |  |  | 0.03 | 0.00046154
B.1.16 | Survey Design Construction Technologies | 80 | 40 |  | 500 | 1.6 | 0.024615
B.1.17 | Community/Private Initiative |  |  |  |  | 0.731 | 0.011246
B.1.18 | Urban CIS CD (Partner Org Payments) |  | (36 months) | 50 | 360000 | 18 | 0.27692
B.1.19 | Honorarium for Community Activist | 2 | 15 months | 425 | 750 | 9.563 | 0.14712
| Total |  |  |  |  | 68.9435 | 1.0607
B2 | Health Environment & Sanitation Awareness (HESA)
B.2.1 | HESA Training | 8 | 6 | 425 | 125 | 2.55 | 0.039231
B.2.2 | Healthy Home Training | 10 | 3 | 425 | 125 | 1.5938 | 0.024519
B.2.3 | O & M Training | 5 | 5 | 425 | 75 | 0.79688 | 0.01226
B.2.4 | Household Materials (Kits) | 10 | - | 425 | 150 | 0.6375 | 0.0098077
B.2.5 | HESA Material Kits | 8 | - | 425 | 300 | 1.02 | 0.015692
B.2.6 | Entry Community Activities |  |  | 425 | 30000 | 12.75 | 0.19615
B.2.7 | Resource Persons Payment | 40 | 15 |  | 500 | 0.3 | 0.0046154
| Total |  |  |  |  | 19.6481 | 0.30228
B3 | Support to Women and Children
B.3.1 | Functional/Economic Education | 40 | 6 months | 425 | 1075 | 18.275 | 0.28115
B.3.2 | Develop Micro Credit Linkages | 20 | - | 425 | 160 | 1.36 | 0.020923
B.3.3 | Women & Children Initiatives | 40 | 24 months | 425 | 1000 | 17 | 0.26154
[5 empty] | Total | 36.635 | 0.56362
| Total: |  |  |  |  | 125.2266 | 1.9266
|  | Total Cost Summary of Community Development Showing Contingencies |  |  |  |  | PKR in Million
|  | Items | Total | Year 1 | Year 2 | Year 3 | Year 4
|  | Base Cost | 125.23 | 18.78 | 37.57 | 37.57 | 31.31
|  | Price Contingency* | 13.4316 | 0 | 2.4421 | 4.8841 | 6.1055
|  | Total | 138.6616 | 18.78 | 40.0121 | 42.4541 | 37.4154
* @ Y1=0, Y2=6.5%, Y3=13% and Y4=19.5%
Annual implementation plans of this component will be approved by the Steering Committee.

## Table 4
Table 4
Table 4: - INFRASTRUCTURE UPGRADING AND SERVICES
|  |  | Total Cost |  | 2002 |  | 2003 |  | 2004 |  | 2005
|  |  | PKR(M) | USD(M) | PKR(M) | USD(M) | PKR(M) | USD(M) | PKR(M) | USD(M) | PKR(M) | USD(M)
INFRASTRUCTURE UPGRADING AND SERVICES
1 | Water Supply | 953.79 | 808.95 | 12.4454 | 121.3425 | 1.8668 | 242.685 | 3.7336 | 242.685 | 3.7336 | 202.2375 | 3.1113
| Physical Contingency 5%. |  | 40.4475 | 0.62227 | 6.0671 | 0.09334 | 12.1342 | 0.18668 | 12.1342 | 0.18668 | 10.1119 | 0.15557
| Price Contingency * |  | 86.7599 | 1.3348 | 0 | 0 | 15.7745 | 0.24269 | 31.5491 | 0.48537 | 39.4363 | 0.60671
| Total |  | 936.1574 | 14.4024 | 127.4096 | 1.9601 | 270.5938 | 4.163 | 286.3683 | 4.4057 | 251.7857 | 3.8736
2 | Community Latrine | 26.325 | 18.954 | 0.2916 | 2.8431 | 0.04374 | 5.6862 | 0.08748 | 5.6862 | 0.08748 | 4.7385 | 0.0729
| Physical Contingency 5%. |  | 0.9477 | 0.01458 | 0.14216 | 0.002187 | 0.28431 | 0.004374 | 0.28431 | 0.004374 | 0.23692 | 0.003645
| Price Contingency * |  | 2.0328 | 0.031274 | 0 | 0 | 0.3696 | 0.0056862 | 0.73921 | 0.011372 | 0.92401 | 0.014216
| Total |  | 21.9345 | 0.33745 | 2.9853 | 0.045927 | 6.3401 | 0.09754 | 6.7097 | 0.10323 | 5.8994 | 0.09076
3 | Stormwater Drainage | 140.4 | 101.088 | 1.5552 | 15.1632 | 0.23328 | 30.3264 | 0.46656 | 30.3264 | 0.46656 | 25.272 | 0.3888
| Physical Contingency 5%. |  | 5.0544 | 0.07776 | 0.75816 | 0.011664 | 1.5163 | 0.023328 | 1.5163 | 0.023328 | 1.2636 | 0.01944
| Price Contingency * |  | 10.8417 | 0.1668 | 0 | 0 | 1.9712 | 0.030326 | 3.9424 | 0.060653 | 4.928 | 0.075816
| Total |  | 116.9841 | 1.7998 | 15.9214 | 0.24494 | 33.8139 | 0.52021 | 35.7852 | 0.55054 | 31.4636 | 0.48406
4 | Internal Pathways | 148.75 | 107.1 | 1.6477 | 16.065 | 0.24715 | 32.13 | 0.49431 | 32.13 | 0.49431 | 26.775 | 0.41192
| Physical Contingency 5%. |  | 5.355 | 0.082385 | 0.80325 | 0.012358 | 1.6065 | 0.024715 | 1.6065 | 0.024715 | 1.3388 | 0.020596
| Price Contingency * |  | 11.4865 | 0.17672 | 0 | 0 | 2.0884 | 0.03213 | 4.1769 | 0.06426 | 5.2211 | 0.080325
| Total |  | 123.9415 | 1.9068 | 16.8682 | 0.25951 | 35.825 | 0.55115 | 37.9134 | 0.58328 | 33.3349 | 0.51284
5 | Foot Bridges | 140.4 | 101.088 | 1.5552 | 15.1632 | 0.23328 | 30.3264 | 0.46656 | 30.3264 | 0.46656 | 25.272 | 0.3888
| Physical Contingency 5%. |  | 5.0544 | 0.07776 | 0.75816 | 0.011664 | 1.5163 | 0.023328 | 1.5163 | 0.023328 | 1.2636 | 0.01944
| Price Contingency * |  | 10.8417 | 0.1668 | 0 | 0 | 1.9712 | 0.030326 | 3.9424 | 0.060653 | 4.928 | 0.075816
| Total |  | 116.9841 | 1.7998 | 15.9214 | 0.24494 | 33.8139 | 0.52021 | 35.7852 | 0.55054 | 31.4636 | 0.48406
6 | Street Pavement | 70.2 | 50.544 | 0.7776 | 7.5816 | 0.11664 | 15.1632 | 0.23328 | 15.1632 | 0.23328 | 12.636 | 0.1944
| Physical Contingency 5%. |  | 2.5272 | 0.03888 | 0.37908 | 0.005832 | 0.75816 | 0.011664 | 0.75816 | 0.011664 | 0.6318 | 0.00972
| Price Contingency * |  | 5.4208 | 0.083398 | 0 | 0 | 0.98561 | 0.015163 | 1.9712 | 0.030326 | 2.464 | 0.037908
| Total |  | 58.492 | 0.89988 | 7.9607 | 0.12247 | 16.907 | 0.26011 | 17.8926 | 0.27527 | 15.7318 | 0.24203
7 | Street Lighting | 5.265 | 3.7908 | 0.05832 | 0.56862 | 0.008748 | 1.1372 | 0.017496 | 1.1372 | 0.017496 | 0.9477 | 0.01458
| Physical Contingency 5%. |  | 0.18954 | 0.002916 | 0.028431 | 0.0004374 | 0.056862 | 0.0008748 | 0.056862 | 0.0008748 | 0.047385 | 0.000729
| Price Contingency * |  | 0.40656 | 0.0062548 | 0 | 0 | 0.073921 | 0.0011372 | 0.14784 | 0.0022745 | 0.1848 | 0.0028431
| Total |  | 4.3869 | 0.067491 | 0.59705 | 0.0091854 | 1.268 | 0.019508 | 1.3419 | 0.020645 | 1.1799 | 0.018152
8 | Solid Waste Management | 10.53 | 7.5816 | 0.11664 | 1.1372 | 0.017496 | 2.2745 | 0.034992 | 2.2745 | 0.034992 | 1.8954 | 0.02916
| Physical Contingency 5%. |  | 0.37908 | 0.005832 | 0.056862 | 0.0008748 | 0.11372 | 0.0017496 | 0.11372 | 0.0017496 | 0.09477 | 0.001458
| Price Contingency * |  | 0.81313 | 0.01251 | 0 | 0 | 0.14784 | 0.0022745 | 0.29568 | 0.004549 | 0.3696 | 0.0056862
| Total |  | 8.7738 | 0.13498 | 1.1941 | 0.018371 | 2.536 | 0.039016 | 2.6839 | 0.041291 | 2.3598 | 0.036304
9 | Tagging/ Numbering Streets | 1.755 | 1.2636 | 0.01944 | 0.18954 | 0.002916 | 0.37908 | 0.005832 | 0.37908 | 0.005832 | 0.3159 | 0.00486
| Physical Contingency 5%. |  | 0.06318 | 0.000972 | 0.009477 | 0.0001458 | 0.018954 | 0.0002916 | 0.018954 | 0.0002916 | 0.015795 | 0.000243
| Price Contingency * |  | 0.13552 | 0.0020849 | 0 | 0 | 0.02464 | 0.00037908 | 0.04928 | 0.00075816 | 0.061601 | 0.0009477
| Total |  | 1.4623 | 0.022497 | 0.19902 | 0.0030618 | 0.42267 | 0.0065027 | 0.44731 | 0.0068818 | 0.3933 | 0.0060507
10 | Trunk Infrastructure | 165.75 | 32 | 0.49231 | 4.8 | 0.073846 | 9.6 | 0.14769 | 9.6 | 0.14769 | 8 | 0.12308
| Physical Contingency 5%. |  | 1.6 | 0.024615 | 0.24 | 0.0036923 | 0.48 | 0.0073846 | 0.48 | 0.0073846 | 0.4 | 0.0061538
| Price Contingency * |  | 3.432 | 0.0528 | 0 | 0 | 0.624 | 0.0096 | 1.248 | 0.0192 | 1.56 | 0.024
| Total |  | 37.032 | 0.56972 | 5.04 | 0.077538 | 10.704 | 0.16468 | 11.328 | 0.17428 | 9.96 | 0.15323
| Grand Total: | 1662.98 | 1426.1486 | 21.9407 | 194.0967 | 2.9861 | 412.2244 | 6.3419 | 436.2554 | 6.7116 | 383.572 | 5.9011
Summary A)
| Government ADP |  | 1199.7472 | 18.4576 | 163.2838 | 2.5121 | 346.7837 | 5.3351 | 366.9998 | 5.6462 | 322.6799 | 4.9643
| Community Share ** |  | 226.4014 | 3.4831 | 30.8129 | 0.47404 | 65.4407 | 1.0068 | 69.2556 | 1.0655 | 60.8921 | 0.9368
| Total |  | 1426.1486 | 21.9407 | 194.0967 | 2.9861 | 412.2244 | 6.3419 | 436.2554 | 6.7116 | 383.572 | 5.9011
Summary B)
| Base Cost |  | 1232.36 | 18.9594 | 184.854 | 2.8439 | 369.708 | 5.6878 | 369.708 | 5.6878 | 308.09 | 4.7398
| Physical Contingency 5%. |  | 61.618 | 0.94797 | 9.2427 | 0.1422 | 18.4854 | 0.28439 | 18.4854 | 0.28439 | 15.4045 | 0.23699
| Price Contingency * |  | 132.1706 | 2.0334 | 0 | 0 | 24.031 | 0.36971 | 48.062 | 0.73942 | 60.0776 | 0.92427
| Total |  | 1426.1486 | 21.9407 | 194.0967 | 2.9861 | 412.2244 | 6.3419 | 436.2554 | 6.7116 | 383.572 | 5.9011
* Price Contingency @ Y1=0,Y2=6.5,Y3=13,Y4=19.5%
** 20% inclusive except item nos. 2, 8 and 10

## Table 4.1 & 4.2
Table 4.1 | [12 empty] | Table 18.0.0 - Backup
GOVERNMENT OF AZAD JAMMU & KASHMIR
COMMUNITY DISTRICT INFRASTRUCTURE SERVICES PROJECT
PROPOSED PHYSICAL INFRASTRUCTURE | [12 empty] | PROPOSED PHYSICAL INFRASTRUCTURE
SUMMARY OF WORKS DISTRIBUTION | [12 empty] | FINANCES DISTRIBUTION IN DISTRICTS
|  | Water | Community | Stormwater | Access |  | Street | Street | Solid | Tagging / | Trunk |  |  |  | SUB-COMPONENT: WATER SUPPLY SCHEMES
|  | Supply | Latrines | Drainage | Internal | Foot | Pavement | Lighting | Waste | Numbering | Infrastructure /
No. | District | Schemes |  |  | Pathways | Bridges |  |  | Management | Streets | Micro Hydel St. |  | S. |  | Spring-based |  | Ground Water-based
|  | No. | No. | (Linear Meter) | (Kilometers) | (Linear Meter) | (Linear Meter) | (No. of Poles) | No. of Bin/Depot | Job |  |  | No. | District | Gravity | Pumping | Tubewell | Open Well | Hand Pump | Total
1 | Muzaffarabad | 378.5275 | 217.956 | 61457.4324 | 85.68 | 1132.1856 | 16924.7025 | 152.3134 | 122 | 1 | 1 |  | 1 | Muzaffarabad | 180.5576 | 20.062 | 0 | 0 | 0 | 200.6196 | 200.6196
2 | Bagh | 203.7356 | 109.478 | 33702.4629 | 42.84 | 566.0928 | 9281.2884 | 75.4382 | 65 | 0 | 1 |  | 2 | Bagh | 99.0155 | 11.0017 | 0 | 0 | 0 | 110.0172 | 110.0172
3 | Poonch | 174.4298 | 85.447 | 34198.0874 | 33.66 | 444.7872 | 9417.778 | 59.6321 | 55 | 0 | 1 |  | 3 | Poonch | 100.4716 | 11.1635 | 0 | 0 | 0 | 111.6351 | 111.6351
4 | Sudhnoti | 187.0697 | 47.062 | 18338.1048 | 18.36 | 242.6112 | 5050.1128 | 32.3307 | 35 | 0 | 1 |  | 4 | Sudhnoti | 47.8898 | 11.9725 | 0 | 0 | 0 | 59.8623 | 59.8623
5 | Kotli | 208.7966 | 179.571 | 47332.1354 | 70.38 | 930.0096 | 13034.7507 | 124.2935 | 108 | 0 | 1 |  | 5 | Kotli | 123.6076 | 30.9019 | 0 | 0 | 0 | 154.5094 | 154.5094
6 | Mirpur | 44.8967 | 54.739 | 27507.1572 | 21.42 | 283.0464 | 7575.1692 | 37.3599 | 66 | 0 | 1 |  | 6 | Mirpur | 26.938 | 8.9793 | 8.9793 | 26.938 | 17.9587 | 89.7935 | 89.7935
7 | Bhimber | 75.0117 | 85.447 | 25276.8472 | 33.66 | 444.7872 | 6960.9663 | 59.6321 | 44 | 0 | 1 |  | 7 | Bhimber | 24.7539 | 8.2513 | 8.2513 | 24.7539 | 16.5026 | 82.5129 | 82.5129
Total: |  | 1272.4676 | 779.7 | 247812.2273 | 306 | 4043.52 | 68244.768 | 541 | 495 | 1 | 7 |  |  | Total | 603.234 | 102.3322 | 17.2306 | 51.6919 | 34.4613 | 808.95 | 808.95
Table 4.2
PROPOSED PHYSICAL INFRASTRUCTURE
SUMMARY OF DISTRICT WISE COST DISTRIBUTION
|  | Water | Community | Stormwater | Access |  | Street | Street | Solid | Tagging / | Trunk
|  | Supply | Latrines | Drainage | Internal | Foot | Pavement | Lighting | Waste | Numbering | Infrastructure / | Total
No. | District | Schemes |  |  | Pathways | Bridges |  |  | Management | Streets | Micro Hydel St.
|  | Rs | Rs | Rs | Rs | Rs | Rs | Rs | Rs | Rs | Rs
1 | Muzaffarabad | 200.6196 | 5.1991 | 25.0698 | 26.5608 | 25.0698 | 12.5349 | 0.94012 | 1.8802 | 1.2636 | 7.936 | 307.074 | 24.8%
2 | Bagh | 110.0172 | 2.7496 | 13.748 | 14.5656 | 13.748 | 6.874 | 0.51555 | 1.0311 | 0 | 4.352 | 167.6009 | 13.6%
3 | Poonch | 111.6351 | 1.9889 | 13.9501 | 14.7798 | 13.9501 | 6.9751 | 0.52313 | 1.0463 | 0 | 4.416 | 169.2646 | 13.8%
4 | Sudhnoti | 59.8623 | 1.2212 | 7.4805 | 7.9254 | 7.4805 | 3.7403 | 0.28052 | 0.56104 | 0 | 2.368 | 90.9198 | 7.4%
5 | Kotli | 154.5094 | 4.4314 | 19.3078 | 20.4561 | 19.3078 | 9.6539 | 0.72404 | 1.4481 | 0 | 6.112 | 235.9506 | 19.1%
6 | Mirpur | 89.7935 | 1.3748 | 11.2208 | 11.8881 | 11.2208 | 5.6104 | 0.42078 | 0.84156 | 0 | 3.552 | 135.9226 | 11.1%
7 | Bhimber | 82.5129 | 1.9889 | 10.311 | 10.9242 | 10.311 | 5.1555 | 0.38666 | 0.77332 | 0 | 3.264 | 125.6275 | 10.2%
Total Cost (Rs. mil.): |  | 808.95 | 18.954 | 101.088 | 107.1 | 101.088 | 50.544 | 3.7908 | 7.5816 | 1.2636 | 32 | 1232.36
|  | 232 | 0.53 | 437.7358
|  | 127 | 0.54 | 235.1852
|  | 129 | 0.64 | 201.5625
|  | 69 | 0.32 | 215.625
|  | 179 | 0.74 | 241.8919
|  | 104 | 2 | 52
|  | 95 | 1.1 | 86.3636

## Table 4.3
Table 4.3
PROPOSED PHYSICAL INFRASTRUCTURE
TARGET POPULATION FOR WATER SUPPLY SCHEMES
S. |  | PC-I Provision | Avg. Cost | Avg. No. | Target
No. | District | Base Cost | of 1 Scheme | of Schemes | Population (m)
1 | Muzaffarabad | 200.6196 | 0.53 | 378.5275 | 0.13375
2 | Bagh | 110.0172 | 0.54 | 203.7356 | 0.073345
3 | Poonch | 111.6351 | 0.64 | 174.4298 | 0.074423
4 | Sudhnoti | 59.8623 | 0.32 | 187.0697 | 0.039908
5 | Kotli | 154.5094 | 0.74 | 208.7966 | 0.10301
6 | Mirpur | 89.7935 | 2 | 44.8967 | 0.059862
7 | Bhimber | 82.5129 | 1.1 | 75.0117 | 0.055009
| Total | 808.95 |  | 1272.4676 | 0.5393

## Table 4.4 & 4.5
Table 4.4
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: COMMUNITY LATRINES (Peri-Urban)
|  | Population | No. of | Av. Cost / | Total
No. | District | to be served | Schemes | Scheme | Cost
|  |  | No. | Rs. (mil.) | Rs. (mil.)
1 | Muzaffarabad | 6200 | 3 | 0.3 | 0.9
2 | Bagh | 3400 | 2 | 0.3 | 0.6
3 | Poonch | 3450 | 1 | 0.3 | 0.3
4 | Sudhnoti | 1850 | 1 | 0.3 | 0.3
5 | Kotli | 4775 | 3 | 0.3 | 0.9
6 | Mirpur | 2775 | 1 | 0.3 | 0.3
7 | Bhimber | 2550 | 1 | 0.3 | 0.3
| Total | 25000 | 12 | 0.3 | 3.6
Notes
Detaile is provided in Att.4.4
Table 4.5
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: COMMUNITY LATRINES (Rural)
|  | Population | No. of | Av. Cost / | Total
No. | District | to be | Schemes | Scheme | Cost
|  | benefitted | No. | Rs. (mil.) | Rs. (mil.)
1 | Muzaffarabad | 12400 | 214.956 | 0.02 | 4.2991
2 | Bagh | 6800 | 107.478 | 0.02 | 2.1496
3 | Poonch | 6900 | 84.447 | 0.02 | 1.6889
4 | Sudhnoti | 3700 | 46.062 | 0.02 | 0.92124
5 | Kotli | 9550 | 176.571 | 0.02 | 3.5314
6 | Mirpur | 5550 | 53.739 | 0.02 | 1.0748
7 | Bhimber | 5100 | 84.447 | 0.02 | 1.6889
| Total | 50000 | 767.7 | 0.02 | 15.354
Notes
In Rural areas, the community latrine can be for Schools, Mosques, BHUs. The exisiting design used for schools is proposed to be used.
The Unit Cost for Community Latrine (one latrine house with appropriate disposal system) in the Rural area is based on IDA RWSS completed work. The cost of land is not included in the estimate.

## Table 4.6
Table 4.6
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STORMWATER DRAINAGE
|  |  | Type of Area |  | Total
S. |  | Terrain: | Hilly | Flat/Rolling | Hilly/Flat/Rolling
No. | District | Section: | Type A | Type B | Type A+B
|  |  | (Linear Meter) | (Linear Meter) | (Linear Meter)
1 | Muzaffarabad |  | 32306.4742 | 29150.9581 | 61457.4324
2 | Bagh |  | 17716.4536 | 15986.0093 | 33702.4629
3 | Poonch |  | 17976.9897 | 16221.0977 | 34198.0874
4 | Sudhnoti |  | 9639.8351 | 8698.2698 | 18338.1048
5 | Kotli |  | 24881.1959 | 22450.9395 | 47332.1354
6 | Mirpur |  | 14459.7526 | 13047.4047 | 27507.1572
7 | Bhimber |  | 13287.3402 | 11989.507 | 25276.8472
| Total |  | 130268.0412 | 117544.186 | 247812.2273
| Average Cost/Linear Meter (Rs.) |  | 388 | 430
| Total Cost (Rs.) |  | 50544000 | 50544000 | 101.088
Notes
Length of drains proposed is in proportion to the population breakup.
The design of each site alongwith cost will be prepared prior to its implementation for the approval of competent authority
Approximately 100 houses (population 700 persons) with a cost of one million rupees will be benefitted.

## Table 4.7
Table 4.7
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: ACCESS - INTERNAL PATHWAYS
S. |  | Rural | Total
No. | District | (Kilometers) | (Kilometers)
1 | Muzaffarabad | 85.68 | 85.68
2 | Bagh | 42.84 | 42.84
3 | Poonch | 33.66 | 33.66
4 | Sudhnoti | 18.36 | 18.36
5 | Kotli | 70.38 | 70.38
6 | Mirpur | 21.42 | 21.42
7 | Bhimber | 33.66 | 33.66
| Total | 306 | 306
| Average Cost/Kilometer (Rs.) | 0.35
| Total Cost (Rs. mil.) | 107.1 | 107.1
Notes
Length of pathways proposed in a district is in proportion to the population breakup.
For Typical Cross Section of Pathway, see Att.4.7
Unit Costs based on the Composite Schedule of Rates 1998, with average 12% premium.
Upgradation/construction work will be confined to stone/brick soling.

## Table 4.8
Table 4.8
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: ACCESS - FOOT BRIDGES
S. |  | Rural | Total
No. | District | (Linear Meter) | (Linear Meter)
1 | Muzaffarabad | 1132.1856 | 1132.1856
2 | Bagh | 566.0928 | 566.0928
3 | Poonch | 444.7872 | 444.7872
4 | Sudhnoti | 242.6112 | 242.6112
5 | Kotli | 930.0096 | 930.0096
6 | Mirpur | 283.0464 | 283.0464
7 | Bhimber | 444.7872 | 444.7872
| Total | 4043.52 | 4043.52
| Average Cost/Linear Meter (Rs.) | 25000
| Total Cost (Rs. mil.) | 101.088 | 101.088
Notes
Length of Foot Bridges proposed in a district is in proportion to the population breakup.
Typical Design is given in the Att.4.8
Average length of Foot Bridge is assumed to be 61.0 m (200 ft).
Unit Cost assumed for Suspension Foot Bridge is based on market rates.
Location and type of bridge (foot or jeepable) would be decided on the basis of
technical viability and population size to be served.

## Table 4.9
Table 4.9
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STREET PAVEMENT (SIDE WALKS/FOOTPATHS, WALKWAYS & STREETS)
| Districts | Side Walks/ | Walkways | Street Pavement
S. |  | Footpaths |  |  | Total
No. |  | Type A+B | Type A+B | Type A+B
|  | (Linear Meter) | (Linear Meter) | (Linear Meter) | (Linear Meter)
1 | Muzaffarabad | 7568.2488 | 5071.0137 | 4285.44 | 16924.7025
2 | Bagh | 4150.33 | 2780.8785 | 2350.08 | 9281.2884
3 | Poonch | 4211.3642 | 2821.7738 | 2384.64 | 9417.778
4 | Sudhnoti | 2258.2678 | 1513.1251 | 1278.72 | 5050.1128
5 | Kotli | 5828.7722 | 3905.4985 | 3300.48 | 13034.7507
6 | Mirpur | 3387.4017 | 2269.6876 | 1918.08 | 7575.1692
7 | Bhimber | 3112.7475 | 2085.6589 | 1762.56 | 6960.9663
| Total | 30517.1321 | 20447.6359 | 17280 | 68244.768
| Average Cost/Linear Meter (Rs.) | 530 | 791 | 1053 | 50544000
| Estimated Cost (PKR ) | 16174080 | 16174080 | 18195840 | 50544000
| Estimated Cost (PKR in million)) | 16.1741 | 16.1741 | 18.1958 | 50.544
Notes
Detail is given in Att.4.9

## Table 4.10
Table 4.10
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STREET LIGHTING
Low Income/
S. | District | Peri-Urban
No. |  | (No. of Units)
1 | Muzaffarabad | 152.3134
2 | Bagh | 75.4382
3 | Poonch | 59.6321
4 | Sudhnoti | 32.3307
5 | Kotli | 124.2935
6 | Mirpur | 37.3599
7 | Bhimber | 59.6321
| Total | 541
| Average Cost/Pole (Rs.) | 7000
| Total Cost (Rs. mil.) | 3.7908
Notes
This sub-component to be implemented as a pilot to assess the impact before further
expansion to all beneficiaries/communities. Target Population for street lighting is 20,000.
One street light proposed to be provided for every 48 persons or 6 households.
Unit Cost of Street Light includes the provision of Mild Steel Pole, light bulb, foundations, cable,
control box, etc. and is estimated at market rates. Besides pole mounted, the street light will
also be wall mounted or fixed on existing poles.

## Table 4.11
Table 4.11
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: SOLID WASTE MANAGEMENT
|  |  | Low Income/Peri-Urban |  |  |  | Table 4.11
S. |  | Target Peri Urban | Waste Collection Bin | Waste Collection Depot | Tools, Implements and Materials*
No. | District | Population | (Masonary) | (RCC) |  | Total
|  |  | (No.) | (No.) | (Rs)
1 | Muzaffarabad | 13041 | 110 | 12 |  |  | PROPOSED PHYSICAL INFRASTRUCTURE
2 | Bagh | 6520.5 | 60 | 5 |  |  | SUB-COMPONENT: COMMUNITY LATRINES (Peri-Urban)
3 | Poonch | 5123.25 | 50 | 5
4 | Sudhnoti | 2794.5 | 30 | 5 |  |  |  |  | Population |  |  |  |  | Average Pop. | No. of | Av. Cost / | Total | Total
5 | Kotli | 10712.25 | 100 | 8 |  |  | No. | District | at 2000 | Peri-Urban |  | Target for Peri-Urban |  | size | Schemes | Scheme | Cost | Cost
6 | Mirpur | 3260.25 | 60 | 6 | [5 empty] | % | No. | % | No. | >1000 | No. | Rs. (mil.) | Rs. (mil.) | USD (mil.)
7 | Bhimber | 5123.25 | 40 | 4 |  |  | 1 | Muzaffarabad | 655543 | 20% | 131108.6 | 10% | 13110.86 | 3300 | 4 | 0.3 | 1.2 | 0.018462
| Total | 46575 | 450 | 45 | 0.6066 |  | 2 | Bagh | 386548 | 20% | 77309.6 | 10% | 7730.96 | 3300 | 2 | 0.3 | 0.6 | 0.0092308
| Average Cost/No. (Rs.) |  | 10500 | 50000 | Variable |  | 3 | Poonch | 363067 | 20% | 72613.4 | 10% | 7261.34 | 3300 | 2 | 0.3 | 0.6 | 0.0092308
| Total Cost (Rs. mil.) |  | 4.725 | 2.25 | 0.6066 | 7.5816 | 4 | Sudhnoti | 205921 | 20% | 41184.2 | 10% | 4118.42 | 3300 | 1 | 0.3 | 0.3 | 0.0046154
[7 empty] | 6 | Mirpur | 217941 | 80% | 174352.8 | 5% | 8717.64 | 3300 | 4 | 0.3 | 1.2 | 0.018462
Notes
Waste Collection Bin (Masonary) 7*5 feet
Waste Collection Depot (RCC) 10*9 feet
* Wheel barrows, masks, gloves, shovels etc.
[7 empty] | 7 | Bhimber | 295107 | 80% | 236085.6 | 5% | 11804.28 | 3300 | 4 | 0.3 | 1.2 | 0.018462
[8 empty] | Total | 2124127 |  | 732654.2 |  | 52743.5 |  | 17 |  | 5.1 | 0.078462

## Table 4.12
Table 4.12
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: TAGGING/NUMBERING STREETS & HOUSES
As this is a totally new initiative therefore it is proposed to do a Pilot Project in the Muzaffarabad District in the Low Income/Peri-Urban area.
Low Income/
S. | District | Peri-Urban | Total
No. |  | (Job)
1 | Muzaffarabad | 1 | 1
| Total | 1 | 1
| Lumpsum for Job | 1.2636 | 1.2636
| Total Cost (Rs. mil.) | 1.2636 | 1.2636

## Table 4.13
Table 4.13
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: TRUNK INFRASTRUCTURE
Low Income/
S. | District | Peri-Urban | Total
No. |  | (Job)
1 | Muzaffarabad | 1 | 1
2 | Bagh | 1 | 1
3 | Poonch | 1 | 1
4 | Sudhnoti | 1 | 1
5 | Kotli | 1 | 1
6 | Mirpur | 1 | 1
7 | Bhimber | 1 | 1
| Total | 7 | 7
| Lumpsum for Jobs | 32 | 32
| Total Cost (Rs. mil.) | 32 | 32
Note:
A) | Major share of the sub-component will be allowcated for provision of water supply
and drainage infrastructure.
B) | Construction of micro-hydel station will also be undertaken as pilot project
collaboration with Hydro Electric Board.

## Att.4.4
Attachment of Table 4.4
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: SANITATION - LATRINES
A. | For Community Latrines in the Rural areas (schools, mosques, BHUs), follow the existing Design.
B. | Public Latrine (Urban)
Total Covered area = 324 sft
Size of each toilet is 5ft x 3 ft.
Entrance passage is 3 ft wide.
Separate entrance for men and women.
Estimated cost @ Rs. 900 /sft: 291,600/- (Say Rs.0.3 million)
Construction of an urban public latrine consists following:
i) | Stone/Brick masonry in foundation/walls
ii) | RCC (1:2:4) roofing.
iii) | Glazed tiles on internal walls.
iv) | Joinery Work (Steel)
v) | P/F of Ist Class Sanitary appliances
vi) | P/F of Electrification.
vii) | P/F of Water Tank (Fiber Glass/Polyethelyne).
viii) | Constt. Of Septic Tank.
18'-0"
18'-0"
Not to Scale
Men
Women
Typical Layout

## Att. T4.7
Attachment of Table 4.7
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: ACCESS - INTERNAL PATHWAYS(upgradation)
Item Rate Analysis per Km length of Rural Road. Quantities based on historical data
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Pick Work | 1000 Cft. | 9561.5 | 706.65 | 6756.634
2 | Jamper Work | 1000 Cft. | 8011.75 | 1379.4 | 11051.408
3 | Blasting Work | 1000 Cft. | 6524 | 1834.75 | 11969.909
4 | Earth Filling | 1000 Cft. | 7103 | 653.4 | 4641.1002
5 | R.R Retaining Walls/Breast Walls | 100 Cft. | 7600.4 | 1227.65 | 93306.3106
6 | Wire Crates | 100 Sft. | 868 | 895 | 7768.6
7 | Cross Drainage | Nos. | 3 | 25000 | 75000
8 | Stone Soling 6" th. With sand fill | 100 Cft | 19680 | 850 | 167280
9 | Side berms | 100Sft | 6560 | 100 | 6560
10 | Stone pitching 3"Th. on berm and drain | 100 Cft. | 10037 | 4 | 40148
|  |  | Total: |  | 424481.9617
|  |  | Deduction 13% on Item No.5 |  | -12129.8204
|  |  | Total: |  | 412352.1413
**** | Contractors' profit |  | Deduct 15% **** |  | -61852.8212
|  |  | Total: |  | 350499.3201
|  |  | Say |  | 350000
Notes / Assumptions

## Att.T4.6-A
Attachment of Table 4.6
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STORMWATER DRAINAGE
Item Rate Analysis
Drain Type: A (for Hilly terrain)
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 0.3078 | 31.65 | 9.7419
2 | P.C.C (1:4:8) in bed | M3 | 0.0285 | 1063.75 | 30.3169
3 | P.C.C (1:2:4) | M3 | 0.1775 | 2069.4 | 367.3185
|  |  | Total: |  | 407.3772
S.R = | Schedule Rates 1998 |  | Add 12% above on item 1,2,3 |  | 48.8853
M.R = | Market Rates |  | Total: |  | 456.2625
|  |  | Deduct 15% Contractor Profit |  | -68.4394
|  |  | Total: |  | 387.8231
|  |  | Say |  | 387.8231
Note: | The design for Storm Water Drain of each site alongwith cost will be prepared prior to its
| implementation for approval of competent authority. |  |  |  |  | Typical Cross Section
150 mm
150 mm
400 mm
150 mm
380 mm
75 mm PCC 1:4:8
PCC 1:2:4
(Not to Scale)
Type A
Varies 300 - 375 mm
150 mm

## Att.T4.6-B
Attachment of Table 4.6
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STORMWATER DRAINAGE
Item Rate Analysis
Drain Type: B (for Flat terrain)
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 0.3078 | 31.65 | 10
2 | P.C.C (1:4:8) in bed | M3 | 0.0285 | 1063.75 | 30
3 | P.C.C (1:2:4) | M3 | 0.1775 | 2069.4 | 367
4 | Cement Plaster 12mm (1:3) | M2 | 1.032 | 43.45 | 45
|  |  | Total: |  | 452
S.R = | Schedule Rates 1998 |  | Add 12% above on item 1,2,3,4 |  | 54.24
M.R = | Market Rates |  | Total: |  | 506.24
|  |  | Deduct 15% Contractor Profit |  | -75.936
|  |  | Total: |  | 430.304
|  |  | Say |  | 430.304 | Typical Cross Section
Note: | The design for Storm Water Drain of each site alongwith cost will be prepared prior to its
implementation for approval of competent authority.
150 mm
150 mm
400 mm
380 mm
12 mm Pl
Varies 300 - 375 mm
150 mm
75 mm PCC 1:4:8
150 mm
PCC 1:3:6
(Not to Scale)
Type B

## Att.Ta4.9-A&B
Attachment of Table 4.9
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: SIDE WALK (Footpath)
Type A (for hilly terrain)
Item Rate Analysis per meter length. Quantities based on Schedule of Rates 1998 & Market Rates
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 0.3915 | 31.65 | 12
2 | P.C.C (1:4:8) in bed | M3 | 0.122 | 1063.75 | 130
3 | Sand bedding | M3 | 0.061 | 450 | 27
4 | Dressed stone in 1:3 Sand Cement Mortar | M2 | 1.22 | 290 | 354
5 | P/L Kerb Stone P.C.C (1:2:4) on both side in 1:3 Cement Sand Martor | M3 | 0.075 | 2069.4 | 155
|  |  | Total: |  | 678
S.R = | Schedule Rates 1998 |  | Add 12% above on item 1,2,5 |  | 35.64
M.R = | Market Rates |  | Total: |  | 713.64
|  |  | Deduct 15% Contractor Profit |  | -107.046
|  |  | Total: |  | 606.594
|  |  | Say |  | 606.594
Type B (for hilly terrain)
Item Rate Analysis per meter length. Quantities based on Schedule of Rates 1998 & Market Rates
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 0.3915 | 31.65 | 12
2 | P.C.C (1:4:8) in bed | M3 | 0.122 | 1063.75 | 130
3 | Sand bedding | M3 | 0.061 | 450 | 27
4 | Brick (1:3) Cement Sand Mortar | M3 | 0.0756 | 1303 | 99
5 | P/L Kerb Stone P.C.C (1:2:4) | M3 | 0.075 | 2069.4 | 155
|  |  | Total: |  | 423
S.R = | Schedule Rates 1998 |  | Add 12% above on item 1,2,5 |  | 35.64
|  |  | Add 75% above on item 4 |  | 74.25
M.R = | Market Rates |  | Total: |  | 532.89
|  |  | Deduct 15% Contractor Profit |  | -79.9335
|  |  | Total: |  | 452.9565
|  |  | Say |  | 452.9565
50 mm Sand Bed
100 mm Dressed Stone
100 mm PCC 1:4:8
1.22 m
100 mm
375 mm
Compacted Sub-Grade
50 mm Sand Bed
100 mm Dressed Stone
100 mm PCC 1:4:8
1.22 m
100 mm
375 mm
Compacted Sub-Grade

## Att.T4.9-A&B
Attachment of Table 4.9
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: WALKWAY
Item Rate Analysis
Rural Area
Type: A (for Hilly terrain)
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 0.5899 | 31.65 | 19
2 | P.C.C (1:4:8) in bed | M3 | 0.214 | 1063.75 | 228
3 | Sand bedding | M3 | 0.107 | 450 | 48
4 | PCC (1:2:4) | M2 | 2.135 | 198.77 | 424
5 | P/L Kerb Stone P.C.C (1:2:4) | M3 | 0.112 | 2069.4 | 232
|  |  | Total: |  | 951
S.R = | Schedule Rates 1998 |  | Add 12% above on item 1,2,4,5 |  | 108.36
M.R = | Market Rates |  | Total: |  | 1059.36
|  |  | Deduct 15% Contractor Profit |  | -158.904
|  |  | Total: |  | 900.456
Typical Cross Section of Walkway |  |  | Say |  | 900.456
Item Rate Analysis
Rural Area
Type: B (for Flat/Rolling terrain)
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 0.572 | 31.65 | 18
2 | P.C.C (1:4:8) in bed | M3 | 0.214 | 1063.75 | 228
3 | Sand bedding | M3 | 0.107 | 450 | 48
4 | Brick Soling (1:3) Cement Sand Mortar | M3 | 0.1324 | 1303 | 172.5172
5 | P/L Kerb Stone P.C.C (1:2:4) | M3 | 0.076 | 2069.4 | 157
|  |  | Total: |  | 623.5172
S.R = | Schedule Rates 1998 |  | Add 12% above on item 1,2,5 |  | 48.36
|  |  | Add 75% above on item 4 |  | 129.3879
M.R = | Market Rates |  | Total: |  | 801.2651
|  |  | Deduct 15% Contractor Profit |  | -120.1898
|  |  | Total: |  | 681.0753
Typical Cross Section of Walkway |  |  | Say |  | 681.0753
50 mm Sand Bed
100 mm PCC 1:2:4
100 mm PCC 1:4:8
Varies 1.83 - 2.44; Av. 2.135 m
150 mm
375 mm
Compacted Sub-Grade
50 mm Sand Bed
Brick on Edge
100 mm PCC 1:4:8
100 mm
375 mm
Varies 1.83 - 2.44; Av. 2.135 m
Compacted Sub-Grade

## Att.T4.9b-A&B
Attachment of Table 4.9
PROPOSED PHYSICAL INFRASTRUCTURE
SUB-COMPONENT: STREET PAVEMENT
Item Rate Analysis
Rural Area
Type: A
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 1 | 31.65 | 32
2 | P.C.C (1:4:8) in bed | M3 | 0.4 | 1063.75 | 426
3 | PCC (1:2:4) laid in Panels | M2 | 4 | 198.77 | 795
|  |  | Total: |  | 1253
S.R = | Schedule Rates 1998 |  | Add 12% above on item 2,3 |  | 146.52
M.R = | Market Rates |  | Total: |  | 1399.52
|  |  | Deduct 15% Contractor Profit |  | -211
|  |  | Total: |  | 1188.52
Typical Cross Section of Street Pavement |  |  | Say |  | 1188.52
Type: B
S.No. | Item Description | Unit | Qty. | Rate/Unit (Rs.) | Amount (Rs.)
1 | Earth Work Excavation | M3 | 1 | 31.65 | 32
2 | P.C.C (1:4:8) in bed | M3 | 0.4 | 1063.75 | 426
3 | Brick Soling (1:3) Cement Sand Mortar | M3 | 0.248 | 1303 | 323.144
|  |  | Total: |  | 781.144
S.R = | Schedule Rates 1998 |  | Add 12% above on item 1,2 |  | 54.96
|  |  | Add 75% above on item 3 |  | 243
M.R = | Market Rates |  | Total: |  | 1079.104
|  |  | Deduct 15% Contractor Profit |  | -161.8656
|  |  | Total: |  | 917.2384
Typical Cross Section of Street Pavement |  |  | Say |  | 917.2384
50 mm Sand Bed
100 mm PCC 1:2:4
100 mm PCC 1:4:8
Varies 1.83 - 2.44; Av. 2.135 m
150 mm
375 mm
Compacted Sub-Grade
50 mm Sand Bed
Brick on Edge
100 mm PCC 1:4:8
100 mm
375 mm
Varies 1.83 - 2.44; Av. 2.135 m
Compacted Sub-Grade