## Sheet1
Annex 'F'
Procurement Packaging for Goods and Works for 1st year
Sub Sector | Description of Procurement | Procurement Category Goods/Works | Implementation Agency |  |  | Estimated Total Value |  | Total Estimated Number of Contract Packages |  | Estimated Cost per Contract |  | Remarks
|  |  |  | Community Contracting | Community Share | Entire Project | Year 1 | Entire Project | Year 1 | Minimum | Maximum
1) Vehicle and Equipment | Purchase of vehicles, computers, survey equipment, etc | Goods | LGRDD | 0 | 0 | 74.86 | 51.49 | 7 | 5 | 3.75 | 28.5 | O&M will be taken through 2 contracts in the 1st year
1)Water Supply | a) Supply of Pipes and fittings | Goods | LGRDD | 0 | 0 | 630.2205 | 94.5331 | 56 | 14 | 2.836 | 13.2346 | Based on the assumption of annual rounds of 7 district wise contract packages. After first year this arrangement will be reviewed re-establish whether it is feasible to allow each community to procure the pipes directly
| b) Supply of pumps and motors | Goods | LGRDD | 0 | 0 | 33.1695 | 4.9754 | 56 | 21 | 0.099508 | 0.46437 | Same as above
| c) Installation of pipes and construction of Water Tanks, etc | Works | LGRDD | 228.501 | 184.275 | 228.501 | 34.2751 | 438 | 65.7 | 1.0283 | 4.7985 | i) construction will be done by communities; ii) 15% of schemes for 2 tanks in each schemes
| d) Construction of Tubewells | Works | LGRDD | 29.484 | 0 | 29.484 | 4.4226 | 43.8 | 6.57 | 0.6 | 1 | i) construction will be done by the communities; ii) 20% of 15% of total schemes are T/W schemes
2) Community Latrines | Construction of latrine | Works | LGRDD | 26.325 | 0 | 26.325 | 3.9487 | 1107.405 | 166.1107 | 0.02 | 0.3 | i) construction will be done by the communities; ii) Rural and urban latrine cost 0.02million and 0.3million respectively
3) Stormwater Drainage | Construction of drains | Works | LGRDD | 140.4 | 28.08 | 140.4 | 21.06 | 160 | 24 | 0.07 | 0.7 | construction will be done by the communities | 20% in rural; 80% in urban; .1km to 1km max
4) Access, Internal Pathways | Upgradation of rural roads/pathways | Works | LGRDD | 175.5 | 35.1 | 175.5 | 26.325 | 501 | 75 | 0.28 | 1.4 | construction will be done by the communities | max 5km in a CIP site
5) Access, Foot Bridges | Construction of foot bridges | Works | LGRDD | 98.28 | 28.08 | 140.4 | 21.06 | 125 | 19 | 0.9 | 11.5 | i)construction will be done by the communities for small bridges; ii) big bridges by the government | 25% site; min 45 m for pedestrian; max 175m for jeapable
6) Street Pavements | Construction of street pavements | Works | LGRDD | 70.2 | 14.04 | 70.2 | 10.53 | 160 | 24 | 0.7 | 1.49 | construction will be done by the communities | 20% rural; 80% urban; min .1km; max 1km
7) Street Lighting | Installation electric poles and conductors | Works | LGRDD | 5.265 | 1.053 | 5.265 | 0.78975 | 75 | 11 | 0.01 | 0.5 | construction will be done by the communities | min 8 poles; max 50 poles
8) Solid Waste Management | Construction of collection bins, filth depots | Works | LGRDD | 10.53 | 2.106 | 10.53 | 1.5795 | 43 | 6 | 0.04 | 0.12 | construction will be done by the communities | 14 collection bins with one filth depot; min1; max 3
9) Tagging/ Numbering Streets | Marking and installation of street signage | Works | LGRDD | 1.755 | 0.351 | 1.755 | 0 | 1 | 0 | 1.4 | 1.4 | construction will be done by the communities | 1 job only in one urban area
10) Trunk Infrastructure/ Hydel Power | Construction of truk infrastructure and hydel/solar power pilots | Works | LGRDD | 41.4375 | 0 | 165.75 | 0 | 100 | 15 | 0.3 | 3
|  |  | Sub-Total | 827.6775 | 293.085 | 1732.36 | 274.9893
|  |  | % Community Contracting | 47.78% |  | 1657.5

## Sheet2
Annex 'F'
Procurement Plan for 1st Year
Steps for Goods and Works | Purchase of vehicles | Purchase of computers and Photocopiers, Multimedia | Purchase of survey equipment | Purchase of Motorcycles | Pipe procurement through 1 bid for 7 packages district wise lots | Pipe procurement through 1 bid for 7 packages district wise lots | Pumps and motors procurement through 1 bid for 7 packages district wise lots | Pumps and motors procurement through 1 bid for 7 packages district wise lots | Pumps and motors procurement through 1 bid for 7 packages district wise lots | Construction of Water Tanks through 66 contracts | Construction of Tubewells through 7 contracts | Constuction of Community latrines through 166 contracts | Construction of drains through 24 contracts | Upgradation of rural roads/pathways through 75 contracts | Construction of foot bridges through 19 contracts | Construction of street pavements through 24 contracts | Installation electric poles and conductors through 11 contracts | Construction of collection bins, filth depots through 6 contracts | Marking and installation of street signage | Construction of truk infrastructure and hydel/solar power pilots through 15 contracts
Averge Contract cost ( Million Rs) | 28.5 | 11.75 | 9 | 2.24 | 47.2665 | 47.2665 | 1.6585 | 1.6585 | 1.6585 | 0.51932 | 0.6318 | 0.023788 | 0.8775 | 0.351 | 1.1084 | 0.43875 | 0.071795 | 0.26325
Contract Type | ICB | NCB/ Local Shopping | NCB/ Local Shopping | NCB | NCB | NCB | Local Shopping | Local Shopping | Local Shopping | Community Contracting | Community Contracting | Community Contracting | Community Contracting | Community Contracting | NCB/Community Contracting | Community Contracting | Community Contracting | Community Contracting | Community Contracting | Local Shopping
Total Cost in 1st year (Million Rs) | 28.5 | 11.75 | 9 | 2.24 | 47.2665 | 47.2665 | 1.6585 | 1.6585 | 1.6585 | 34.2751 | 4.4226 | 3.9487 | 21.06 | 26.325 | 21.06 | 10.53 | 0.78975 | 1.5795 | 0 | 0 | 274.9893
Preparation of Bidding Document/ (Specification in case of Shopping) | 2002-07-01 | 2002-07-01 | 2002-07-01 | 2002-07-01 | 2002-03-01 | 2002-09-01 | 2002-07-01 | 2002-11-01 | 2003-03-01 | [5 empty] | 2002-07-01
Bank's Clearance of Bidding Documents (for prior review cases) | 2002-08-20 | 2002-08-20 | 2002-08-20 | 2002-08-20 | 2002-04-20 | 2002-09-20 | [8 empty] | 2002-08-20
Advertisement of IFB | 2002-09-10 | 2002-09-10 | 2002-09-10 | 2002-09-10 | 2002-05-10 | 2002-10-10 | 2002-07-15 | 2002-11-15 | 2003-03-15 | [5 empty] | 2002-09-10
Bid Submission/ Opening Date | 2002-10-10 | 2002-10-10 | 2002-10-10 | 2002-10-10 | 2002-06-10 | 2002-11-10 | 2002-07-30 | 2002-11-30 | 2003-03-30 | [5 empty] | 2002-10-10
Completion of Evaluation and Recommendations | 2002-10-20 | 2002-10-20 | 2002-10-20 | 2002-10-20 | 2002-06-20 | 2002-11-20 | 2002-08-20 | 2002-12-20 | 2003-04-20 | [5 empty] | 2002-10-20
Bank's Clearance of evaluation and Recommendation (For prior review cases only) | 2002-11-10 | 2002-11-10 | 2002-11-10 | 2002-11-10 | 2002-07-10 | 2002-12-10 | [8 empty] | 2002-11-10
Award of Contract | 2002-11-30 | 2002-11-30 | 2002-11-30 | 2002-11-30 | 2002-07-30 | 2002-12-30 | 2002-08-30 | 2002-12-30 | 2003-04-30 | 2002-07-01 | 2002-07-01 | 2002-07-01 | 2002-07-01 | 2002-07-01 | 30-Nov-02/ 1-Jul-02 | 2002-07-01 | 2002-07-01 | 2002-07-01
Copy of Signed Contract Sent to Bank (for prior review cases) | 2002-12-10 | 2002-12-10 | 2002-12-10 | 2002-12-10 | 2002-08-10 | 2003-01-10 |  |  |  | 2002-07-10 | 2002-07-10 | 2002-07-10 | 2002-07-10 | 2002-07-10 | 10-Dec-02/ 10-Jul-02 | 2002-07-10 | 2002-07-10 | 2002-07-10
Completion of Contract | 2003-03-10 | 2003-01-30 | 2003-01-30 | 2003-01-30 | 2002-10-10 | 2003-04-10 | 2002-12-30 | 2003-04-30 | 2003-08-30 | 2004-07-10 | 2004-07-10 | 2004-07-10 | 2004-07-10 | 2004-07-10 | 10-Dec-04/ 10-Jul-04 | 2004-07-10 | 2004-07-10 | 2004-07-10