Annex ‘C’

Brief Description on sub-components

This program operation will comprise three complementary components in support of low-income communities: (a) decentralized planning and implementation assistance; (b) community development; and (c) basic infrastructure and services.   The project would cost 2294.26 million Pakistan Rupee (PKR) [United States Dollar (USD) 35.30 million equivalent] over five years.  Donors (IDA others) would finance between 75-80  % of the program operation, the balance to be met by communities, local/municipal/town councils/governments and GoAJK.  Each component is described as follows:

1.	DECENTRALIZED PLANNING AND IMPLEMENTATION: component would develop the capacity of state, district/tehsil/local governments, communities and NGO/CBOs for: (i) Program development on community driven development (CDD) approaches and techniques, promotion and awareness campaigns, and capacity building; (ii) Design and implementation of infrastructure projects, including technical criteria and guidance, engineering drawings and specifications and community contracting procedures;  (iii) Institutional strengthening through improved procedures for project implementation, Operational Manual detailed guidelines, and special studies and (iv) establishing a  monitoring and evaluation system including process monitoring and capacity/training activities; and (v) operational activities including activities to support the program management and coordination and implementation agencies,  recurrent and operating costs .  The component will finance technical services, capacity building activities, vehicles and equipment, incremental staff and program operations costs; and (vi) under this component, two baseline survey jobs will be undertaken.  First job will be completed during the inception period of the program while second job will be completed before the close of the program.

- CISP through the district offices and municipal/town councils will have the service delivery arrangements and responsibilities with the communities.  Contracted individuals and or other service providers (SPs) will support the communities.  These SPs consist of NGOs,   Community   Based  Organizations (CBOs), private firms, and institutions which have sufficient capacity to help in capacity building  and other support activities. The management/implementing authorities on the basis of transparent qualifications criteria would select them.  Since the proposed program is demand-led and community based, communities   themselves will be responsible for playing the major role in each of the three project phases   (Pre-planning, Planning and Implementation).  As many communities lack organizational and technical skills to complete schemes on their own. The district/municipal/town offices and other SPs will assist them. The   role of these SPs will be to assist CISP by facilitating a decision-making and planning  process  at   the community level, and to provide technical support to ensure quality of construction.  These SPs will also be used to build overall capacities, provide training, some monitoring, auditing as well as other specialized services and expertise.  These SPs may also consist of apex/resource  NGOs  and  firms,  training  organizations,  and  other   private, professional associations or entities with the requisite qualifications.

- Rural communities, with CISP support, will implement single schemes directly.  In the case of peri-urban schemes, which may require other arrangements, a 8-12 month study and pilot activities  will be conducted during the first year to finalize the  most  appropriate  method  of  implementation  for the CI schemes in the urban areas.

- This program component  includes funding for the following activities:

  - Program development on CDD approaches, Comunications, Promotional Campaigns .  This include  user-friendly participatory tools and community action-planning kits, and audiovisual programs would be produced and distributed for use by CISP .  This will include the use of filmstrip and slide projectors designed for community use. A program information package will be designed, produced and distributed to staff/NGOs, communities, and local government officials.  This will include a  description of the project cycle, criteria and procedures for working with the  CISP

  - Design and implementation assistance, survey.  including technical criteria and guidance, engineering drawings and specifications and community contracting procedures;  Impact, Site Appraisals and Water Quality  Testing   It includes  the  cost of impact evaluation in 5-10% of the project communities, pre-planning site appraisals conducted  either by CISP or a support organization for each community and the cost of purchasing  water  quality  testing  kits.    Water quality testing will be carried out by LGRDD with technical support from EPA and other line departments as needed

  - Institutional Strengthening and Monitoring & Evaluation:.  This include; (i) strengthening activities at the state wide level on the policy development and operational manual; and (ii) Monitoring and Evaluation.  This  includes; (i)  operationalizing the MIS and the monitoring and evaluation program at the state, district/ULC and  a community level; and (ii)  staff capacity and training programs for personnel of District/Municipal Council and other partners including support organizations to ensure that they can effectively carry out their terms of reference as catalysts of communities in completing the development cycle  in community schemes.  Some specific studies, M&E and capacity building training are also under consideration which may be taken up during implementation of the CISP.

iv.	Program Implementation Support and Operations

- administrative and overhead costs, staff compensation, LGRDD and the municipal/town offices and vehicles O&M rental and traveling  allowances.  Compensation includes salaries and benefits for the staff and local  consultants, and other SPs  for the CISP  and seven District Offices.  At the District /Municipal/town level, higher level staff/consultants and support staff are supported.

- equipment and vehicle. This includes the purchase of vehicles,  furniture and fixtures for various CISP offices.  It also includes computers equipment consisting of one terminal for each professional staff, and  requisite  software  and  multimedia equipment.

- implementation support. Approximately 36 person  months   of  senior advisors is provided over a 1-2 year period, to help support the overall management  processes of the program, and in particular, to strengthen the community development component of the project.  Given the skill balance of the team, the advisors should be  specialists in working with the private and voluntary sector, and have strong skills in  community development and participatory methods.  Also, .…… person months (either local or  international) of short term consultancies will include, but not be limited to community infrastructure,  water and sanitation engineering, economic analysis, media/communications, social marketing, and participatory development and monitoring and evaluation.

- audit. : This includes funding for the cost of an audit to be carried  out by government auditors, the cost of an audit to be carried out by a private auditor as well     as the cost of a financial audit of the planning phase and the cost of a financial and  technical  audit of schemes once completed.

- This will include an initial 3 weeks intensive field based immersion with a SPs, (training institutions, NGOs, etc) in participatory methods for community infrastructure,  water  supply and sanitation.  This training should be undertaken before launching  activities with district and municipal staff and  social organizers.  Subsequent staff training at regional and international sites   will include cross visits to other community-based projects in  other countries.  Specific skill training in computers, project  management, design of environmental components, participatory methods, and  gender sensitivity will be included

2.	COMMUNITY DEVELOPMENT: This would include (i)mobilization/organization and capacity building  through development of community action plans  (iii) health, and environmental sanitation awareness (HESA) , and (d) Support to Women and Children ((SWC) for women and children in the areas of  community education  (functional/economic literacy), and special learning activities designed to increase their participation, skills and management training and linkages to economic and micro-credit opportunities. The latter component will link communities to existing government, private, banking and non-government organizations for establishing partnerships on income generating activities and access to small scale credit (e.g., Pakistan Poverty Alleviation Fund, Micro-credit Bank etc.,).  The project will finance capacity building activities, and services provided by other Service Providers ( local NGOs , and private groups) , training and related equipments. The main thrust of  community development activities is to encourage users, particularly women, to participate in decision making to increase ownership for long term scheme sustainability.  This component consist of funding for three activities:

- Mobilization and  Capacity Building Activities include awareness raising and organization. These include a series of small workshops, group discussions, information campaigns and participatory community action planning (CAP) training to enable users to organize and elect a representative and responsive Community Based Organization and/or  User Group/Committee. Efforts would be made to have at least 30% representation of women in the CBO/user group. Non Formal Education (NFE) will be integrated with the CAP process and will focus on functional literacy, decision making and problem solving.

- Planning and Preparation phases.  The focus is on group building, self investigation,  problem solving and discussing options for water supplies and environmental sanitation  and other community infrastructure leading to the  formulation  of  a  CAP  as  a  proposal  for  implementation   phase financing.  The role of the District/Municipal/Town offices and their SPs  is to build  capacity  and  facilitate  the  active  participation  of women, confirm demand and willingness to contribute to project costs, and take    responsibility for operation and maintenance.  During these two phases 15% of the beneficiary  population would be trained in participatory CAP and monitoring in addition to training  targeted to women/ table 1).  Gender issues will be  incorporated in all project interventions. The CBO generally consists of 7-12 members, hence at least 30% CBO members will be trained per community

## Table 1: Training Provided to Community Leaders/ Members

| ### Planning Phase | Implementation Phase |
| --- | --- |
| Participatory CAP & monitoring (10days) | CBO workshop (3 days) |
| CBO members (7 days) | CBO treasurer training. (2 days) |
| Nonformal education (NFE) (24 weeks) | CBO training during construction. (3 days) |
| Health, Hygiene and Sanitation Activities (HHSA) training (7 days) | HHSA training to school teachers, community health promoter and community leaders. (8 days) |
| Cross visits to neighboring CI , RWSS projects. (3 days) | Mother & child health training to tap stand/women's groups. (7 days) |
| Nursery establishment & catchment protection training. (3 days) | Community maintenance worker on the job training. |
|  | Latrine construction workshop. (2 weeks) Support to Women and Children (SWC) workshop. @3 days) |
|  | Refresher training to CBO, members, treasurer, Community Mobilization and organization Workers/staff, (total of 15 days) |

SP  inputs per community will vary depending on scheme size and complexity but the mix of skills required will be the same for all.  Project support will include the salaries of (i) a   Community Facilitator (CF) with a high school certificate/diploma and experience in community  development work and hygiene and sanitation issues; and (ii) a Community Development Supervisor (CDS)    with at least a graduate degree in social sciences and minimum 2 years experience in  community development and/or community water supply and sanitation, other basic infrastructure.   SP staff inputs on average include 12 months for each community.

iii.	Implementation Phase.  In this phase responsibility for community organization and strengthening is shared equally by the Water and Sanitation Committee (WSC)  and SP staff.  In order to enable the WSC to carry out its functions effectively training at  the community level focus on those skills needed to implement and manage schemes for long term scheme sustainability; effective use of improved water supplies through HESA; and training  to enable women to take advantage of time savings.

Training to CBO members will focus on the roles and responsibilities, community monitoring and procurement issues.  At least one community treasurer/community   will receive training on simple book/record keeping to enable the CBO to maintain its book   of accounts. Health Environmental Sanitation Awareness (HESA) activities will be targeted to traditional birth attendants, community elders , school teachers, students  with special emphasis on beneficiary women, and their young children.  The program provides funds for   training at least 3 primary school teachers/community, at least 2 women from each   tap stand/women's group or 2 women from each hamlet/settlements. HESA training and small workshops will center on personal and domestic hygiene and environmental sanitation, latrine  options and drainage.  District staff and their partners will assist community education participants and/or tap stand groups to establish linkages with other organizations for income generation activities, explore options and identify skill enhancement training.

iv. Health Environmental Sanitation Awareness ( HESA) .  The second activity will focus in improving personal and  domestic hygiene and environmental sanitation.  Activities would  be  conducted  in  informal  settings and by using real life situations and experiences.  Women would be the focal point  for HESA, and activities would be conducted through tap stand  and/or  women's  groups.  Women would be involved in monitoring and evaluation by measuring changes in hygiene practices such as water use and management, and tap stand hygiene.  For HESA activities at least 2       women from each tap stand /women's group will be trained.  The number of sessions/training    activity and intensity will vary from community to community and will depend on scheme size and need.

v.  Support to Women and Children (SWC) Activities- .  The third  activity provides support to help (i) women  develop skills required to realize the benefits of improved  community infrastructure particularly water supplies; (ii) improve access  to the formal credit system-, (iii) promote women's role in planning and implementing community infrastructure and water  supply and sanitation schemes including environmental management initiatives; and (iv) encourage participation in resource mobilization activities such as collection of user  charges, and monitoring and evaluation.  Project support would be in the form of training. This component will focus its activities on community education (functional/economic literacy) and tap stand/women's groups.

- INFRASTRUCTURE UPGRADING AND SERVICES:  This component involves investment for  infrastructure upgrading and services, with priorities to be established in consultation with the communities through their CBOs.   A menu of infrastructure to be provided would typically include: water supply and sanitation schemes; storm-water drainage, flood protection,  footpaths, streets lighting, solid waste collection and disposal, and community facilities.  Other types of infrastructure such as  access footbridge  could be considered if identified as community priority; and trunk infrastructure required to ensure that basic infrastructure function efficiently would also be included.  While it is not possible to determine what kinds of sub- project schemes will be selected in advance, based on the RWSS, and NWFP-CIP  experience the social assessment of priorities in AJK, it is likely that rural water supply, and local/neighborhood access, will be major priorities with substantial attention also given to public health and sanitation, and community development programs.   Particular attention will be given to the interconnection between the delivery and timing of water supply and health and sanitation components.   The project will finance capacity building, technical services, training, civil works and related equipment.

The major component of the program is rural water supply and sanitation and the upgrading of basic infrastructure in approximately 575 rural and peri-urban communities.  This would be implemented in three phases/batches.  Detailed designs will be prepared for Phase I communities which would be largely rural water supply and sanitation.  Additional communities will be identified for Phase/batch  2 of the program which include peri-urban communities and limited funding will also be included for additional communities in Phase/batch 3.

This component would be demand driven, with the infrastructure to be provided according to the priorities of the respective communities.  The fundamental concept of the program is to foster a sense of ownership of the infrastructure on the part of the communities. Communities’ ability to choose among different initiatives and encourage them to contribute financially to the investments they choose, and to take greater responsibility for the operation and maintenance of the completed programs.  Appropriate functional standards for planning, design, and construction would be developed taking cognizance of locally available materials, ease of construction and maintenance, and affordability.  Affordability and a balanced provision of infrastructure will be important objectives in the design process, although the program allows communities to choose from a range of alternative standards within cost ceilings. Another important objective of the process is to improve operation and maintenance (O&M), and communities would be required to agree to satisfactory O&M arrangements prior to selecting any specific infrastructure scheme.

The final composition of the program would only be known after each community has prepared its CAP and has been reviewed and modified to conform with technical, financial and other agreed criteria. This process, following the establishment of CBOs and their participation in the planning and design process carried out by the CISP staff  and other staff of the LGRDD and Local Councils/Governments, and its SPs/consultants, will be completed up to detailed engineering design for each Phase/batch of communities.

## i.	Selection of Priorities

Past experience suggests that following are generally the top community priorities, although further demand surveys will be conducted.

(a) water supply;

(b) drainage;

(c) access; and

(d) solid waste disposal

The order of priority may differ from community to community and, in a few cases, other priorities such as flood protection works might take precedence. Sanitation facilities and practices in the communities are generally considerably poor, and yet demand for sanitation facilities (e.g. latrines) has rarely featured in the lists of community priorities in the past. This may imply that the survey processes may have been too limited resulting in a narrow range of community infrastructure demands. Thereby efforts will be made to improve participatory demand techniques.

During the implementation of Phase/batch 1 and in designing subsequent program phases/batches, community liaison and preparation activities will emphasize the possibility of other infrastructure elements being included, and also fully explain the advantages and opportunities the program offers to improve health and sanitation.

Possible further choices of infrastructure facilities, subject to prior community agreement to satisfactory O&M arrangements, could include: provision of community facilities such as community halls, flood protection, foot bridges, basic access.

Primary education and primary health facilities are available through a number of other programs, and the first consideration would be to seek such facilities from these alternative sources (principally due to the need to provide for continuing, relatively high, recurrent costs, and to coordinate with AJK-wide sector and development policies and plans).

ii.	Water Supply

Water in rural areas is supplied by various means including spring boxes, rain water ponds, stand posts, hand-pumps, wells and through individual or shared house connections. In larger communities and urban or peri-urban areas tube-wells and reservoirs, constructed and operated by PHED, serve the distribution systems. In some cases water is supplied direct from rivers through gravity systems. In urban areas where a piped supply system exists the distribution systems are often surface laid, routed along and across drainage channels and often submerged in polluted water. These pipes are prone to damage and with intermittent supply systems, low pressures and faulty equipment, contamination of the water supply is a risk. Rehabilitation of distribution systems as well as augmentation, generally to serve house connections, will thus be a major sub-component of the program which will also improve necessary trunk facilities such as tube-well and pump restoration/replacement where critical.

iii.	Sanitation Promotion and Community Latrines (public toilets)

Although sanitation tends not to be an initial community priority, surveys and meetings with women's community organizations have shown in the past that the sector requires urgent intervention. A sanitation component has therefore been included in the program. The major thrust of the program will be a two stage process of:  (a) generating much greater community awareness of sanitation and health linkages, and to improve sanitation practices. The experience of the RWSSP in AJK and other areas will be drawn upon, particularly in the education and training field. and (b) the physical elements of the sanitation program to be established under the program will have two main parts:  promotion through demonstration of public latrines (incuding if applicable on a pilot basis, pre-treatment ponds in urban or peri-urban communities where sewerage systems exist).  The demonstration latrines will generally be consistent with the RWSSP experience -  to encourage  householders to install appropriate toilet facilities. The success of the sub-component will be dependent on the effectiveness of the health awareness and sanitation education.

  - Storm Water Drainage

The storm-water drains invariably act as sewage carriers, conveying their contents either to main watercourses, to open areas or to fields. Based on community demands, comprehensive open channel storm water drainage systems will be constructed as trapezoidal or rectangular channels  in either bricks/stones or concrete.  System designs have allowed for the fact that sludge will continue to be discharged to the drains for the foreseeable future.

v.	Access, Internal Pathways, Signage and Street Lighting

In rural areas, access is provided through a network of narrow, generally unpaved paths, little more than a car's width across, sometimes flanked on one or both sides by open ditches. The main access roads to urban settlements are more integrated with the town's road network and generally paved, although often lacking maintenance. The network of roads and footpaths within urban settlements are similar to those in rural areas although carrying significantly more traffic. Improvements within the program  are limited to paving of existing streets and footpaths. Appropriate functional planning, design and construction standards are to be used. The materials proposed in road and footpath construction generally reflect locally used construction material, such as bricks and stones. Concrete is used in steep slope locations and where storm water flows are significant. Asphalt or double surface dressing will only be used for access roads and wider streets.

vi.	Solid Waste Management

Brick or stone-built containers (collection points) primarily intended to reduce the spread of refuse by wind and animals will be constructed, and coverage will be designed to appropriate and consistent planning standards. Purchase of land for collection points sites is not likely to be necessary since communities generally agree to provide sites (approximately 4 sq.m. each). However, where such an arrangement might not be forthcoming, land may be purchased. Allowances for land acquisition in the program costs are sufficient to cover this exceptionally. Local transportation (hand or animal drawn carts) needs in urban areas will also be provided as necessary.

vii.	Trunk Infrastructure and Community Facilities

Trunk infrastructure will include off-site infrastructure and that infrastructure serving the community at large. It would include, for example:

(a) tubewells, bulk water transmission, storage and distribution;

(b) basic rural access, foot bridges etc. flood protection.

This sub-component would also support Community Facilities which include rehabilitation of existing facilities  mainly to support women/children and community group activities (eg., functional/economic literacy, group/individual skill learning,  primary health care)

Consistent with most of the public infrastructure supply in Pakistan, communities would not necessarily contribute directly to trunk infrastructure costs. These would be financed through general government revenues. Trunk infrastructure required to allow secondary and tertiary infrastructure to function would need to be in place prior to implementing program-financed secondary/tertiary investments. The program includes a component for such infrastructure, which is subject to an assessment of technical and economic feasibility if costs exceed a threshold amount. Subject to this requirement, once a community has determined a service to be a priority, the development of any required trunk infrastructure could commence directly, and be undertaken in parallel with community mobilization, development and resource mobilization activities.

viii.	Water Quality Testing and Time Savings study US$0.080 million

- Water Quality Testing.  It includes the cost of impact evaluation in 5-10% of the project communities, pre-planning site appraisals conducted either by CISP or a Support organization for each community and the cost of purchasing water quality testing kits.  Water quality testing will be carried out by LGRDD with technical support from EPA and other line departments (PHED), as needed : A study will be undertaken to review the current water quality monitoring mechanisms in the rural  water supply schemes and recommend mechanism for pilot implementation which should promote private sector capacity in water quality testing and identify  practical  approaches to necessary corrective actions by the communities.

- Time Saving Study: A short study will be carried out to assess whether significant numbers of water supply schemes are likely to meet the initial viability criteria set  up for the Project;

ix.   Technical Training, Capacity Building.  This includes:

- Design and implementation assistance, survey.  including technical criteria and guidance, engineering drawings and specifications and community contracting procedures; continuing research on  low Cost Options and Local Environmental Management:  To expand and improve on technical options in all construction activities.  Review surface water conservation and ground water recharge techniques currently followed in AJK, other provinces and in  other countries and recommend feasible technical solutions and delivery systems for implementation in the project communities.  Studies  will also be undertaken to determine how to achieve the greatest sanitation coverage in a community;

- Impact, Site Appraisals training in the following basic courses/modules:

	The preparation of pre feasibility studies during a 3 day workshop and planning phase proposal preparation during a 4 day workshop.  Both workshops are  taking place during the pre-planning phase-,  Participatory Community Action Planning (CAP) and monitoring during 10 day workshop during the Planning Phase.

	Survey, design, and costs (15  days workshop), construction technologies (15  days workshop), during the planning phase and construction monitoring (8 days workshop) during the implementation phase,

	Monitoring and Evaluation methods and tools.  This training is taking placeduring the planning phase and consists of a 5 days workshop (for  District/Municipal Staff and SOsSpecialized training as needed for both the planning phase and implementation phase),

	District/Municipal based workshops, state and  annual review meeting,

	Training of trainers for Women Development Initiatives :  5-10 days during the implementation phase, and Training for community development supervisors in health education, women's development (10 days) during the planning phase,

	CISP / District/Municipal level  Training and Communications . In addition to the above training, costs associated with Training Materials Production.

	CISP Staff training: This will include an initial 3 weeks intensive field-based immersion with an SP in participatory methods for community infrastructure in particular water supply and sanitation.  This training should be undertaken before launching activities with District/ Municipalities and SOs.  Subsequent staff training at state, province and international sites will include cross visits to other community-based projects in Sri Lanka,  Nepal, India, Philippines, Thailand and other similar programs.  Specific skill training in computers, project  management, design of environmental components, participatory methods, and gender sensitivity will be included.

# x.	Planning, Design and Construction Standards

1.	In developing the standards the emphasis has been on the need to provide effective infrastructure which is affordable and easily constructed and subsequently operated and maintained by the communities.  For rural water supply and sanitation the CISP will follow the standards and service levels for the recently completed IDA-RWSS project.  For peri-urban and urban areas the standards and service levels developed for NWFP-CIP will generally be followed. The standards and service levels for various infrastructure are as follows:

A.	Water supply

- Water will be drawn from springs, natural streams, canals, shallow and deep aquifers.  Overhead reservoirs will be provided on the basis of technical justification and demand from the communities.  The minimum terminal pressure head will be 8 meters for rural and 10 meters for urban network.

3.	Water supply standards will be:

(a) 	Minimum supply from public standposts or community tanks for rural settlements

Design consumption:			25 liters per capita per day

Maximum walking distance:	100 meters

Storage (if required):		Max 35% of average daily consumption

Design peak factor:			1.0

(b) 	Improved supply from public standposts or community tanks for rural/urban settlements

Design consumption:			45 liters per capita per day

Maximum walking distance:		100 meters

Storage (if required):			Max 35% of average daily consumption

Design peak factor:			1.0

(c)	Intermediate level service through yard connections (15 mm dia pipe from street distributor main) for peri-urban settlements

Design consumption:			60 liters per capita per day

Storage (if required):			Max 35% of average daily consumption

Design peak factor:			1.5

(d)	Full house connection (15 mm dia pipe from street distributor main) for peri-urban settlements

Design consumption:			90 liters per capita per day

Storage (if required):			Max 35% of average daily consumption

Design peak factor:			1.5

4.   In hilly terrain galvanized iron or HDPE pipes will be used.  However, in flat terrain pipes of different materials may also be considered.  Pipes should be buried as far as possible between a depth of 0.5 and 1.0 meter.  In snow fall areas the pipes should be buried below the freezing level.

B.	Community/ Public Latrines

5.	Latrines constructed in the rural and urban areas would have pucca superstructure.  The wastewater from these latrines will be disposed in accordance with the environmental guidelines.  Separate apartments for male and female would be provided, wherever required.  Number of WCs, Urinals and Wash Basins would be determined based on the field conditions.

C.	Stormwater Drainage

6.	The minimum requirement is for adequate drainage for access roads, minor streets and foot paths.  In general, drains will be provided in the center of footpaths, and on one side or on both side of roads depending on need and space availability.  As far as possible open drains would be provided.  Local materials would be preferred as construction material.

7.	Design capacity for all channels will take into account a sullage volume equivalent to 80% of the amount of the potable water supplied and, in addition, for tertiary drains, local rain fall run-off.  For larger areas the capacity of the primary and secondary drains will be calculated from the catchment area and rainfall intensity.  Run-off will generally be calculated using a maximum storm intensity of 50 mm/hour (smaller areas) representing one year return period, plus an allowance of sullage (dry weather flow).

8.	Drainage channels will consist of either concrete, semi circular or “V” shaped channels or rectangular channels of plastered brick or stone masonry on a concrete base.  Where such channels are liable to carry sullage water including significant volumes of raw sewage, sulphate resistant cement shall be used in the construction.  Where possible, drainage gradients will be such as to ensure a self cleansing velocity of 0.6 meter per second at peak flow.  Connections from houses will be via small concrete surface channels or 75mm or 100mm pipes.

9.	The provision of flood protection works to divert stormwater away from or around a community, or, where neither solution is practical, to channel and control flood flows through a community, may be included where considered a community priority.  Designs will be prepared on a case-by-case basis and are expected to involve stone masonry and concrete work.

D.	Internal Pathways/roads

10.	The planned service level for rural roads is to provide all weather access to 100% of population in the target settlement.  Only rehabilitation and improvement of existing tracks and katcha roads will be undertaken.  Asphalt roads and new tracks or roads will not be constructed.

E.	Foot Bridges

11.	Three type of bridges have been considered, suspension, trusses and concrete.  These bridges will be designed for the pedestrian and light vehicular traffic.  These bridges will be provided both for rural and peri-urban settlements.

F.	Street Pavement and Sidewalks/ Footpath

12.	Dressed stone or bricks and concrete pavements would be provided.  The selection of these materials would be as per local conditions.  These pavements will be provided along with the drainage system.  Sidewalks will be provided along the roads/ streets and for those settlements that are located on hilly terrain.

G.	Street Light

13.	The provision of street lighting will only be considered in urban areas.  However, in rural communities, community preference for street lighting, based on a perceived priority for reasons of security, may be considered.

14.	Lighting will be pole-mounted, wall-mounted or mounted on existing power lines at strategic points and will not be necessarily give full coverage.  Lamps will be fluorescent bulbed.  Cabling between lights will be via ducts set in concrete or overhead.

H.	Solid Waste Management

15.	Improved solid waste management will be achieved by improved operation and maintenance through community-based arrangements.  Investment in facilities will likely be small and limited to : (a) construction of waste collection bins of about 0.2 cubic meters capacity; (b) construction of open, brick/ stone/ block built, collection containers of approximately 5 cubic meters capacity; and (c) in rural areas, advise on the location of the disposal sites.  In rural communities, in view of the limited volumes of solid waste remaining to be disposed of (the majority of the rural waste is recycled), bulk transport will not be necessary.  If communities do require periodic haulage they will mobilize agricultural tractor and trailers.  However, for permanent disposal from urban communities linkage will be made with the city-wide waste collection and disposal systems.  For design purposes the volume of solid waste generated in urban areas is based on 1.5 to 2 litres per person per day and in rural areas 0.75 to 1.5 litres per person per day.

I.	Tagging/ Numbering Streets

16.	A pilot project will be initiated in an urban settlement for tagging and numbering streets in order to develop typical designs and specifications.  Upon successful completion of the pilot the activity will be replicated at a wider scale.

J.	Trunk Infrastructure/ Hydel Power Generation

17.	The design criteria for the trunk infrastructure will be followed from the agencies where the CISP site is located.  For example, in case the community network is to be connected with the city network then the design parameters followed by the city for the connecting trunk system would prevail.  Similarly, pilot projects for promotion of appropriate technology such as micro level power generation will be undertaken.