## Sheet1
Annex 'B'
CISP: Implementation Phasing
Imple. Arrengements |  | CIS Implementation Streams | 2002 |  | 2003 | 2004 |  | 2005 | 2006 | Remarks
Rural Community Infrastructure Sub Program (RCISP)
By Field Team Group I (20 Teams) |  | Round A1: 100 Community Infrastucture Sites(CIS) covering 100 villages | [7 empty] | Pre Project Phase completed in 2001
|  | Round B1: 100 CISs | [7 empty] | Villages already influenced by the previous RWSSP and RWS schemes
Round B2: 100 CISs
By Field Team Group II (20 Teams) |  | Round A2: 100 CISs
Round A3: 100 CISs
|  | Cumulative No of Rural CISs/ Villages | 100 |  | 300 | 400 |  | 500 | 500 | Out of 1640 Villages
|  | Rural Population reached | 176000 |  | 528000 | 704000 |  | 884100 | 884100 | Out of Total Pop.2.9 M
Urban Community Infrastructure Sub Program (UCISP)
By Partner Organization/ Servise Providers |  | Round C1: 25 CIS covering 25 urban low income communities (LIS) | [7 empty] | Pilot Projects
Round C2: 50 CISs
|  | Cumulative No of Urban CIS/ LIS |  |  | 25 | 75 |  | 75 | 75
|  | Urban Population reached |  |  | 62500 | 187500 |  | 187500 | 187500
|  | Total No of CIS Projects (Cumulative) | 100 |  | 325 | 475 |  | 575 | 575
|  | Total No of polulation reached | 176000 |  | 590500 | 891500 |  | 1071600 | 1071600 | Out of Total Pop.2.9 M
Round A:Includes new villages (with full comm. infrastructure Package) |  |  |  | Pre- Planning Phase |  |  | Project Preparation Phase
Round B: Includs RWSS Project Villages |  |  |  | Implementation and O & M Phase
Round C: Peri-Urban Low Income Communities
CIS:Village in Rural Sub Program; Low Income Settlement in Urban Program

## Sheet2
Annex 'B'
PROPOSED PHYSICAL INFRASTRUCTURE
IMPLEMENTATION PLAN FOR WORKS
PHYSICAL PHASING BY SUB-COMPONENT
S. | SUB-COMPONENT | Unit | Year 1 15% | Year 2 30% | Year 3 30% | Year 4 25% | Total
1 | Water Supply | No. | 190.8 | 381.6 | 381.6 | 318 | 1272
2 | Community Latrines | No. | 117 | 234 | 234 | 195 | 780
3 | Stormwater Drainage | Linear Meter | 37171.8 | 74343.6 | 74343.6 | 61953 | 247812
4 | Access - Internal Pathways | Kilometer | 45.9 | 91.8 | 91.8 | 76.5 | 306
5 | Access - Foot Bridges | Linear Meter | 606.6 | 1213.2 | 1213.2 | 1011 | 4044
6 | Street Pavement | Linear Meter | 10236.75 | 20473.5 | 20473.5 | 17061.25 | 68245
7 | Street Lighting | No. | 81.15 | 162.3 | 162.3 | 135.25 | 541
8 | Solid Waste Management | No. | 74.25 | 148.5 | 148.5 | 123.75 | 495
9 | Tagging / Numbering Streets | Job |  | 1 |  |  | 1
10 | Trunk Infrastructure / Micro Hydel Station | Job | 1 | 2 | 2 | 2 | 7
Note: The implementation cycle of a typical scheme, from inception to handing over, is estimated to be two years. Thus, a scheme proposed at the start of Year 1 shall complete by the end of the Year 2. However, the construction of each scheme will be limited to one year and spill over of construction work will be avoided.