PART A

# PROJECT DIGEST

| 1) Name of the Project: |  | Community Infrastructure Services Program (CISP) of AJK |
| --- | --- | --- |
| 2) Authorities Responsible for: i). Sponsoring: ii) Execution: iii) Operation & Maintenance: |  | Local Government and Rural Development Department, Government of Azad Jammu and Kashmir -do- Beneficiary Communities/ Community Based Organizations |
| 3) Time required for completion of Program: |  | 48 Months (July 2002 – June 2006) |
| - Plan Provision: - (i) If the program is included in Five year Plan, specify actual allocation: (ii) If not included in the current plan, how is it now proposed to be accommodated (inter/inter-sectoral adjustments in allocation or other reason may be indicated). b. If project in not included in the plan what warrants its inclusion in the plan: |  | The program is proposed to be included in the AJK Government’s 10 year Perspective Plan (2001-2011) N.A N.A |
| - Relationship of the Project with the objectives of the sector: indicate the contribution of the project, quantified if possible to the targets in Five Year Plan and name the other projects (whether sanctioned or under preparation) which would program within the sector: |  | I. The project objectives are in line with the sector objectives viz: - Poverty alleviation - Focus on improving the well being of low-income communities. - Capacity building at the local levels for good governance - Encouraging community participation in local development. - Improvement of health indicators. II. A major portion of the program funds are proposed to be spent on providing infrastructure services including: - Water supply - Sanitation - Access (Roads and Bridges) - Street Pavement - Drainage - Street light |
| - Capital Cost of the Program (Including Contingencies) |  | - Local PKR 1749.995 million - F.E Cost: PKR 14.875 million Total: PKR 1764.87 million |
| - Annual Recurring Expenditure after Completion: |  | The infrastructure will be operated and maintained by the participating community. |
| 8) Objectives of the Program preferably in quantifiable terms: |  | As per general agreements reached during various missions of the IDA to the CISP, the objectives of the program will be to improve overall living conditions and sustainable access to basic infrastructure, health and sanitation facilities for about 830000 people living in rural and urban low income communities through: - Delivering cost effective and sustainable community development programs and sustainable infrastructure services to 375 un-served and under-served, low income rural and 75 peri-urban communities using participatory community based approaches; - Strengthening the role and capabilities of the Districts and lower level of local governments to extend technical, financial and management support to the community-based organizations (CBOs) at about 425 sites; - Increasing participation through community development and expanding the number and capacity of community based organizations (CBOs) to increase their participation in development activities; and - Promoting effective governance and accountability through improvement of operational procedures/guidelines, monitoring and evaluation. This also includes financial, budgeting and processing procedures to ensure transparency in program implementation. |

Compiled and

Prepared by:	1.	Ghulam Murtaza Khan) ________________________________________

Deputy Project Director LGRDD

2.	(Syed Zaheer Hussain Gardezi),  _________________________________

Additional Project Director LGRDD

Reviewed and

Checked by:  		(M. Saleem Bismil ) ___________________________________________

Director, LGRDD

Approved By: 	(Sardar Riaz Ahmad Khan) _____________________________________

Secretary, LGRDD

#### PART B

#### PROJECT DESCRIPTION

| #### 9) | #### Location of the program: |  | #### Azad Jammu and Kashmir |
| --- | --- | --- | --- |
| #### 10) | Existing facilities: |  | CISP comprises three components; - Decentralized Planning and Implementation; - Community Development; and - Infrastructure Upgrading and Services. #### A description of the current situation in each of these areas is given below; |
|  |  |  | 1. Decentralized Planning and Implementation: At present planning and implementation processes are divided between state districts and offices with top down approach generally prevailing. Identification of community schemes is done at the Local Council/Markaz/ District levels. Community involvement needs further strengthening. The project communities which implement the community schemes are mostly unregistered. This ‘loose’ relationship often hampers proper financial close of the completed schemes. - Due to lack of proper community mobilization, organization and training, selection of sites often suffers from biases. - Approval of all schemes is normally done at the state level. - Implementation is normally done with the active involvement of district offices. 2. Community Development - At present there are unregistered Water and Sanitation Committees (WSCs) and informal groups in about 500 villages. Proper auditing of accounts in the WSCs is yet to be instituted. - Formal community based organizations (CBOs) to implement schemes are evolving but at very slow pace. - Women representation is almost non-existent. - Capacity to develop community action plans is minimal. - Lack of trained community workers/leaders to ensure sustainability of schemes. - Lack of authority on use of government development funds at the community and users groups level. - Lack of training on issues of health, hygiene, sanitation, organization and campaigns etc. 3. Infrastructure Upgrading and Services: The extent, age and condition of the existing infrastructure varies from community to community and ranges from essentially non-existent, through aged and dilapidated to recent but poorly maintained. - Water supply schemes are mostly spring based in the Northern parts of AJK and in some plain areas of the Southern parts of AJK ground water (dug well, hand pump and boreholes) is used. Maintenance is generally below the standards, unofficial connections to the supply network cause decreases in delivery pressure, and leakage in the supply network is generally a significant problem. Main and distribution pipelines in urban and other densely populated areas are often located along sullage water drains providing the possibility of drawing contaminated water into the line through leaking joints. The quality of the water is poor in some cases. About 40% population is yet to be provided with piped water facilities. - Drainage (sullage and stormwater flow) facilities comprise katcha and pucca drains along the roads/streets/pathways of the settlements. These are poorly maintained in the overwhelming majority of cases, are generally of inadequate size for the flows, many are discontinuous (i.e. not interconnected), many have no outfall and there is no treatment of the waste water. This situation generally results in the drains overflowing into the streets, collecting in low points and forming puddles of stagnant water throughout the community. In urban slum settlements and peri-urban inhabitations, the situation is often aggravated by discharge of human waste into the drainage channels. - Sanitation facilities are mostly rudimentary with many properties having no latrine facilities whatsoever. In such cases residents usually use the fields adjacent to the settlements. Where latrines exist they are mostly not properly used and their maintenance is highly neglected. Overall availability of latrines with the households is about 40% but in the case of rural areas this facility is still below 20%. There are not available reasonable facilities of Public/Community latrines. - Solid waste disposal practices vary, with waste in rural and some semi urban areas generally comprising organic matter which itself gets composted at dumping places and some times it is burnt by the residents. In urban areas non-organic waste is also generated and it is generally collected by the urban local councils and transported to the dumping sites. - In most communities storage of waste is unorganized and waste is often deposited in public places/streets/roads from where it is scattered into the streets by the wind and by scavenging animals, resulting in unhygienic and unsightly conditions in the community. - Accesses to and within communities are paved (brick, stone, concrete, black topped) but many, particularly more minor streets and access way in rural communities, are kutcha. The paved streets are generally inadequately maintained, many in need of extensive Repair/reconstruction or are buried by over burden. Unpaved streets and pathways become impassable in the rainy season, generate dust nuisance in summer and generally make pedestrian and vehicular access difficult. The communities living across the rivers and streams face access difficulties where nearby crossings are not available. - The institutions, the government departments and local councils which are responsible for delivery of infrastructure are not successful in achieving the targets, as required, due to: - Insufficient management skills - Lack of resources Current Indicators: Some of the current indicators, detailed below provide the basis for investment in the program under the new project: - Access to Road/Transport: Link roads are not available in most rural areas, tracks for 4x4 Jeep exist in some areas. Public/private transport plies on the main roads only which entails 2-3 Km. Of walking to destination. After sunset transport is usually not available. Similarly, access to remote areas is difficult due to inadequate foot bridges, pathways. - Water Supply/Sanitation: About 81% urban and 55% rural population has access to water supply. Overall 40% households have latrines while in rural areas less 20% households have this facility. - Drainage: While most of the urban areas have planned drainage systems, the rural areas have little or none. Investments made in providing access/roads without proper drainage in such areas are always at risk of being washed away. - Street Pavements/Lighting: Settlements of urban/peri-urban areas having the poor inhabitants are mostly unplanned and their streets are mostly unpaved and without streetlight facilities. - Solid Waste Management (SWM): Present arrangements are grossly below the standard. Collection and disposal of solid wastes is required to be imposed specially at district headquarters. - Tagging/Numbering Streets: At present, there is no organized system of identifying houses/properties in the low income communities in the urban/peri-urban and slum areas. - Trunk Infrastructure: Infrastructure provided under the previous projects and to be provided under CISP schemes will be integrated into the trunk/main infrastructure. These linkages will ensure better coordination of management of the facilities. This also includes new and appropriate technology. Community Organization: At present the communities are organized on the basis of Biradarees (clans), political affiliations and income levels. While most of the development schemes are planned and implemented by the various line departments of the Government. Participation of the community is low with the shift in emphasis to the bottom – top approach in planning/implementing infrastructure. The communities are expected to play a leading role in CISP. However this would entail proper training, motivation, upgrading of the skills and effective involvement of women. |
| #### 11) 11.1 | #### Description of Program Background |  | Introduction: Azad Jammu and Kashmir with an area of 13297 Sq. Km. Has a population of 2.9 million (1998 census) about 88% of the population lives in the rural areas. About 40% of the population lives below the poverty line. An IDA assisted Rural Water Supply and Sanitation Program Project (RWSSP), spreading over 8 years implementation span and costing about 1210 million rupees, was completed by the LGRDD in 2000. Performance of this Program Project has been highly satisfactory. Under this project, 1600 drinking water supply schemes for a population of about one million were selected and implemented. Majority of these schemes have been functioning under the formal and informal arrangements of the beneficiary communities. Success of this program project persuaded the Govt. of AJK to plan and implement an other community based program project that should address drinking water supply problems of the remaining communities and along the water supply schemes should also provide other community based infrastructure and services to the low income communities both in urban and rural areas. The World Bank indicated their interest in providing financial assistance to the new expected project in which lessons learnt from the RWSSP and the World Bank assisted community infrastructure project of the NWFP could be practiced and further developments in the community based approaches could be achieved. |
| #### 11.2 | #### Program Components |  | Program Components: The program will comprise the following three complementary components: #### Decentralized Planning and Implementation - Community Development - Infrastructure Upgrading and Services |
|  |  | #### (ii) iii) | Decentralized Planning and Implementation: This component of the program would develop the capacity of state, district, communities, CBOs and specially to facilitate to enhance the decentralized capabilities at district and local level. This component would provide funds for the following; Technical Assistance and Capacity Building: The objective of this component would be to provide additional expert technical inputs and as well as training and exposures to the public and volunteer sector in AJK in order to enhance the capacity of the program implementing agencies to achieve the expected outputs of the program. Funds have been set for the following main sub-areas - Consultancy inputs: Approximately 58 manmonths (MM) of senior advisors (Community Dev. Specialist- International 6 M), Procurement Specialist through Firm (10 MM) and short term technical assistance (National 40 M) is provided during the program period, to provide support for the overall management processes of the program, and in particular, to strengthen the community development component. Given the skill balance of the team, the advisors should be specialists in working with the voluntary sector, and have strong skills in community development and participatory methods. Consultancy inputs will be procured under the World Bank Guidelines. - Surveys: Funds have been allocated to carry out a) water quality testing program and to b) conduct Baseline Surveys. Two baseline surveys will be conducted during the first year and last year of the program to collect the information on infrastructure facilities and community based services. - Institutional Strengthening: During the first year of CISP, a Capacity Building Programme of the concerned agencies will be prepared. Funds would be allocated for the implementation of this Capacity Building Program that includes overseas training programs and study tours of senior and mid level officials from the concerning departments and CISP, having various roles in the CISP operations, staff capacity and training programs for personnel of District/Municipal Council and other partners including CBOs to ensure that they can effectively carry out their terms of reference as catalysts of communities in completing the development cycle in community schemes. - Operational Cost: Cost of incremental staff required for the program implementation, and other running cost of the program including office rent, O&M of vehicles and equipment, the fuel cost and TA/DA provisions etc. For details see Annex “D” table 2.1 and 2.2. - Vehicles and Equipment: This includes the purchase of vehicles, furniture and fixtures for various CISP offices. It also includes computers equipment consisting of one terminal for each professional staff, and requisite software and multimedia equipment. Community Development: This would include (i) mobilization/organization and capacity building through development of community action plans (iii) health, and environmental sanitation awareness (HESA) , and (d) Support to Women and Children (SWC) in the areas of community education (functional/economic literacy), and special learning activities designed to increase their participation, skills and management training and linkages to economic and micro-credit opportunities. The latter component will link communities to existing government, private, banking and non-government organizations for establishing partnerships on income generating activities and access to small scale credit (e.g., Pakistan Poverty Alleviation Fund, Micro-credit Bank etc.,).The component will finance capacity building activities, and services provided by other Service Providers (local NGOs, and private groups), training and related equipments. The main thrust of community development activities is to encourage users, particularly women, to participate in decision making to increase ownership for long term scheme sustainability. This component consists various activities. Details are in Annex “D” table 3. Mobilization and Capacity Building Activities include awareness raising and organization. These include a series of small workshops, group discussions, information campaigns and participatory community action planning (CAP) training to enable users to organize and elect a representative and responsive Community Based Organization and/or User Group/Committee. Efforts would be made to have at least 30% representation of women in the CBO/user group. Non Formal Education (NFE) will be integrated with the CAP process and will focus on functional literacy, decision making and problem solving. Mobilization and capacity building activities will be carried out through out the community project cycle, the main phases of which are: - Planning and Preparation. The focus is on group building, self investigation, problem structuring and discussing options for water supplies and environmental sanitation and other community infrastructure leading to the formulation of the CAP as a proposal for implementation phase financing. The role of the District/Municipal/Town offices and their service providers is to build capacity and facilitate the active participation of women, confirm demand and willingness to contribute to program costs, and take responsibility for operation and maintenance. CBO generally consists of 7-12 members; hence at least 30% CBO members will be trained per community. CISP staff or Service provider’s inputs per community will vary depending on scheme size and complexity but the mix of skills required will be the same for all. - Implementation. In this phase responsibility for community organization and strengthening is shared equally by the CBOs and SP staff. In order to enable the CBOs to carry out their functions effectively training at the community level focuses on those skills needed to implement and manage schemes for long term sustainability; effective use of improved water supplies through HESA; and training to enable women to take advantage of time savings. - Training to CBO members will focus on the roles and responsibilities, community monitoring and procurement issues. At least one community treasurer per community will receive training on simple book/record keeping enabling the CBO to maintain its book of accounts. HESA activities will be targeted to traditional birth attendants, community elders, school teachers, students with special emphasis on beneficiary women, and their young children. HESA training and small workshops will center on personal and domestic hygiene and environmental sanitation, latrine options and drainage. District staff and their partners will assist community to establish linkages with other organizations for income generation activities, explore options and identify skill enhancement training. Funds, under this component, would be allocated for the following activities mainly targeting for institutional strengthening at community level through providing training and exposures to community leaders, staff members of the program. Health Environmental Sanitation Awareness (HESA) The second activity will focus in improving personal and domestic hygiene and environmental sanitation. Activities would be conducted in informal settings and by using real life situations and experiences. Women would be the focal point for HESA, and activities would be conducted through tap stand and/or women’s groups. Women would be involved in monitoring and evaluation by measuring changes in hygiene practices such as water use and management, and tap stand hygiene. For HESA activities at least 2 women from each tap stand /women's group will be trained. The number of sessions/training activity and intensity will vary from community to community and will depend on scheme size and need. Support to Women and Children (SWC) Activities. The third activity provides support to help (i) women develop skills required to realize the benefits of improved community infrastructure particularly water supplies; (ii) improve access to the formal credit system, (iii) promote women's role in planning and implementing community infrastructure and water supply and sanitation schemes including environmental management initiatives; and (iv) encourage participation in resource mobilization activities such as collection of user charges, and monitoring and evaluation. Project support would be in the form of training- mainly participative type of the training activities. This part of the component will focus its activities on community education (functional/economic literacy) and develop Micro Credit Linkages. Infrastructure Upgrading and Services: This component involves investment for infrastructure upgrading and services, with priorities to be established in consultation with the communities through their CBOs. A menu of infrastructure to be provided would typically include: water supply and sanitation schemes; storm-water drainage, flood protection, footpaths, streets lighting, solid waste collection and disposal, and community facilities. Other types of infrastructure such as access footbridge could be considered if identified as community priority; and trunk infrastructure required ensuring that basic infrastructure functions efficiently would also be included. Particular attention will be given to the interconnection between the delivery and timing of water supply, and health and sanitation activities. The major sub component is rural water supply and sanitation and the upgrading of basic infrastructure in approximately 425 rural and peri-urban communities. |
| 11.2.1 11.2.2 | Policy Framework Social Aspects |  | This component would be demand driven, with the infrastructure to be provided according to the priorities of the respective communities. The fundamental concept of the program is to foster a sense of ownership of the infrastructure on the part of the communities. Communities’ ability to choose among different initiatives and encourage them to contribute financially to the investments they choose, and to take greater responsibility for the operation and maintenance of the completed programs. Appropriate functional standards for planning, design, and construction would be developed taking cognizance of locally available materials, ease of construction and maintenance, and affordability. Affordability and a balanced provision of infrastructure will be important objectives in the design process, although the program allows communities to choose from a range of alternative standards within cost ceilings. Another important objective of the process is to improve operation and maintenance (O&M), and communities would be required to agree to satisfactory O&M arrangements prior to selecting any specific infrastructure scheme. The final composition of the program would only be known after each community has prepared its CAP and has been reviewed and modified to conform with technical, financial and other agreed criteria. This process, following the establishment of CBOs and their participation in the planning and design process carried out by the CISP staff and other staff of the LGRDD and Local Councils/Governments, and its service providers and consultants. Past experience suggests that following are generally the top community priorities, (a) water supply; (b) drainage; (c) access; and (d) solid waste disposal The order of priority may differ from community to community and, in a few cases, other priorities such as flood protection works might take precedence. Sanitation facilities and practices in the communities are generally considerably poor, and yet demand for sanitation facilities (e.g. latrines) has rarely featured in the lists of community priorities in the past. This may imply that the survey processes may have been too limited resulting in a narrow range of community infrastructure demands. Thereby efforts will be made to improve participatory demand techniques. Water Supply Water in rural areas is supplied by various means including spring boxes, rain water ponds, stand posts, hand-pumps, wells and through individual or shared house connections. In larger communities and urban or peri-urban areas tube-wells and reservoirs, constructed and operated by PHED, serve the distribution systems. Public Works Department will be consulted in the schemes where beneficiaries are living in urban areas and existing network of the Public Works Department is proposed to be used. This department will also be consulted if water sources under their control are selected for the CISP schemes. Sanitation Promotion and Community Latrines (public toilets) Although sanitation tends not to be an initial community priority, surveys and meetings with women's community organizations have shown in the past that the sector requires urgent intervention. A sanitation component has therefore been included in the program. The major thrust of the program will be a two-stage process of (a) generating much greater community awareness of sanitation and health linkages, and to improve sanitation practices. The experience of the RWSSP in AJK and other areas will be drawn upon, particularly in the education and training field and (b) the physical elements of the sanitation program to be established under the program will have two main parts: promotion through demonstration of public latrines (including if applicable on a pilot basis, pre-treatment ponds in urban or peri-urban communities where sewerage systems exist). The demonstration latrines will generally be consistent with the RWSSP experience – to encourage householders to install appropriate toilet facilities. Storm Water Drainage The storm-water drains invariably act as sewage carriers, conveying their contents either to main watercourses, to open areas or to fields. Based on community demands, comprehensive open channel storm water drainage systems will be constructed as trapezoidal or rectangular channels in either bricks/stones or concrete. Design and cost estimates specific to site will be prepared and approved prior to implementation. Access, Internal Pathways, Signage and Street Lighting In rural areas, access is provided through a network of narrow, generally unpaved paths, little more than a car's width across, sometimes flanked on one or both sides by open ditches. The main access roads to urban settlements are more integrated with the town's road network and generally paved, though often lacking maintenance. The network of roads and footpaths within urban settlements are similar to those in rural areas but carrying significantly more traffic. Improvements within the program are limited to improvement/upgradation of only existing tracks and Katcha roads, paving of existing streets and footpaths. Appropriate functional planning, design and construction standards are to be used. The materials proposed in road and footpath construction generally reflect locally used construction material, such as bricks and stones. Concrete is used in steep slope locations and where storm water flows are significant. In case of foot bridges detailed technical scrutiny will be made prior to start of work. Technical viability and number of people to be served will be given due importance while selecting the schemes and type of bridges (foot/jeepable). Internal path ways/ walk ways / side walks/ streets should serve one settlement or provide linkage between two or more settlements. Solid Waste Management Brick or stone-built containers (collection points) primarily intended to reduce the spread of refuse by wind and animals will be constructed, and coverage will be designed to appropriate and consistent planning standards. Purchase of land for collection points sites is not likely to be necessary since communities generally agree to provide sites. Local transportation (hand or animal drawn carts) needs in urban areas will also be provided as necessary. Trunk Infrastructure and Community Facilities Trunk infrastructure will include off-site infrastructure and that infrastructure serving the community at large. Major share of the sub-component will be allocated for provision of water supply and drainage infrastructure. Consistent with most of the public infrastructure supply in AJK, communities would not necessarily contribute directly to trunk infrastructure costs. The program includes a component for such infrastructure, which is subject to an assessment of technical and economic feasibility if costs exceed a threshold amount. Subject to this requirement, once a community has determined a service to be a priority, the development of any required trunk infrastructure could commence directly, and be undertaken in parallel with community mobilization, development and resource mobilization activities. Against this sub component, micro hydel schemes would also be eligible. These schemes will be taken up on pilot basis with involvement of the AJK Hydro Electric Board. Policy Framework: To guide the community based approach to basic infrastructure services in AJK, it has been agreed with the World Bank that a policy framework would need to be formulated to achieve the objectives of the CISP. The policy framework would be developed and made applicable keeping in view the following guiding principles: - Provision of integrated social, economic and physical infrastructure and services to low income communities in rural and urban areas to be selected based on the community demands. - Priority to those communities which demonstrate commitment through their capacity for social organization and financial and other cost sharing contribution; - Communities organized into CBOs or user committees to participate in and be jointly responsible for the identification, design, and implementation of community development activities, infrastructure and services and to be fully responsible for their subsequent O&M; - Communities to contribute land required and at least a 20% share of the capital costs of infrastructure in cost sharing arrangements to be agreed (other than community latrines, solid waste management and trunk infrastructure); - Devolution of powers and authority to the lower tiers of the Government and elected local governments; - Empowerment of the beneficiary communities through their CBOs and organizations; - Ensuring that the essentials of the good governance are promoted through the CISP activities; - Local councils/governments to be effectively involved in the planning and implementation of the CISP activities; Social Aspects Sub-project selection will ensure compliance with social safe guards, poverty focus, inclusiveness, participation of community based organizations, benefits to poorer groups/areas and prevention of elite takeover and will ensure existence of a local level grievance redressal mechanism. It has been agreed with the IDA that (a) approval will appraise against the social parameters laid out at selection; (b) implementation will be at decentralized level with community participation and ownership; (c) the M&E will be a multi-tiered system with participatory community monitoring being one aspect. Monitoring indicators for participatory monitoring will be simple, relevant and used at the community level; (d) support women’s and children component will be closely monitored to ensure progress in implementation and accrual of benefits, and (e) village cross visits will be utilized for experience sharing and solution of problems. |
| #### 11.3 11.4 | #### Institutional Arrangements Implementation Schedule |  | Institutional Arrangements: CISP will be implemented through the existing institutional structure of GoAJK to deal with community infrastructure services. While the program relies heavily on the existing system for accomplishment of program objectives, the program will facilitate and enhance the capacity of the existing institutions in keeping with the ongoing decentralization of local government system in Pakistan. (The overall Institutional structure of CISP is sketched out in Figure I in Annex C). As it is made schematic in Figure I in Annex C, main institutional bodies responsible for the overall CISP implementation are: - CISP Steering Committee (SC): At the highest level of the GoAJK, a Steering Committee will be set up under the Additional Chief Secretary (P&D), and membered by Secreataries Finance, P&D, LG&RD, Works, Social Welfare and Health. The Steering Committee may co-opt other members from public and private sectors including communities, if so required. The Steering Committee will advise on policies and provide overall guidance for the programme, review and approve annual implementation plans, conduct quarterly review of the implementation of CIS Programme, arrange to monitor the Programme, review and decide about consultancy services required for CIS Programme. - Program Management and Coordination Committee (CISP PMCC): To manage and coordinate the program planning and implementation activities, a PMCC would be set up under the chairmanship of the Secretary LGRDD. PMCC would be responsible for reviewing and coordinating planning and implementation matters and also for preparing the overall policy framework and Annual Work Plans for obtaining the approval of SC, approve sub-projects and proposals of other CISP activities/sub components. PMCC, being intra-sector agency would comprise officers of the LGRDD, PWD, LGB, EPA, CISP and representation from other organizations as may be required during the implementation of the Program. - CISP Staff: A full time Project Director will be employed with full administrative and financial powers and will be a focal person responsible for execution of the project. No officer from the lower hierarchy will be posted as Project Director. It has been agreed with the World Bank that the existing trained staff of the RWSSP would be shifted to and continues in CISP. As per requirement of the workload, some new staff positions have also been provided in CISP. List of the staff to be employed on CISP is given in Table-3.1 of Annex- ‘D’. - District staff and CBOs. The existing district offices of LGRDD would be the main implementing arm in carrying out the rural CIS program while Urban Local Councils would function as the implementing agencies for the urban community sub projects/schemes. - CBOs and Users' Groups will be the main partners in the planning and implementation of CISP. Community Based Organizations (CBOs), would be assigned roles in implementing community level CIS Project. Implementation Schedule/ Annual Work Plans: CISP would be implemented through two sub programs i.e. Rural CIS Sub Program and Urban CIS Sub Program. The Rural CIS sub program will cover about 375 villages benefiting 680,000 rural population while Urban Sub Program consists of 50 low income settlements benefiting 150,000 population. Thus more than 27% population of AJK will be benefited. Program implementation schedules are provided in Annex B. Annual Work Plan (AWP) for CISP would be prepared for each year of operation and submitted to SC for its approval before implementation The schemes started in a financial year will be completed in the same financial year and there will be no spill over. |
| #### 11.5 | #### Community Project Development Process |  | Community Project Development Process: CISP would be implemented through community projects (amounting 425), each confined to an un-served or under-served low income village or settlement in rural and urban areas. Communities will submit proposals to the district/urban local councils who then will be responsible for technical review of each proposal. The senior staff at state level and LGB will review the proposals based on agreed criteria for eligibility and selection (based on the technical, financial, economic, social and environmental factors). The proposals will then be endorsed to the PMCC for final approval. Project Development Process includes following main component/ activities: - Community mobilization, awareness training, project identification, CBO registration - Preparation of community action plan (CAP), - Community participation in project preparation and design; - Implementation of infrastructure and community development activities; - Hand-over of completed assets for operation and maintenance. As part of this process each eligible community, with assistance from CISP, is to prepare a Community Action Plan (CAP) which will be discussed with the local council/Local Government, approved by the Program Management and Coordination Committee (PMCC) and reviewed by IDA, if required. The CAP includes: (a) the organizational structure of community organization - including office bearers, project related committees and user groups, membership, representation of women's and other interested groups' etc.; (b) an assessment of the basic infrastructure needs of the community; (c) the selected infrastructure design, including summary of other technical options considered, community development, training and hygiene awareness requirements; (d) a statement of investment and O&M costs, sources of funding and timetable for resource mobilization; (e) arrangements for collection, safekeeping and accounting for the community's contribution; and (f) an implementation plan, including arrangements and a timetable for procurement, supervision and monitoring and evaluation. |
| #### 11.6 | #### Site (scheme) Selection Criteria |  | Site (scheme) Selection Criteria Communities for the Phase I of CISP have already been identified (vide Annex-‘A’.) Eligibility of these identified communities and of those to be identified during subsequent phases will be assessed/evaluated based on the following criteria: a. Low income b. Lack of basic infrastructure and slum areas c. Investment potential d. Size of settlements above 1000 persons e. Geographic spread across districts and urban/rural balance f. Potential for community participation g. Per capita slabs, if any, as may be approved by the SC |
| 11.7 | #### Scheme Finance Eligibility |  | Scheme Finance Eligibility: To be eligible for the program financing schemes proposed by communities have to satisfy the following requirements demonstrating that they are technically sound, ready for implementation, and economically and financially viable: - Community and Local Council/Government Participation and Contribution. The community must demonstrate a willingness to participate in the selection design and implementation of the infrastructure and, in particular, to contribute land and at least 20% to the capital costs of the community infrastructure (excluding trunk infrastructure costs and the land) and to undertake O&M. The Local council/Government must be prepared to participate in all CISP activities in their jurisdiction. - Resource Availability. Trunk infrastructure must be available, or to be provided subject to technical and economic justification. If the primary infrastructure costs of any scheme exceed 50% of the gross cost limit, a technical and economic justification and feasibility analysis will be prepared for review prior to its approval. Any land required must be in public or common ownership or dedicated under legally acceptable arrangements. - Environmental Sustainability. Any scheme which creates the possibility of an adverse environmental impact has been avoided. - Technical Viability. Schemes must demonstrate improvements benefiting the majority of households lacking service, endeavor to provide a balanced package of infrastructure elements, conforming with technical design standards, and have implementation arrangements consistent with proven capacities of community/CBO. Infrastructure sub-components are to be designed as completely functioning systems. - Economic Viability. Excluding the cost of primary infrastructure, the cost of schemes must fall below a cost limit. Although communities will still be able to select a higher cost scheme by contributing full incremental costs. If gross costs exceed per capita cost limits to be pre determined, then data should be provided to (i) indicate the source of incremental financing, and, (ii) reconfirm that the site confirms with the agreed selection criteria. Sustainability The community must be aware of O&M consequences of their schemes, and prior agreements must be in place for adopting completed infrastructure, for the provision of O&M financing. Continuing O&M of earlier phases of project infrastructure must be satisfactory. |
| #### 11.8 | #### Cost Sharing and O&M |  | ### Cost Sharing and O&M: ### The GoAJK agreed with the World Bank on cost sharing and O&M broad arrangements, which are: ### CBOs would be registered bodies and the CISP would facilitate the registration process. The government would review the various methods of registration and use which are appropriate for community organizations; ### Communities would share in the capital costs of the various physical infrastructures through component sharing and minimum percentage sharing principles. The details of capital cost sharing will be notified and delineated in the policy framework; ### Communities would receive the government contribution in the form of advances equal to previously agreed installments. Where applicable, the communities would also deposit their share in the bank account. Advance payment from the government share would be regulated by clear procedure to be given by the PMCC. - Entire O&M responsibility of the completed community projects will be taken over by the beneficiary communities through their user groups, or organizations. |
| #### 11.9 | #### Design Standards |  | Design Standards #### The planning and design standards adopted for CISP are flexible, cost effective and, in most cases, compatible with the other line agencies dealing in provision of similar basic infrastructure through various schemes. The CISP standards and scheme designs will be reviewed and commented by the IDA/World Bank, if so required. However, design standards of the RWSSP will be used in the case of drinking water supply schemes to be undertaken in CISP. |
| #### 11.10 | #### Finances |  | Finances: The CISP would initially use the system used in the RWSSP with appropriate refinements and modifications in order to make it more sound and as much in line with the mainstream system of the GoAJK. It has been agreed with the World Bank that the refinements and modifications would entail, at a minimum, at the start of the program operation. General guidelines to streamline the CISP accounting would be as follows: - as much as possible, use the Accountant General’s Office staff, to be responsible for auditing and accounting purposes of CISP. - Have the Financial Information System part of the Management Information System, developed and introduced by the time of credit effectiveness. Financial Information System should cover preparation of quarterly reports of expenditure, initially at District level and consolidated for the programme, showing amounts expended for each component, and for infrastructure, by type of infrastructure. At reasonable intervals and preferably at the close of each month, reconciliation would be made. - Responsibility of managing funds should be at the state and district level. - Government contribution as agreed between CBO and CISP would be transferred to the CBOs’ bank accounts (or other savings arrangements in the case of communities which do not have Banks in their vicinity) for works managed by the communities. The bank account would be in the name of CBO and would have joint signatories from CBO and CISP. Joint operation would continue till the time the government share is fully expended and accounted for. |
|  |  |  | Audit: The audit arrangements for CISP would be: - CISP’s financial statements and audited financial statements will be sent by the Auditor General with a management letter to IDA within 6 months after closing of the financial year - A system/ form of financial and technical check on the performance, relating to the works as well as financial records, of CBOs/Users' Groups, LGRDD (including the state, district and urban local council offices) will be established and incorporated into the manual and detailed guidelines. Necessary training will be provided to CBOs/Users' Groups and their partners as needed. It was also agreed that the Financial Monitoring Report (FMR) shall be an important part of the financial management system. Disbursement The proposed IDA share would be disbursed over a period of four years. This estimated share of foreign financing is about 80% of the total cost of the CISP. During negotiations with the IDA, the foreign financing share will be agreed subsequently. The proceeds of the foreign financing would be disbursed against eligible expenditures, net of taxes and duties. Tentative disbursement against foreign financing is proposed as follows: Category/Cost Items; Share. 1. Civil Works; 80%. 2. Goods and Equipment; 100%. 3. Operations and Incremental Staff; 100%. 4. Consultants services and training; 100%. |
| #### 11.11 | #### Program Cost |  | Program Cost: Base costs have been calculated in October 2001 prices and the conversion rate used for one USD is 65 PKR. Price contingencies and physical contingencies on the base cost estimates have been added as follow: ##### Price Contingencies; %. FY1; 0. FY2; 6.5. FY3; 13. FY4; 19.5. Physical Contingencies (On works only); 5%. Costs are summarized in table below. Further details appear in Annex ‘D’ which provides a complete set of cost tables. CISP: Summary of Estimated Costs Components; PKR; USD. Decentralized and implementation; 180.68; 3.488. Community Development; 125.23; 0.855. Infrastructure upgrading and services; 1232.36; 25.584. Base Cost; 1538.27; 29.928. Price Contingencies; 164.98; 3.800. Physical Contingencies; 61.62; 1.279. Grand Total; 1764.87; 35. Financing Plan: A financing plan is shown in the table below. These estimates have been prepared based on discussions with the missions of IDA. The community participation part of the cost estimates is calculated based upon previous experience of the RWSSP. Source; # PKR. Communities; 226.400. Govt. of AJK; 238.470. IDA; 1300.00. Total; 1764.87. Special Account (a) To facilitate timely payment/disbursement, a Special Account would be opened by the LGRDD, with an amount of up to US$.1.5 million in the National Bank of Pakistan on terms and conditions acceptable to IDA. This would be used for IDA's share of financing of the expenditures. The Special Account would be used for payments of all eligible foreign and local expenditures. The Special Account would be replenished as per the IDA procedures. (b) On the part of GoAJK, revolving fund with an adequate amount of PKR would be set up to arrange prompt payments to the CBOs/Users' Groups and eligible claims. This revolving fund would be used for the payment of the claims/bills and replenished with the transfers of funds from the respective shares of IDA and GoAJK. Final adjustment/settlement of the revolving fund would be made at the close of the CISP accounts. Retroactive Financing: Retroactive financing would be requested from the IDA to cover eligible expenditures on civil works, materials, incremental staff, vehicles and equipment, consultancy services and training amounting to about US$ 1.000 Million equivalent, incurred after Oct 2001 and before the credit effectiveness date. Procurement: - To provide procurement support and guidance and to serve as the focal point for procurement matters related to both the rural and urban sub-programs, the services of a procurement consultant will be hired. Basic procurement training will be received from the Bank staff before the start of the CISP and periodically during its implementation. - Procurement of Goods, Equipment and Works under the program will be carried out in accordance with the World Bank’s Procurement Guidelines, and Consultants’ Services will be procured according to the Bank’s Consultant Guidelines. The Bank’s standard/sample bidding documents will be used for procurement of goods and works under International Competitive Bidding and National Competitive Bidding. The model contract document for procurement of works through community participation (based on the Bank’s sample format) will be used. |
| #### 12 | Give date when capital expenditure estimates were prepared |  | October, 2001 |
| #### 13 | Give break down of capital cost year wise, covering the whole of the investment period as indicated. |  | A summary of capital cost is provided in Table 1 of Annex ‘D’ |
| #### 14 | Basis of cost estimates (give full details): |  | Cost estimates for civil works are based on the Composite Schedule of Rates, 1998 with average 12% premium. For water supply schemes, the cost estimates are based on the completed RWSS works. |
| #### 15 | Estimates of annual maintenance / recurrent expenditures After completion of the Project and Agency responsible for meeting the recurrent expenditure. |  | Maintenance cost of all scheme will be met by the respective beneficiary comminutes and hence no additional cost to be born by the LGR&DD. Community Based Organizations representing the beneficiary communities will be responsible for meeting maintenance/ recurrent cost |
| #### 16 | Unit cost of each category of service output. |  | The unit costs of the various service outputs are: ## Piped Water Supply Public Tap stand = Service Level PKR 1500 Per Person ## Sanitation Community Latrine(Rural)= PKR 20,000 Per Unit Public Latrine (Urban) = PKR 300,000 Per Unit ## Drainage Storm water drain PCC(Flat terrain)=PKR 430 Per Meter Storm water drain PCC (Hilly) =PKR 388 Per Meter ## Access Road (up-gradation) = PKR 350,000 Per Km Bridge (foot/jeepable) = PKR 25,000 Per meter Footpath/Walkway/Street Pavement ## Footpath dressed stone (avg.width 1.25m)=PKR 607 P/Meter ## Footpath Brick (avg.width 1.25 m) =PKR 453 P/Meter Walkway PCC(avg.width2.25 m) =PKR 900 Per Meter Walkway Brick(avg.width2.25 m) =PKR 681Per Meter Brick paved street (average 4 meter width= PKR 917 P/M PCC street (average 4 meter width) = PKR 1189 P/M |
| #### 17 | Expected Income Statement (profit and loss accounts) |  | All facilities and services created by the program would be owned and managed by the beneficiary communities. |
| #### 18 | Indicate if any charges will be levied for providing the service. |  | No changes are proposed to be levied on the service provided, as O&M responsibility will rest with the communities/CBOs. Scheme specific tariff will be determined by the respective CBOs |
| #### 19 | Annual phasing of physical work and financial requirements for the Project. |  | A summary of the annual phasing of physical work is shown in Annex ‘B’. Summary of the financial requirements is shown in Table-1 of Annex ‘D’ |
| #### 20 | Foreign exchange expenditure: |  | (1) Consultants' Services = PKR 4.850 million (2) Training PKR 10.000 million Total = PKR 14.875 million Say = USD 0.23 million |
|  | a) Likely sources and foreign exchange cost of the project. |  | IDA and other donors. |
|  | b) Present position regarding availability, commitment or negotiations. |  | Appraisal of the CISP completed .in December 2001. Project Appraisal Document (PAD) has been circulated. Negotiations are expected during the first quarter of 2002. |
| #### 21. | Indicate sources and amount of rupee component of Program. |  | (a) AJK Government =PKR 238.47 million (b) Community =PKR 226.40million (c) IDA and other donors =PKR 1300.00 million |
| #### 23. | Risk Analysis - |  | Risk assessment of the program carried out by the World Bank concludes that overall risk rating comes within “Modest Risk ‘ category. |
| #### 24. | Results of the Program |  |  |
|  | - Direct benefits. |  | (a) Improved water supply facilities for about 5,39,000 population. (b) Better access, sanitation and environmental facilities for about 425 communities. |
|  | - Indirect and other socio/economic benefits iii- Economic Appraisal |  | (a) Community mobilization and organization for collective efforts. (b) Creation of physical assets commonly owned and to be used by the communities. (c) Provision of the community based services especially to the low income families, particularly the women and children. (d) Contribution to decrease the occurrence of environment related diseases. (e) Contribution to the public education and awareness on the governance issues. Social Benefits All such programs which are established for public utility such as water supply and community infrastructure etc. are to be evaluated on the bases of social costs and benefits. The ultimate benefits that are potentially achievable through participatory development schemes of water supply and community infrastructures relate to: - Time, cost and energy saving; - Increased leisure; - Involvement in income generating activities; - Less diseases less medical expenditure; - Better children care; - Support to livestock; - Collective efforts of development for common benefits; - Integration of the poorer segments of population in local development resulting in poverty reduction; - Beneficiaries’ participation leading to inculcation of democratic values; - More time to education ; and - Reduced infant and maternal morality rate; iii-Economic Appraisal: The program is to target the poor communities for providing them basic services. Hence calculation of IERR or cost benefit ration is not required. The social benefits listed above justify the investment. |
| #### 25 | 25. a) Approximate number and categories of job opportunities likely to be created indirectly as a result of: |  | - Implementation Skilled and Unskilled labour = 75,000 workdays - Operation and Maintenance Skilled and Unskilled Employees = 465 Nos |
|  | Economic life of project components - Building - Equipment - Books |  | Water supply - Electro mechanical equipments = 5-10Yrs - Pipes GI = 25Yrs HDPE = 30Yrs Sanitation - Latrines = 30Yrs - Local Sewerage Systems = 20Yrs - SWM structures = 30Yrs Access - Roads = 15Yrs - Bridges = 25Yrs - Streets = 20Yrs Street Lights = 20Yrs |
| #### 26- | Community/ Beneficiary Participation |  | CISP is community based community managed program and hence the beneficiary participation is the cornerstone of the program implementation. Communities will contribute land and at least 20% of the capital cost of infrastructure sub-components as to be agreed with the beneficiary communities during planning of their sub-projects/schemes. Entire O&M will be responsibility of the beneficiary community through their CBOs/Users' Groups/Organizations. |
| #### 27- | Provision for Future Expansion |  | The World Bank has indicated their interest to consider the follow up project subject to the successful implementation of the CISP |

PART C

#### PROJECT REQUIREMENTS

| 28. I) Detailed list of technicians and professionals required for implementation of the project. |  |  |  |  |
| --- | --- | --- | --- | --- |
| - Manpower: |  |  | Category Person Months Professionals (Advisors, Consultants) 58 Management and Coordination 360 Engineering and Technical 4800 Community Development 3360 Information Technology 840 Finance, Audit and Accounts 880 Clerical 640 Others 4000 Total 14938 |  |
| - Likely shortage of manpower by occupation. |  |  | Not expected. |  |
| - Efforts to be made in the program for skills development |  |  | (a) Community mobilization and organization. (b) Participatory planning and implementation of community based projects (c) Appropriate technology (d) Monitoring and Evaluation (e) Information Technology (f) Project Management and Supervision |  |
| - Physical and other facilities to be provided from the Project. |  |  | Vehicles, Office and Field Equipments and Office accommodations (rental buildings) |  |
| - If any civil works of any kind included in the Project, then provide details: |  |  | CISP includes civil works. Details are provided in the Infrastructure Upgrading and Services component of the Programme. |  |
| - Material, supplies and Equipment requirements: |  |  | G.I Pipes = 5.60 million meter HDPE = 0.27 million meter Motor/Pumps = 300 units Cement = 37,000 metric ton Steel = 1210 metric ton Steel Wire Rope = 73,000 meter Vehicles = 21 Nos. Motor Cycles = 28 Nos Computer sets = 32 Sets Photocopiers = 14 Nos Field equipment = for all districts Furniture/fixture = for 10 offices |  |
| - In the case of imported material and equipment for execution, indicate: |  |  | Vehicles may be procured under International Competitive Bidding (ICB), if so required under the World Bank Guidelines. |  |
| Part “D” Environmental Aspects |  |  |  |  |
| - Environmental Evaluation/ Impact Assessment |  |  | A comprehensive Environmental Management Framework (EMF) for CISP has been developed by Director EPA of the Govt. of AJK. This EMF provides environmental assessment, mitigation strategies, capacity building, and institutional requirements to make this project environmentally acceptable. This EMF has also been approved by the World Bank. A copy of the EMF is enclosed for Environment Section. All the recommendations made in the EMF for this project will be implemented. A comparative analysis of potential environmental problems and potential benefits of CISP reveals that the overall impact of the project will be environmentally positive (if implemented properly according to the EMF). Most of the sub-projects will yield cumulative environmental benefits while some sub-projects may produce small-scale negative environmental impacts. The sub-projects likely to give positive cumulative benefits to the environment are:- - Water Supply - Health, Hygiene and Sanitation Awareness - Community Development and Capacity Building The subprojects that may cause both positive and negative cumulative environmental effects are: - Demonstration and community latrines - Drainage and Street Pavements - Sewerage - Solid Waste Management The only sub-project that is likely to have only negative cumulative impact on the environment is the construction of access (roads and bridges). However, the construction of roads and bridges is unlikely to cause any major environmental impact due to very small size and localized |  |
|  | 34. Item-wise economic /Financial implications involved in implementing Environmental Pollution Control Measures |  |  | # Use. The requirements of the environment framework will be complied with while selecting and implementing the CISP activities. Important decisions in this regard are given below: - Update both EMF and Operational Manual (which is derived from the EMF), as per comments/suggestions; - Carry out further consultations and test forms and checklists with project staff and communities; and - Once revisions are completed, the updated EMF will also be made available in public locations; - Environmental Manual and Resource Kit will be developed for use by program staff. The environmental screening and mitigation guidelines and checklists already provided in the EMF will be refined and expanded and included in the Environment Manual and Resource Kit for use by program staff.. - Services of an environment specialist will be hired. Outline TOR and schedule are provided in the EMF document and guidelines. - EPA will continue to act as a service provider during preparation and implementation of the program, and the required financial resources will be provided to EPA from the CISP. (a) carry out the 6-monthly monitoring (b) assist the project to design the environmental training programs and prepare training materials (c) assist the project in the health, environment and sanitation awareness component (HESA). - The Director of the EPA will be a member of the Program Management and Coordination Committee (PMCC). - Linkages of CISP will be developed with other Departments and AJK-EPA activities to enhance environmental benefits of the project, as described in the EMF. - At the time of source selection, water will be tested for biological contamination (e.g. E-coli count). The labs of Health Department will analyze the water. EPA is commissioning a comprehensive statewide study to analyze the quality of drinking water, for physical, chemical and biological parameters. Results of the study will be available before program effectiveness and will inform the nature of testing procedures and mitigation measures to be put in place before and during program implementation, notably in areas where chemical contamination has been detected (e.g. hotspots for fluoride, etc.). - For water quality monitoring, facilities will be created within Health Department / PHED to test water quality as required by the communities (on demand). EPA will monitor periodically a representative sample of water schemes under operation. Water quality indicators will be made available publicly. - The activities under the CISP concerning the environment will be primarily planned and implemented with active participation of the EPA. The CISP will provide a suitable vehicle and operational cost to the EPA to support and monitor the program activities. - The financial requirements for implementing the environmental framework with description and justification are provided in Chapter 8 of the EMF. These costs have been included in relevant components of the PC-1 - Community Development, Decentralized Planning and Implementation, and Incremental Staff. CISP is a project aimed at enhancing environmental conditions of the low-income settlements in rural and urban area. Therefore no specific pollution control measures are required |

D:\cdisp-11-2\pc1-cisp-green.doc

FIGURE 2: CISP IMPLEMENTATION: ORGANIZATIONAL STRUCTURE

Program Implementation

Responsibility Levels

Program Policy and

Approval of Annual Work Plan

Government

of

AJK

Steering

Committee

Policy

-------------------------Overall

Program Management, Coordination and Supervision

----------------------------------

Secretary

LGRDD

Program Management & Coordination Committee (PMCC)

PMCC Secretariat

---------------------------

Program

(Rural/ Urban)

Implementation,

Facilitation &

Monitoring

Attached Department of

LGRD

Local Government Board

Urban Sub Prog.

Rural Sub Prog.

---------------------

# CIS

Sub

Project

Implementation

LG&RD

District Office

Urban Local Authorities M Corp./ MC/ TC

Service Providers(State/ Private) Partner Organizers (e.g. NGOs)

Community Based Organizations

Tentative out line of Terms of Reference for expected Consultants’ Services

### Background

## Introduction: The Government of AJK is planning to launch the Community Infrastructure Services Program (CISP), with financial assistance of IDA of the World Bank , aiming at improving the living conditions of low income communities in AJK through the development and implementation of an effective participation based program to deliver sustainable and affordable infrastructure and services to low income communities.

## CISP: Objectives: The objectives of the proposed program are to;

- deliver cost effective and sustainable community development programs and sustainable  infrastructure services to un-served and under-served, low income rural communities using participatory community based approaches ;

- test models of similar approaches in peri-urban communities;

- strengthening the role and capabilities of the Districts and lower level of local governments to extend technical, financial and management support to the community-based organizations (CBOs);

- increase participation through community development and expanding the number and capacity of community based organizations (CBOs) to increase their participation in development activities; and

- effective governance and accountability through improvement of operational procedures/guidelines, monitoring and evaluation , financial and the budgeting and processing procedures to ensure transparency in the implementation.

It has been envisaged that the above objectives will be achieved through:

- Efficient Governance in the context of decentralized planning and implementation.

- Participation of communities and civil society.

- Provision of infrastructure upgrading and services and community development in low income communities.

Rationale: Low-income communities remain in this position due to variety of reasons. Mainly they have no access to market oriented assets, due to lack of awareness, knowledge and resources. Their problems and needs should be considered in a holistic and integrated development framework giving weight age to capacity building and institutional strengthening at community level. Improving family income through income generation activities and empowering them to join the mainstream of development are essential ingredients.

Community Infrastructure Services Programme aims at sustainable development of under-served and un-served settlements within the socio- economic environment of the AJK, deviating from the conventional top down delivery mechanisms. It is envisaged in this task to create a viable economic and social environment for the community to enter the mainstream of development, so that the burden of the government to maintain these settlements and providing facilities and amenities is reduced. Self-reliance and enhancing family income may answer many issues in this regard. The settlers may be empowered to contribute to the national economy and social development in general. The economic and social upliftment will contribute to the environment improvement and sustainability.  The major factors that contribute to the environmental sustainability is the income,  knowledge and enabling public and local government administration mechanism. It is therefore  important to strengthen the institutional framework back up by the systems and procedures conducive for the community managed initiatives.

As the CISP fosters a new approach to community infrastructure development and  upgrading, the government of AJK  has decided to obtain expert technical inputs to assist the program implementing agencies to develop and adopt a set of procedures, methods, and skills to encourage concerned communities to play an active role in the planning, implementation, operation, maintenance, and financing of community level facilities and services.

TA Objectives and overview: The main objective of the proposed technical assistance Consultancy Services is to obtain competent technical assistance to the CISP program management agencies through experienced professionals who are well acquainted with different aspects of expertise demanded by community program implementation.  The Consultants will assist in program implementation, specially in the areas of community development and procurement and provide facilitation, advice and backstopping support to CISP. Approximately 58 person months(PM) of senior advisors (Community Development Specialist- International 6 PM), Procurement Specialist( National 12 PM) and short term technical assistance (National 40 PM)   is required during the program period, to provide support for the overall management  processes of the program, and in particular, to strengthen the community development component of the project.  Given the skill balance of the team, the advisors should be specialists in working with the private and voluntary sector, and have strong skills in community development and participatory methods.

##### Expected Consultancy Inputs

1	Community Development Specialist-(International):

Time inputs: 	6 Person Months

Background: Community development is the central theme of the programme and hence the CISP would focus much attention on development of appropriate methodologies, procedures and systems for community mobilization and active involvement of user communities in planning, designing, construction and management of infrastructure services through development of participatory techniques by implementing community sub projects during the period of this program.

Scope of Work: to provide support for the overall management processes of the program, and in particular, to strengthen the community development component of the program. The specific tasks would be;

- Review and revise the basic methodology and approach being adopted in the program on Community development and infrastructure improvement

- Refine community sub project implementation procedures and systems in the light of experience gained from the first year community project

Implementation.

- Assess implementation organization (LGRDD District office/Local Councils/  NGOs) capacity and review existing contractual 	agreement with the CBOs.

- Prepare a complete manual for CBOs.

- Undertake training need assessment of NGO/ CBOs for strengthening their capabilities.

- Establish program Implementing Agency performance evaluation system.

- Undertake comprehensive analysis of implementation arrangements of CISP

- Refinement and documentation of relevant policies, procedures and criteria in relation to community development activities

- Development of appropriate methodologies for, establishment and functioning of community development funds as a tool for resource 	mobilization for capital contribution O&M and other community development activities, formulation and strengthening of CBOs, preparation of women development programs

- Coordinate all activities pertaining to review and refinement of community development component program design and follow up project preparation.

In addition to above specific activities, the consultant should provide backstop support mainly through telephone, fax and em communication, during the period  of his non physical availability and, as well as, (b) to provide any project ‘emergency’ support if required and (c) to assist CISP management in coordinating with the Task Leader and the bank staff in Islamabad. The consultants should also provide specific practical advice on any queries the LGRDD, LGB, local bodies/councils may have which can be reasonably accommodated within the resources available to the consultant for the institutional development part of the assignment.

The purpose of this TA assignment to assist CISP program management to execute program to reach its expected outputs and thus community development specialist is supposed to coordinate these consultant inputs as the Team Leader of the TA Program. Specifically it involves following tasks;

- Coordinate all activities carried out under TA Program and report the progress to Sec/ LG&DD

- Review output report and provide comments, guidance for necessary improvements

- Liaise with all stakeholders on TA activities

- Assist LG&RDD to hold TA workshops

- Prepare synthesis report on overall TA Package

Background and qualifications

- A relevant recognized university degree(post Graduate) in social science with extensive experience and qualifications in community based project/ program implementation

- At least 15 years of relevant community based sector experience in project / program planning formulation and implementation, of which minimum of five  years should be in developing countries preferably in Aisa, (Pakistan).

- At least 5 years' international experience in community development in developing countries in Asia.;

- Extensive experience in mobilization strategies for low-income communities.

2.	Procurement Specialist (National):

Time inputs: 12 Person Months

Background: The worldwide evidence on World Bank funded projects and programs concludes that the main reason for their ineffective implementation is the issues associated with procurement. This situation is acute in community projects and program as community procurement systems and procedures are yet to be fully developed.

Scope of work: to provide assistance to the CISP management (LGRDD, LGB and district offices, local councils to undertake their procurement activities. The specific tasks would be;

- Review and revise the procurement methodologies and procedures

- Assess implementation organization (LGRDD District office/Local Councils/  NGOs) procurement capacity and review existing documentation

- Prepare a complete manual for CBOs.

###### Undertake training on procurement matters

- Coordinate all activities pertaining to CISP procurement.

In addition to above specific activities, the consultant should provide backstop support mainly through telephone, fax and em communication, during the period of non physical availability as well as, (b) to provide any project ‘emergency’ support if required and (c) to assist CISP management in coordinating with the Task Leader and the bank staff in Islamabad. The consultants should also provide specific practical advice on any queries the LGRDD, LGB, local bodies/councils may have which can be reasonably accommodated within the resources available to the consultant for the institutional development part of the assignment.

Background and qualifications

- A relevant recognized university degree(post Graduate) in relevant subject with extensive experience and qualifications in handling procurement matters in community based project/ program

- At least 5 years of procurement experience in world bank funded projects / programs

- Short-term Consultants:

Time inputs: 40 person months

Short term consultancy inputs are required to assist the CISP management in specific areas such as monitoring and evaluation, management information system development, engineering designs, financial management, micro credit, institutional ,training and capacity building, and environment etc. The inputs of the short-term consultants would be required for studies and evaluation needed for Mid Term Review of the program and during follow up program preparation. Specific TOR will be developed, as and when necessary, to obtain the services of these short-term consultants.